Angola

Africa | LDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Angola is presented in this country card as part of Africa, with Angola also associated with an unspecified subregion and the LDC grouping. The filtered data for Angola highlights 2 projects for Angola, including 0 active or planned projects for Angola and 2 completed or closed projects for Angola.

For Angola, the report includes 9 requests for Angola, 1 RPTC proposals for Angola, 1 RPTC activities for Angola, and 0 travel records for Angola. Financially, Angola shows USD 1,024,440 in project budget, $45,487 in proposal planned budget, and $194,900 in consumed RPTC activity budget for Angola.

The main organizational coverage for Angola points to Division for Inclusive Social Development, Economic Analysis and Policy Division, Financing for Sustainable Development Office, PD. Activity records for Angola list 82 participants, including 44 women participants, the current quality review for Angola includes 59 data quality notes. Current highlights for Angola include a request focus for Angola: Request #5516 ? This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses.; an RPTC proposal focus for Angola: United Nations Regional Workshop on the 2030 World Programme on Population and Housing Censuses for Francophone Africa: International Standards and Innovative Approaches
; an activity focus for Angola: Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 2 |
| Project budget | USD 1,024,440 |
| Requests | 9 |
| RPTC proposals | 1 |
| Proposal planned budget | $45,487 |
| RPTC activities | 1 |
| Consumed RPTC budget | $194,900 |
| Activity participants | 82 |
| Women participants | 44 |
| Travel records | 0 |
| Evaluations | 5 |
| Data quality notes | 59 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inclusive development for indigenous peoples in Africa | 2023C | country | Division for Inclusive Social Development | Closed | 01 Jan 2020 | 30 Jun 2023 | USD 664,440 | Angola, Namibia, Uganda, Zimbabwe |  |
| Strengthening capacity of National Tax Administrations And Ministries of Finance in developing countries to protect and broaden their tax base for financing of sustainable development | 1415AV | country | Financing for Sustainable Development Office | Closed | 14 May 2020 | 17 Dec 2020 | USD 360,000 | Angola, Dominican Republic, Panama, Paraguay, Trinidad and Tobago, United Republic of Tanzania | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5516 | Request #5516 ? This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Completed | Statistics Division | 14 May 2026 | 15 Jun 2026 | 19 Jun 2026 | Seiffe Tadesse ¦ tadesse5@un.org | This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 5168 | Request #5168 ? Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. | Completed | Statistics Division | 17 Jan 2025 | 1 | 1 | Deepchandsingh Jagai ¦ djagai@sadc.int | Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. |  |  |
| 5061 | Request #5061 ? Support the Angolan Government, through the Department for International Cooperation of the Ministry of Planning, and the UN Resident Coordinator's Office, in their efforts to identify SDG-aligned investment projects and to mobilize private financing through a future SDG Investment Fair. | Ongoing | Financing for Sustainable Development Office | 01 Sept 2024 | 01 Sept 2024 | 31 Jul 2025 | Gil Matos Henriques ¦ gil.henriques@mep.gov.ao | Support the Angolan Government, through the Department for International Cooperation of the Ministry of Planning, and the UN Resident Coordinator's Office, in their efforts to identify SDG-aligned investment projects and to mobilize private financing through a future SDG Investment Fair. |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4020 | Request #4020 ? The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. | Completed | Economic Analysis and Policy Division | 18 Nov 2021 | 01 Jan 2022 | 31 Jan 2022 | Namsuk Kim ¦ kimnamsuk@un.org | The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. |  |  |
| 3915 | Request #3915 ? The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. | Completed | Economic Analysis and Policy Division | 10 May 2021 | 26 Jun 2021 | 15 Dec 2021 | Namsuk Kim ¦ kimnamsuk@un.org | The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. |  |  |
| 3575 | Request #3575 ? To provide benchmarks on National Platform on SDG | Completed | Statistics Division | 05 Dec 2019 | 12 Dec 2019 | 12 Dec 2019 | Paolo Balladelli ¦ paolo.balladelli@un.org | To provide benchmarks on National Platform on SDG |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.21 | United Nations Regional Workshop on the 2030 World Programme on Population and Housing Censuses for Francophone Africa: International Standards and Innovative Approaches / | SD | 30 Jun 2026 | 30 Jun 2026 | $45,487 | Algeria, Angola, Benin, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Equatorial Guinea, Gabon, Guinea, Guinea-Bissau, Madagascar, Mali, Mauritania, Morocco, Niger, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Togo, Tunisia | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Inclusive Development for Indigenous Peoples in Africa | 2024 | DISD; CDPMO | Angola, Botswana, Burundi, Kenya, Malawi, Mozambique, Namibia, South Africa, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Design and implement, with the participation of target governments and Indigenous Peoples, a second phase of the project to continue processes initiated in target countries, including developing Free, Prior and Informed Consent (FPIC) mechanisms, Indigenous Peoples' Analysis (IPA) per country/region, and supporting institutional capacity. / - Engage other bilateral and multilateral donors such as USAID, European Union, World Bank, and African Development Bank to mobilize technical and financial support, ensuring meaningful participation of Indigenous Peoples. / - Increase engagement with Indigenous Peoples in target countries by setting mechanisms to increase diversity and reach Indigenous Peoples in remote areas, supporting their participation in project activities and political processes. / - Increase the incorporation of United Nations Resident Coordinators and Country Teams into the project to enable conversations and support Indigenous Peoples' rights, engaging them in the development of Development Assistance Frameworks and country program action plans. / - Expand dialogue and training on Indigenous women, youth, and other groups in society that remain invisible, implementing the project through intersectional lenses and ensuring sufficient financial and technical capacity. / - Improve data collection, monitoring and evaluation, and database management, developing indicators in cooperation with Indigenous Peoples and target governments, and ensuring relevant qualitative indicators are set from the beginning of the project. | - Development approaches that respect Indigenous Peoples’ rights and engage them as partners in design, implementation, management, administration, monitoring, and evaluation are vital to achieving the 2030 Sustainable Development Goals. / - Flexibility and adaptability are essential in project implementation to respond to emerging needs and local contexts, as demonstrated by the development of a conservation toolkit and COVID-19 materials. / - Ownership of the process by Indigenous Peoples and stakeholders at different levels is key to sustainability and success. / - Capacity development and participatory approaches are effective in strengthening national capacities and advancing policy drafts, but institutionalization and political support are necessary for long-term impact. / - Ensuring diversity and inclusion, particularly of Indigenous women and youth, requires targeted activities and proactive engagement strategies. / - Improved monitoring mechanisms, data collection, and systematic evaluation are needed to better assess project outcomes and inform future efforts. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/2023C SB-014517 Indigenous in Africa/Evaluation/DESA_2023C_Evaluation report_Mngt response.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening statistical capacity-building in support of progress towards the Internationally Agreed Development Goals in the Southern African Development Community (SADC) region | 2011 | UNSD | Angola, Botswana, Democratic Republic of the Congo, Eswatini, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, United Republic of Tanzania, Zambia, Zimbabwe |  | - Focus on a single objective to make project planning and evaluation more manageable and effective. / - Put more effort into developing indicators that encompass quantity, quality, and time, and that can be reliably calculated with minimal resources. / - Build production of monitoring and evaluation indicators into the project by providing appropriate budget, staffing, data sources, and procedures in project planning. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 86 - Support to MDGs in SADC/Eval Report Feeney/UNSD-SADC Final Evaluation Report.pdf | Country standardized: 'DR Congo' -> 'Democratic Republic of the Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 2 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 3 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 4 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 5 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 6 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 7 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 8 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 9 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 10 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 11 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 12 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 13 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 45 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 46 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 59 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |