Botswana

Africa | LLDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Botswana is presented in this country card as part of Africa, with Botswana also associated with an unspecified subregion and the LLDC grouping. The filtered data for Botswana highlights 3 projects for Botswana, including 2 active or planned projects for Botswana and 1 completed or closed projects for Botswana.

For Botswana, the report includes 12 requests for Botswana, 2 RPTC proposals for Botswana, 2 RPTC activities for Botswana, and 1 travel records for Botswana. Financially, Botswana shows USD 1,875,400 in project budget, $81,072 in proposal planned budget, and $250,972 in consumed RPTC activity budget for Botswana.

The main organizational coverage for Botswana points to DISD, Division for Inclusive Social Development, Division for Public Institutions and Digital Government, FSDO. Activity records for Botswana list 132 participants, including 71 women participants, the current quality review for Botswana includes 62 data quality notes. Current highlights for Botswana include a request focus for Botswana: Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026)

      
This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA).

      
The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs).

      
Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop.

      
The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA.; an RPTC proposal focus for Botswana: Promoting social inclusion through the creative economy in Botswana and Namibia; an activity focus for Botswana: Promoting social inclusion through the creative economy in Botswana and Namibia.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 3 |
| Project budget | USD 1,875,400 |
| Requests | 12 |
| RPTC proposals | 2 |
| Proposal planned budget | $81,072 |
| RPTC activities | 2 |
| Consumed RPTC budget | $250,972 |
| Activity participants | 132 |
| Women participants | 71 |
| Travel records | 1 |
| Evaluations | 9 |
| Data quality notes | 62 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Promoting a socially inclusive creative economy to support the digital transformation needs of small island developing States and the least developed countries | 2629D | country | Division for Inclusive Social Development | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 640,000 | Botswana, Democratic Republic of Timor-Leste, Indonesia, Madagascar | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| Promoting agricultural cooperatives in sub-Saharan Africa to enhance resilience and adaptation of small-holder farmers to climate change | 2528C | country | Division for Inclusive Social Development | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 647,400 | Botswana, Cameroon, Ghana, United Republic of Tanzania | Duplicate review: selected this entry and excluded projects.csv row 71. |
| Strengthening capacities of developing countries in sub-Saharan Africa to effectively produce and use population estimates and projections in policy-making for sustainable development | ROA 262 | country | Population Division | Closed | 14 Jun 2020 | 17 Dec 2020 | USD 588,000 | Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Djibouti, Ethiopia, Gabon, Ghana, Kenya, Mali, Namibia, Niger, Nigeria, Senegal, Togo, Uganda, Zambia |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5463 | Request #5463 ? To support Youth Creative Workshop | Under consideration | Division for Inclusive Social Development | 10 Dec 2025 | 01 Jan 2026 | 01 Jan 2028 | Mr. Nkoloi Nkoloi ¦ nncoloi@gov.bw | To support Youth Creative Workshop |  |  |
| 5389 | Request #5389 ? RCO Botswana requested DESAâ€™s support for targeted capacity-building and technical guidance to help Botswana establish a more structured approach to SDG localization and VLR preparation. Botswana will present VNR in 2027. So, support is requested in Q2/2026. | Under consideration | Division for Sustainable Development Goals | 29 Nov 2025 | 01 Apr 2026 | 31 Jul 2027 | Wenyan Yang ¦ yang@un.org | RCO Botswana requested DESAâ€™s support for targeted capacity-building and technical guidance to help Botswana establish a more structured approach to SDG localization and VLR preparation. Botswana will present VNR in 2027. So, support is requested in Q2/2026. |  |  |
| 5379 | Request #5379 ? UNDESA/DISD has received a request for cooperation from the United / Nations Resident Coordinator Office in Botswana, to support activities that / will address the Governmentâ€™s intention to address the countryâ€™s potential / in the creative economy. / Botswanaâ€™s Vision 2036 and National Development Plans explicitly / emphasize economic diversification with a shift from its reliance in diamond / mining. Its rich cultural heritage offers strong foundations for creative / industries, and National strategies such as the Economic Recovery and / Transformation Plan include tourism, arts, media, and digital industries as / key sectors for job creation and innovation. Social inclusion remains a / significant challenge due to a complex interplay of structural, economic, and / socio-political factors, aggravated by inequality which persists and even / expands. / UN General Assembly Resolution 78/133 entitled â€˜Promoting creative / economy for sustainable developmentâ€ highlights the importance of the / creative economy in implementing the 2030 Agenda for Sustainable / Development and invites Member States to â€œpromote the inclusion and / mainstreaming of the creative economy into economic policy, as well as in / national and international development plans and strategiesâ€. / The policy advisory mission will be a unique opportunity to exchange with / key strategic stakeholders from Government, the private sector, workersâ€™ / organizations, civil society and development partners in Botswana and to / explore potential for further collaboration, notably in the aftermath of the / second world summit for social development (WSSD2). | Ongoing | Division for Inclusive Social Development | 13 Nov 2025 | 01 Dec 2025 | 05 Dec 2025 | Ms. Wenyan Yang ¦ yang@un.org | UNDESA/DISD has received a request for cooperation from the United / Nations Resident Coordinator Office in Botswana, to support activities that / will address the Governmentâ€™s intention to address the countryâ€™s potential / in the creative economy. / Botswanaâ€™s Vision 2036 and National Development Plans explicitly / emphasize economic diversification with a shift from its reliance in diamond / mining. Its rich cultural heritage offers strong foundations for creative / industries, and National strategies such as the Economic Recovery and / Transformation Plan include tourism, arts, media, and digital industries as / key sectors for job creation and innovation. Social inclusion remains a / significant challenge due to a complex interplay of structural, economic, and / socio-political factors, aggravated by inequality which persists and even / expands. / UN General Assembly Resolution 78/133 entitled â€˜Promoting creative / economy for sustainable developmentâ€ highlights the importance of the / creative economy in implementing the 2030 Agenda for Sustainable / Development and invites Member States to â€œpromote the inclusion and / mainstreaming of the creative economy into economic policy, as well as in / national and international development plans and strategiesâ€. / The policy advisory mission will be a unique opportunity to exchange with / key strategic stakeholders from Government, the private sector, workersâ€™ / organizations, civil society and development partners in Botswana and to / explore potential for further collaboration, notably in the aftermath of the / second world summit for social development (WSSD2). |  |  |
| 5235 | Request #5235 ? The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Under consideration | Statistics Division | 11 Jun 2025 | 11 Jun 2025 | 05 Dec 2025 | Matthias Reister ¦ reister@un.org | The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 5168 | Request #5168 ? Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. | Completed | Statistics Division | 17 Jan 2025 | 1 | 1 | Deepchandsingh Jagai ¦ djagai@sadc.int | Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4097 | Request #4097 ? DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Completed | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals | 15 Feb 2022 | 28 Mar 2022 | 29 Mar 2022 | Eddy Maloka ¦ eddy.maloka@aprm-au.org | DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 3900 | Request #3900 ? DPIDG was requested by the International Association of Schools and Institutes of Administration (IASIA) to provide support in enhancing the capacities of governments in Africa to promote public service innovation and digital government for SDGs. | Completed | Division for Public Institutions and Digital Government | 07 Feb 2019 | 26 Jul 2021 | 30 Jul 2021 | Garegin Manukyan ¦ manukyan@un.org | DPIDG was requested by the International Association of Schools and Institutes of Administration (IASIA) to provide support in enhancing the capacities of governments in Africa to promote public service innovation and digital government for SDGs. |  |  |
| 2778 | Request #2778 ? Advisory service, capacity building workshop and validation workshop, support for drafting documents are the major technical content of the support. | Completed | United Nations Forum on Forest | 22 Jan 2018 | 01 Jul 2019 | 31 May 2021 | Manthe Tsuaneng ¦ bbabusi@gov.bw | Advisory service, capacity building workshop and validation workshop, support for drafting documents are the major technical content of the support. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001379.99.25 | Promoting social inclusion through the creative economy in Botswana and Namibia | DISD | 06 Jun 2026 | 06 Jun 2026 | $56,072 | Botswana, Namibia |  | Proposal past due |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001379.99.25 | Promoting social inclusion through the creative economy in Botswana and Namibia | DISD | 01 Jun 2026 | 05 Jun 2026 | $56,072 | 50 | 27 |  |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002289865 - Botswana | 0002289865 | Past | Botswana |  | DIVISION FOR INCLUSIVE SOCIAL DEVELOPMENT | WORKSHOP ON SOCIAL INCLUSION IN THE CREATIVE ECONOMY |  | 30 May 2026 | 08 Jun 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Inclusive Development for Indigenous Peoples in Africa | 2024 | DISD; CDPMO | Angola, Botswana, Burundi, Kenya, Malawi, Mozambique, Namibia, South Africa, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Design and implement, with the participation of target governments and Indigenous Peoples, a second phase of the project to continue processes initiated in target countries, including developing Free, Prior and Informed Consent (FPIC) mechanisms, Indigenous Peoples' Analysis (IPA) per country/region, and supporting institutional capacity. / - Engage other bilateral and multilateral donors such as USAID, European Union, World Bank, and African Development Bank to mobilize technical and financial support, ensuring meaningful participation of Indigenous Peoples. / - Increase engagement with Indigenous Peoples in target countries by setting mechanisms to increase diversity and reach Indigenous Peoples in remote areas, supporting their participation in project activities and political processes. / - Increase the incorporation of United Nations Resident Coordinators and Country Teams into the project to enable conversations and support Indigenous Peoples' rights, engaging them in the development of Development Assistance Frameworks and country program action plans. / - Expand dialogue and training on Indigenous women, youth, and other groups in society that remain invisible, implementing the project through intersectional lenses and ensuring sufficient financial and technical capacity. / - Improve data collection, monitoring and evaluation, and database management, developing indicators in cooperation with Indigenous Peoples and target governments, and ensuring relevant qualitative indicators are set from the beginning of the project. | - Development approaches that respect Indigenous Peoples’ rights and engage them as partners in design, implementation, management, administration, monitoring, and evaluation are vital to achieving the 2030 Sustainable Development Goals. / - Flexibility and adaptability are essential in project implementation to respond to emerging needs and local contexts, as demonstrated by the development of a conservation toolkit and COVID-19 materials. / - Ownership of the process by Indigenous Peoples and stakeholders at different levels is key to sustainability and success. / - Capacity development and participatory approaches are effective in strengthening national capacities and advancing policy drafts, but institutionalization and political support are necessary for long-term impact. / - Ensuring diversity and inclusion, particularly of Indigenous women and youth, requires targeted activities and proactive engagement strategies. / - Improved monitoring mechanisms, data collection, and systematic evaluation are needed to better assess project outcomes and inform future efforts. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/2023C SB-014517 Indigenous in Africa/Evaluation/DESA_2023C_Evaluation report_Mngt response.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level | 2015 | UNSD | Algeria, Argentina, Bangladesh, Bolivia (Plurinational State of), Botswana, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Chile, Costa Rica, Côte d’Ivoire, Ecuador, Egypt, Ethiopia, Guyana, Jordan, Kenya, Korea, Lebanon, Madagascar, Morocco, Nigeria, South Africa, State of Palestine, Sudan, Togo, Tunisia, Uganda, Uruguay | - Create conditions to improve the technological and knowledge transfer from developed to developing countries. / - Widely promote the adoption of internationally accepted standards related to the generation, process, dissemination and use of geospatial information, created by major standards organizations such as ISO/TC211, OGC, and IHO. / - Include the integration of statistical and geospatial information as a core issue in the UN-GGIM plan work for developing countries, especially in support of the 2020 Round of Censuses and Big Data. / - Continue the work with support of the regional committees of UN-GGIM and the countries themselves to encourage the building of spatial data infrastructures. / - Raise the awareness of the importance of geospatial information at the policy and decision making levels, and strengthen human capacities in developing countries through comprehensive trainings on geodesy, cartography, remote sensing, GIS, and geostatistical mapping. | - The Steering Committee and UNSD/DESA played an important role in aligning the deliveries of the project. / - UNSD/DESA-led projects are effective in connecting experts with organizations and countries interested in geospatial knowledge. / - At a global level, only an organization such as the UN through UNSD/DESA has the capacity to convene and lead projects of this magnitude. / - Developing countries need to increase their technological capacities, which requires more financial resources. / - Improving geospatial information management requires the creation of policies, rules, and methods for information generation, management, dissemination, and use. / - Increasing awareness and support for geospatial and statistical activities among high-level politicians and decision makers is necessary. / - Specialized human resources training is essential for functional geospatial information, beyond just technical, financial, and methodological resources. / - The information exchange mechanism used in this project was effective, allowing developing countries to learn from best practices. / - Institutional coordination between geospatial and statistical offices is still a work in progress and needs to be strengthened. / - Significant gaps in geospatial data and infrastructure exist in developing countries, and this project has helped indicate the right direction. / - There is a lack of economic resources to keep information updated in some developing countries. / - Technological capacities related to geospatial information need to be upgraded. / - There is still a lack of policies, rules, and methods for geospatial information management in some developing countries. / - Specialized human resources training in geospatial disciplines and statistics is essential. / - Strong efforts are needed to create and maintain spatial data infrastructures at all levels, considering the Global Geodetic Reference Frame. / - Awareness and support for geospatial and statistical activities from high-level decision makers need improvement. / - The 2030 Sustainable Development agenda and the 2020 Round of Censuses should be leveraged to reinforce the use of geospatial and statistical data, with executional and follow-up mechanisms for expected outcomes. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 212 - 8th tranche - Geospatial/Evaluation report/Evaluation Report- DA Project-212-8.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Cote d’Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening statistical capacity-building in support of progress towards the Internationally Agreed Development Goals in the Southern African Development Community (SADC) region | 2011 | UNSD | Angola, Botswana, Democratic Republic of the Congo, Eswatini, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, United Republic of Tanzania, Zambia, Zimbabwe |  | - Focus on a single objective to make project planning and evaluation more manageable and effective. / - Put more effort into developing indicators that encompass quantity, quality, and time, and that can be reliably calculated with minimal resources. / - Build production of monitoring and evaluation indicators into the project by providing appropriate budget, staffing, data sources, and procedures in project planning. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 86 - Support to MDGs in SADC/Eval Report Feeney/UNSD-SADC Final Evaluation Report.pdf | Country standardized: 'DR Congo' -> 'Democratic Republic of the Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies | 2015 | DPAD | Afghanistan, Bangladesh, Bhutan, Botswana, Cambodia, Chile, China, Democratic Socialist Republic of Sri Lanka, Eswatini, India, Indonesia, Kazakhstan, Korea, Lao People's Democratic Republic, Lesotho, Mozambique, Myanmar, Namibia, Nepal, Philippines, Singapore, South Africa, Tajikistan, Thailand, Uzbekistan, Viet Nam, Zambia | - Future capacity development projects of UNDESA should be sufficiently ambitious in their objectives but designed with adequate flexibility to deliver capacity development objectives in a demand-driven and nationally-owned manner. / - Future projects should ensure sufficient flexibility in the activities listed in project documents, making the list of activities indicative and not a binding constraint. / - Future training workshops should allocate additional time for discussion among participants and distribute research and background papers in advance. / - Future capacity development projects should include a post-project phase engagement framework to ensure sustainability of project interventions, especially since UNDESA is a non-resident entity. / - Future projects should earmark resources to facilitate the deployment of experts from other UN agencies to reduce dependence on external consultants. / - Future capacity development projects should make fostering South-South Cooperation a stated objective, with a clear focus on enabling developing countries to learn from each other. / - Future projects may devote technical and financial resources to develop an online forum to ensure the sustainability of interventions beyond completion. / - Future projects would benefit from having a clear and well-defined monitoring and evaluation strategy, including early recruitment of an external evaluator and allocation of resources for field visits and online evaluation tools. / - UNDESA should continue to provide policy-advisory and capacity development support to beneficiary countries and add a few additional countries to ensure sustainability of the impacts. | - An integrated approach, building on previous successful projects and deepening engagement in a few countries, leads to significant multiplier effects, cost-savings, and greater policy impact. / - Flexibility and improvisation in project implementation allow for responsiveness to evolving needs and ensure country ownership, rather than following a rigid, pre-determined set of activities. / - There is greater demand for country-specific, evidence-based policy advice than for generic handbooks or textbooks. / - Partnerships with other UN agencies, especially UNDP and regional commissions, are key to sustaining project impact and should be further strengthened. / - South-South cooperation, though not a stated objective, emerged as a valuable outcome and should be explicitly included in future project objectives. / - Establishing online communities or networks for trained officials and trainers can help sustain knowledge exchange and learning beyond project completion. / - A clear and well-defined monitoring and evaluation strategy, including early involvement of external evaluators and use of online tools, improves the quality and comprehensiveness of project evaluation. / - The project generated new requests for support from additional countries, indicating the importance of maintaining and expanding capacity development support to ensure sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/6th tranche/ROA 182 (DPAD)/Final Evaluation Report of MAC - Complete.pdf | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Vietnam' -> 'Viet Nam'. | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening national capacity for the implementation of the Global HIV Prevention Coalition Roadmap | 2020 |  | Botswana, Kenya, Lesotho, Malawi, Namibia, Uganda, Zambia, Zimbabwe | - Consider a no-cost extension to enable utilisation of the unexpended funds to contribute to the impact and sustainability of results and, as part of this, consider funding a coordination post within country prevention coalitions. / - Reduce the reporting burden required for accountability of budget expenditures in order to reduce the level of effort required for compliance. / - Increase justified flexibility between budget lines to ensure optimal impact of expenditures according to emerging needs. / - Ensure effective project oversight and management with contingency planning and consolidated hand-over when staff change. / - Once the above is in place, and with redesigned costed work plans, apply for a no-cost extension to the end of 2021, based on specific priorities in the project countries. / - If feasible, consider contributing project funding for a full-time staff coordination post for prevention within country coalitions, either within the NAC or UNAIDS country office (this also aligns with a recommendation from the GPC review), e.g. UNV, and/or long-term consultancy positions; and seek to mobilise additional funding from other sources for dedicated prevention staff. / - Consider again sub-contracting/engaging ATHENA Initiative to augment further the capacity development among young women leaders in the focal countries to consolidate their impact. / - Consider whether to widen the focus to additional countries should any remain significantly behind regarding building leadership capacity among adolescent girls and young women. Weigh this against the benefit of consolidating gains in the existing countries and providing robust lessons for south to south learning to feed into existing GPC initiatives (such as the NAC community of practice and the South to South Learning Network). / - To improve efficiencies, should there be a no-cost extension, designate a staff member to oversee project implementation and put in place a robust hand-over mechanism in the event of staff changes. / - Identify funding needs to address gaps in capacity development, particularly among adolescent girls and young women, and develop a related capacity development and technical assistance plan. / - Continue to engage capacitated networks of adolescent and young women and implement mechanisms to provide them with small grants for specific events and activities. | - Even relatively small, short-term grants can be catalytic in impact and sustainability of results if timely, strategic and appropriately focused. / - Networks can be greatly strengthened by small, targeted grants for specific activities that build experience and credibility for effective management, and hence eligibility for other funding sources. / - The flexibility in use of project funds, while aligned to the original project objectives, was important in facilitating justified expenditures against changing work plans, and this should continue as good practice. / - Sufficient attention needs to be given to project oversight at both global and country levels, with sufficient hand over when staffing changes. / - Without first ensuring conformity with organisational rules and regulations and adequate oversight, available funds may not be efficiently utilised despite their high relevance to country needs. / - Care is needed to ensure that the mechanisms for utilisation of funds, e.g. for short-term consultancies, are not unduly burdensome, with respect to both initial budget lines and to opportunities for expenditure. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2020_PDF-SDG-2017-06_Eval_UNAIDS.pdf |  | evaluations.xlsx row 253: Divisions not provided. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 2 | evaluations.xlsx row 253: Divisions not provided. |
| 3 | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 6 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 7 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 8 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 9 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 10 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 11 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 12 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 13 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 14 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 15 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 48 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 62 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |