Colombia

Americas

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Colombia is presented in this country card as part of Americas, with Colombia also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Colombia highlights 7 projects for Colombia, including 3 active or planned projects for Colombia and 4 completed or closed projects for Colombia.

For Colombia, the report includes 30 requests for Colombia, 4 RPTC proposals for Colombia, 2 RPTC activities for Colombia, and 1 travel records for Colombia. Financially, Colombia shows USD 5,806,400 in project budget, $115,474 in proposal planned budget, and $201,588 in consumed RPTC activity budget for Colombia.

The main organizational coverage for Colombia points to Division for Sustainable Development Goals, Economic Analysis and Policy Division, Financing for Sustainable Development Office, FSDO. Activity records for Colombia list 1,381 participants, including 709 women participants, the current quality review for Colombia includes 60 data quality notes. Current highlights for Colombia include a request focus for Colombia: Request #5590 ? The International Workshop on the Measurement and Reporting of SDG Indicator 5.4.1, will provide an interregional platform for countries from Latin America and the Caribbean, Asia and the Arab States to assess the current state of measurement and reporting, identify methodological and reporting challenges, and exchange practical experiences. UNSD will contribute global methodological expertise, international standards and relevant country and regional experience to strengthen participantsâ€™ capacity to produce, compile and report high-quality, comparable data on unpaid domestic and care work.

      
As co-custodian of SDG indicator 5.4.1, Secretariat of the IAEG-GS, and lead of the Global Gender Statistics Programme, UNSD will serve as a technical resource for the workshop. Its contribution will connect global methodological guidance and standards with country experiences and needs; support the implementation of international standards; facilitate South-South and interregional learning; and identify priorities and opportunities for coordinated technical assistance and sustained capacity development.

      
In addition to the workshop, UNSD will participate in the XXVII International Meeting on Gender Statistics as a complementary activity. UNSD has been invited to serve as a panellist in sessions on time-use statistics and gender and climate change statistics and to participate in a closed meeting of the Statistical Conference of the Americas Working Group on updating the Classification of Time-Use Activities for Latin America and the Caribbean (CAUTAL). These engagements will broaden knowledge exchange on emerging and persistent gender-statistics issues and reinforce the workshopâ€™s capacity-development objectives. RPTC funding is requested exclusively for essential travel of UNSD/DESA staff and consultants required to deliver these technical contributions.; an RPTC proposal focus for Colombia: Workshop on the use of interoperability standards for the management of geographical names “Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals and the Semantic Web”; an activity focus for Colombia: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 7 |
| Project budget | USD 5,806,400 |
| Requests | 30 |
| RPTC proposals | 4 |
| Proposal planned budget | $115,474 |
| RPTC activities | 2 |
| Consumed RPTC budget | $201,588 |
| Activity participants | 1,381 |
| Women participants | 709 |
| Travel records | 1 |
| Evaluations | 6 |
| Data quality notes | 60 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Accelerating implementation of Data for Now in Colombia and Senegal |  | country | Statistics Division | Closed | 01 May 2020 | 31 Dec 2021 | USD 50,000 | Colombia, Senegal |  |  |
| Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. | 2326A | country | Population Division | Active |  |  | USD 880,000 | Colombia, Costa Rica, Jamaica, Lao People's Democratic Republic, Malaysia, Maldives, Uruguay, Viet Nam | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ ¦ 2326A': End Date End Date is blank. / projects.csv record 'Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ ¦ 2326A': Start Date Start Date is blank. |
| Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people | 2629C | country | United Nations Forum on Forest | Active | 02 Feb 2026 | 31 Dec 2029 | USD 634,400 | Bolivia (Plurinational State of), Colombia, Guyana, Peru |  |  |
| Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries | 1415I | country | Division for Sustainable Development Goals | Closed | 15 Aug 2020 | 17 Dec 2020 | USD 639,000 | Belize, Colombia, Ethiopia, Honduras, Jordan |  | projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Eastern Africa' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Latin America and the Caribbean' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'South America' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Western Asia' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Eastern Africa' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Latin America and the Caribbean' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'South America' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Western Asia' was not matched to GeoData and was ignored. |
| Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises | 2427I | country | Economic Analysis and Policy Division | Active | 01 Feb 2024 | 01 Dec 2027 | USD 650,000 | Colombia, Malawi, Nepal |  |  |
| Strengthening capacity of National Tax Administrations in developing countries to effectively negotiate and apply double tax treaties for financing of sustainable development | 1415A | country | Financing for Sustainable Development Office | Closed | 15 Jan 2020 | 18 Sept 2020 | USD 632,000 | Barbados, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Jamaica, Mexico, Nicaragua, Panama, Paraguay, Peru, Trinidad and Tobago, Uruguay, Venezuela (Bolivarian Republic of) |  |  |
| Towards integrated national financing framework | 2124A | country | Financing for Sustainable Development Office | Closed | 01 Mar 2021 | 28 Jun 2024 | USD 2,321,000 | Belarus, Burkina Faso, Colombia, Costa Rica, Egypt, Indonesia, Jordan, Kyrgyzstan, Pakistan, Zambia |  |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5590 | Request #5590 ? The International Workshop on the Measurement and Reporting of SDG Indicator 5.4.1, will provide an interregional platform for countries from Latin America and the Caribbean, Asia and the Arab States to assess the current state of measurement and reporting, identify methodological and reporting challenges, and exchange practical experiences. UNSD will contribute global methodological expertise, international standards and relevant country and regional experience to strengthen participantsâ€™ capacity to produce, compile and report high-quality, comparable data on unpaid domestic and care work. / As co-custodian of SDG indicator 5.4.1, Secretariat of the IAEG-GS, and lead of the Global Gender Statistics Programme, UNSD will serve as a technical resource for the workshop. Its contribution will connect global methodological guidance and standards with country experiences and needs; support the implementation of international standards; facilitate South-South and interregional learning; and identify priorities and opportunities for coordinated technical assistance and sustained capacity development. / In addition to the workshop, UNSD will participate in the XXVII International Meeting on Gender Statistics as a complementary activity. UNSD has been invited to serve as a panellist in sessions on time-use statistics and gender and climate change statistics and to participate in a closed meeting of the Statistical Conference of the Americas Working Group on updating the Classification of Time-Use Activities for Latin America and the Caribbean (CAUTAL). These engagements will broaden knowledge exchange on emerging and persistent gender-statistics issues and reinforce the workshopâ€™s capacity-development objectives. RPTC funding is requested exclusively for essential travel of UNSD/DESA staff and consultants required to deliver these technical contributions. | Under consideration | Statistics Division | 22 Sept 2026 | 26 Oct 2026 | 30 Oct 2026 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The International Workshop on the Measurement and Reporting of SDG Indicator 5.4.1, will provide an interregional platform for countries from Latin America and the Caribbean, Asia and the Arab States to assess the current state of measurement and reporting, identify methodological and reporting challenges, and exchange practical experiences. UNSD will contribute global methodological expertise, international standards and relevant country and regional experience to strengthen participantsâ€™ capacity to produce, compile and report high-quality, comparable data on unpaid domestic and care work. / As co-custodian of SDG indicator 5.4.1, Secretariat of the IAEG-GS, and lead of the Global Gender Statistics Programme, UNSD will serve as a technical resource for the workshop. Its contribution will connect global methodological guidance and standards with country experiences and needs; support the implementation of international standards; facilitate South-South and interregional learning; and identify priorities and opportunities for coordinated technical assistance and sustained capacity development. / In addition to the workshop, UNSD will participate in the XXVII International Meeting on Gender Statistics as a complementary activity. UNSD has been invited to serve as a panellist in sessions on time-use statistics and gender and climate change statistics and to participate in a closed meeting of the Statistical Conference of the Americas Working Group on updating the Classification of Time-Use Activities for Latin America and the Caribbean (CAUTAL). These engagements will broaden knowledge exchange on emerging and persistent gender-statistics issues and reinforce the workshopâ€™s capacity-development objectives. RPTC funding is requested exclusively for essential travel of UNSD/DESA staff and consultants required to deliver these technical contributions. | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| 5567 | Request #5567 ? The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 Dec 2026 | Kimberly Bordon ¦ kbordon@aladi.org | The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. |  |
| 5498 | Request #5498 ? The invitation relates to participation as a panelist in the session â€œThe Role of the Friends of Official Statistics (FoS) Network in Upholding the Fundamental Principles of Official Statistics (FPOS)â€. The Scientific Programme Committee is responsible for the conference programme and includes members from developing countries, including Nthabiseng Makhata (South Africa), Mahinthan Mariasingham (Philippines) and Camilo Mendez (Colombia). | Under consideration | Statistics Division | 20 Mar 2026 | 12 May 2026 | 14 May 2026 | Misha Belkindas ¦ MishaBelkindas@opendatawatch.com | The invitation relates to participation as a panelist in the session â€œThe Role of the Friends of Official Statistics (FoS) Network in Upholding the Fundamental Principles of Official Statistics (FPOS)â€. The Scientific Programme Committee is responsible for the conference programme and includes members from developing countries, including Nthabiseng Makhata (South Africa), Mahinthan Mariasingham (Philippines) and Camilo Mendez (Colombia). |  |
| 5377 | Request #5377 ? A total RPTC budget of US$20,000 is proposed to cover the consultancy fee for the development of these training materials, which will serve as a practical resource for statisticians, policymakers, and capacity-building initiatives across countries. / Background: Existing international standards and tools, developed under the UNSD migration statistics programme and endorsed by the Statistical Commission, provide a strong foundation for this work. These include the revised Recommendations on Statistics of International Migration and Temporary Mobility, and the accompanying technical reports on core and additional indicators, data integration, operationalization of the conceptual framework and data sources, and communication in the context of migration statistics, which together ensure comparable, high-quality data across countries. The consultancy will develop user-friendly training materials to support national statistical offices in applying these standards, operationalizing the conceptual framework as contained in the revised Recommendations, and producing reliable and comparable international migration statistics. | Completed | Statistics Division | 12 Nov 2025 | 01 Dec 2025 | 31 Mar 2026 | Maria Isabel Cobos ¦ cobos@un.org | A total RPTC budget of US$20,000 is proposed to cover the consultancy fee for the development of these training materials, which will serve as a practical resource for statisticians, policymakers, and capacity-building initiatives across countries. / Background: Existing international standards and tools, developed under the UNSD migration statistics programme and endorsed by the Statistical Commission, provide a strong foundation for this work. These include the revised Recommendations on Statistics of International Migration and Temporary Mobility, and the accompanying technical reports on core and additional indicators, data integration, operationalization of the conceptual framework and data sources, and communication in the context of migration statistics, which together ensure comparable, high-quality data across countries. The consultancy will develop user-friendly training materials to support national statistical offices in applying these standards, operationalizing the conceptual framework as contained in the revised Recommendations, and producing reliable and comparable international migration statistics. |  |
| 5373 | Request #5373 ? There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 May 2026 | Kimberly Bordon ¦ kbordon@aladi.org | There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. |  |
| 5361 | Request #5361 ? The Partnership in Statistics for Development in the 21st Century (PARIS21) aims to improve the production, quality, availability and use of statistics for informed decision-making and sustainable development. Established in 1999 by the United Nations, the European Commission, the Organisation for Economic Co-operation and Development (OECD), the International Monetary Fund and the World Bank, PARIS21 works with governments, international organizations, civil society and other stakeholders to strengthen national statistical systems, particularly in low- and middle-income countries. / The 2025 PARIS21 Annual Board and Partnership Meetings, to be held in Paris on 5â€“6 November 2025, - preparatory meetings are taking place on 4 November 2025 - will provide a platform to discuss coordinated and sustainable support for statistical capacity development, with a focus on Least Developed Countries (LDCs), Landlocked Developing Countries (LLDCs) and Small Island Developing States (SIDS). / Participation by the United Nations Statistics Division (UNSD) will ensure the Department of Economic and Social Affairsâ€™ (DESA) continued engagement in aligning international cooperation, strengthening partnerships and advancing coherence across global capacity building initiatives. / PARIS21 partner countries, who will participate in the meetings, are: / 1. Rwanda / 2. Bhutan / 3. Colombia / 4. Ghana / 5. Honduras / 6. Jamaica / 7. Kenya / 8. Kyrgyz Republic / 9. Lao PDR / 10. Malawi / 11. Mongolia / 12. Niger / 13. Palestine / 14. Paraguay / 15. Philippines / 16. Tunisia | Completed | Statistics Division | 13 Oct 2025 | 05 Nov 2025 | 06 Nov 2025 | Abdulla Gozalov ¦ gozalov@un.org | The Partnership in Statistics for Development in the 21st Century (PARIS21) aims to improve the production, quality, availability and use of statistics for informed decision-making and sustainable development. Established in 1999 by the United Nations, the European Commission, the Organisation for Economic Co-operation and Development (OECD), the International Monetary Fund and the World Bank, PARIS21 works with governments, international organizations, civil society and other stakeholders to strengthen national statistical systems, particularly in low- and middle-income countries. / The 2025 PARIS21 Annual Board and Partnership Meetings, to be held in Paris on 5â€“6 November 2025, - preparatory meetings are taking place on 4 November 2025 - will provide a platform to discuss coordinated and sustainable support for statistical capacity development, with a focus on Least Developed Countries (LDCs), Landlocked Developing Countries (LLDCs) and Small Island Developing States (SIDS). / Participation by the United Nations Statistics Division (UNSD) will ensure the Department of Economic and Social Affairsâ€™ (DESA) continued engagement in aligning international cooperation, strengthening partnerships and advancing coherence across global capacity building initiatives. / PARIS21 partner countries, who will participate in the meetings, are: / 1. Rwanda / 2. Bhutan / 3. Colombia / 4. Ghana / 5. Honduras / 6. Jamaica / 7. Kenya / 8. Kyrgyz Republic / 9. Lao PDR / 10. Malawi / 11. Mongolia / 12. Niger / 13. Palestine / 14. Paraguay / 15. Philippines / 16. Tunisia |  |
| 5321 | Request #5321 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Under consideration | Statistics Division | 19 Aug 2025 | 27 Oct 2025 | 31 Oct 2025 | Julian Chow ¦ chowj@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |
| 5293 | Request #5293 ? Support the Government of Colombia, through ProColombia, in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. | Completed | Financing for Sustainable Development Office | 01 Apr 2024 | 01 Apr 2024 | 04 Jul 2025 | Karen Schutt Esmeral ¦ kschutt@procolombia.co | Support the Government of Colombia, through ProColombia, in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. |  |
| 5257 | Request #5257 ? The request from the countries is to supporting countries to (1) facilitate access to existing DHS data, (2) support the completion of interrupted DHS activities, (3) assess the impact from the termination of the DHS program, and (4) propose sustainable long-term solutions to demographic and health data production. | Ongoing | Statistics Division | 07 Mar 2025 | 07 Mar 2025 | 26 Mar 2027 | Haoyi Chen ¦ chen9@un.org | The request from the countries is to supporting countries to (1) facilitate access to existing DHS data, (2) support the completion of interrupted DHS activities, (3) assess the impact from the termination of the DHS program, and (4) propose sustainable long-term solutions to demographic and health data production. |  |
| 5246 | Request #5246 ? In accordance with Economic and Social Council resolution E/RES/2018/2 of 10 November 2017 and decision 2023/338 of 25 July 2023, the United Nations Group of Experts on Geographical Names convened its 2025 session from 28 April to the 2 May 2025 at the United Nations Headquarters in New York, in conference room three. There were 9 meetings of the 2025 session and each meeting will be three hours: 10:00 a.m - 1:00 p.m. and 3:00 - 6:00 p.m.. In all, 197 participants representing 56 Member States across UNGEGNâ€™s geographical and linguistic divisions and observers participated. Specifically, decision 2025/8 Geographical names data management (f): Urged Member States to mobilize resources to support the development of capacity across all Member States and welcomed the possibility of convening a workshop on Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals, and the Semantic Web from 11 to 15 August 2025 at the headquarters of the Economic Commission for Latin America and the Caribbean in Santiago. | Under consideration | Statistics Division | 02 May 2025 | 11 Aug 2025 | 14 Aug 2025 | Mark Iliffe ¦ mark.iliffe@un.org | In accordance with Economic and Social Council resolution E/RES/2018/2 of 10 November 2017 and decision 2023/338 of 25 July 2023, the United Nations Group of Experts on Geographical Names convened its 2025 session from 28 April to the 2 May 2025 at the United Nations Headquarters in New York, in conference room three. There were 9 meetings of the 2025 session and each meeting will be three hours: 10:00 a.m - 1:00 p.m. and 3:00 - 6:00 p.m.. In all, 197 participants representing 56 Member States across UNGEGNâ€™s geographical and linguistic divisions and observers participated. Specifically, decision 2025/8 Geographical names data management (f): Urged Member States to mobilize resources to support the development of capacity across all Member States and welcomed the possibility of convening a workshop on Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals, and the Semantic Web from 11 to 15 August 2025 at the headquarters of the Economic Commission for Latin America and the Caribbean in Santiago. |  |
| 5207 | Request #5207 ? The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Completed | Statistics Division | 09 May 2025 | 30 Sept 2025 | 03 Oct 2025 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Country standardized: 'Republic of Korea' -> 'Korea'. |
| 5129 | Request #5129 ? The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Completed | Population Division, Statistics Division | 28 Mar 2025 | 16 Jun 2025 | 20 Jun 2025 | Maria Isabel Cobos ¦ cobos@un.org | The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Country standardized: 'Turkey' -> 'Türkiye'. |
| 5136 | Request #5136 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. | Under consideration | Statistics Division | 03 Mar 2025 | 17 Mar 2025 | 27 May 2025 | Pedro Farinas ¦ farinas@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. |  |
| 5083 | Request #5083 ? Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. | Completed | Statistics Division | 20 Sept 2024 | 21 Sept 2024 | 31 Jan 2025 | Camilo Andres Mendez Coronado ¦ camendezc@dane.gov.co | Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. |  |
| 5082 | Request #5082 ? In response to countries' requests for enhanced training in evidence-based Voluntary National Review (VNR) development, UNSD has initiated capacity-building efforts, including workshops and the creation of the "Practical Guide for Evidence-based Voluntary National Reviews." To further support these efforts and meet the demand for accessible, self-paced learning, e-learning materials will be developed based on the Guide, allowing Member States to access the training at any time. These materials will not only reinforce the guidance in the workshops but also offer more in-depth information, country examples, case studies, and practical tools to assist in the development of evidence-based VNRs. | Under consideration | Statistics Division | 20 Sept 2024 | 01 Oct 2024 | 31 Dec 2024 | Yongyi Min ¦ min3@un.org | In response to countries' requests for enhanced training in evidence-based Voluntary National Review (VNR) development, UNSD has initiated capacity-building efforts, including workshops and the creation of the "Practical Guide for Evidence-based Voluntary National Reviews." To further support these efforts and meet the demand for accessible, self-paced learning, e-learning materials will be developed based on the Guide, allowing Member States to access the training at any time. These materials will not only reinforce the guidance in the workshops but also offer more in-depth information, country examples, case studies, and practical tools to assist in the development of evidence-based VNRs. | Country standardized: 'Turkey' -> 'Türkiye'. |
| 5080 | Request #5080 ? This workshop builds on last year's event, which focused on supporting evidence-based Voluntary National Reviews (VNRs) and Sustainable Development Goals (SDG) reporting for National Statistics Office (NSO) SDG focal persons presenting their VNR in 2024, with an emphasis on data. More information can be found here. This time, we are integrating it with the First Global Workshop for the 2025 Voluntary National Reviews, bringing together national VNR focal persons and NSO focal persons. The goal is to connect policy and data experts to enhance evidence-based VNR implementation for the 2025 cohort of countries. / The integrated workshop has been approved with our respective management and the agenda and concept note is being developed. The plan is to support the participation of member states from the approved RPTC budget from SD and OISC. | Under consideration | Office for Intergovernmental Support and Coordination for Sustainable Development, Statistics Division | 19 Sept 2024 | 03 Dec 2024 | 11 Apr 2025 | Yongyi Min, ¦ min3@un.org | This workshop builds on last year's event, which focused on supporting evidence-based Voluntary National Reviews (VNRs) and Sustainable Development Goals (SDG) reporting for National Statistics Office (NSO) SDG focal persons presenting their VNR in 2024, with an emphasis on data. More information can be found here. This time, we are integrating it with the First Global Workshop for the 2025 Voluntary National Reviews, bringing together national VNR focal persons and NSO focal persons. The goal is to connect policy and data experts to enhance evidence-based VNR implementation for the 2025 cohort of countries. / The integrated workshop has been approved with our respective management and the agenda and concept note is being developed. The plan is to support the participation of member states from the approved RPTC budget from SD and OISC. | Country standardized: 'Turkey' -> 'Türkiye'. |
| 3977 | Request #3977 ? The provisional weblink to the Handbook is available here: https://unstats.un.org/capacity-development/handbook/index.cshtml | Completed | Statistics Division | 23 Sept 2021 | 10 Jan 2021 | 31 Dec 2021 | Jurgen Gafke ¦ gafke@un.org | The provisional weblink to the Handbook is available here: https://unstats.un.org/capacity-development/handbook/index.cshtml |  |
| 3974 | Request #3974 ? In committing to the realization of the 2030 Agenda for Sustainable Development, Member States recognized that the dignity of the individuals is fundamental and that the Agendaâ€™s Goals and targets should be met for all nations and people and for all segments of society. Ensuring that these commitments are translated into effective action requires a precise understanding of the target populations and progress made in addressing their particular priorities. / To properly measure this, statistics need to be presented for different population groups and geographical areas. The Global Sustainable Development Goal (SDG) indicator framework has included an overarching principle of data disaggregation: Sustainable Development Goal indicators should be disaggregated, where relevant, by income, sex, age, race, ethnicity, migratory status, disability and geographic location, or other characteristics, in accordance with the Fundamental Principles of Official Statistics. / Small area estimation (SAE) techniques have been proved to be very useful to provide reliable disaggregated data for some SDG indicators, such as poverty estimation, food insecurity and undernutrition, health related indicators, unemployment rate, etc. / Under the guidance of IAEG-SDGs and ISWGHS, a draft set of Toolkit has been developed by UNSD on small area estimation for SDGs. The Toolkit provides guidance to countries, based on national experiences, on the use of small area estimation for SDG data disaggregation. The Toolkit covers essential elements of the use of small area estimation including the use of input data, modelling, data validation and dissemination. The Toolkit also provides practical guidance to countries on how to move from SAE experiments to official production. / In this regard, the UN Statistics Division (as the secretariat of both the Inter-Secretariat Working Group on Household Surveys and IAEG-SDGs working on SAE) is (a) fianlising the SAE Toolkit for SDG data disaggregation; and (b) developing a set of eLearning courses on small area estimation for SDGs data disaggregation, in collaboration with ECLAC Statistics Division and UNFPA . | Completed | Statistics Division | 21 Sept 2021 | 01 Mar 2021 | 28 Feb 2022 | Haoyi Chen ¦ chen9@un.org | In committing to the realization of the 2030 Agenda for Sustainable Development, Member States recognized that the dignity of the individuals is fundamental and that the Agendaâ€™s Goals and targets should be met for all nations and people and for all segments of society. Ensuring that these commitments are translated into effective action requires a precise understanding of the target populations and progress made in addressing their particular priorities. / To properly measure this, statistics need to be presented for different population groups and geographical areas. The Global Sustainable Development Goal (SDG) indicator framework has included an overarching principle of data disaggregation: Sustainable Development Goal indicators should be disaggregated, where relevant, by income, sex, age, race, ethnicity, migratory status, disability and geographic location, or other characteristics, in accordance with the Fundamental Principles of Official Statistics. / Small area estimation (SAE) techniques have been proved to be very useful to provide reliable disaggregated data for some SDG indicators, such as poverty estimation, food insecurity and undernutrition, health related indicators, unemployment rate, etc. / Under the guidance of IAEG-SDGs and ISWGHS, a draft set of Toolkit has been developed by UNSD on small area estimation for SDGs. The Toolkit provides guidance to countries, based on national experiences, on the use of small area estimation for SDG data disaggregation. The Toolkit covers essential elements of the use of small area estimation including the use of input data, modelling, data validation and dissemination. The Toolkit also provides practical guidance to countries on how to move from SAE experiments to official production. / In this regard, the UN Statistics Division (as the secretariat of both the Inter-Secretariat Working Group on Household Surveys and IAEG-SDGs working on SAE) is (a) fianlising the SAE Toolkit for SDG data disaggregation; and (b) developing a set of eLearning courses on small area estimation for SDGs data disaggregation, in collaboration with ECLAC Statistics Division and UNFPA . |  |
| 4675 | Request #4675 ? To organize a capacity development workshop focused on climate resilience and international development finance in Colombia. / The workshop would follow up on the discussions held during the DCF 2023 and serve as an endâ€ofâ€year inflexion point for governments who care about sustainable development and just climate finance. It can also serve as a appropriate forum to discuss global taxation and rethink the international development finance arquitecture from a southern perspective. | Completed | Financing for Sustainable Development Office | 01 Jul 2023 | 20 Nov 2023 | 21 Nov 2023 | Andres Ceballos ¦ andresceballos@apccolombia.gov.co | To organize a capacity development workshop focused on climate resilience and international development finance in Colombia. / The workshop would follow up on the discussions held during the DCF 2023 and serve as an endâ€ofâ€year inflexion point for governments who care about sustainable development and just climate finance. It can also serve as a appropriate forum to discuss global taxation and rethink the international development finance arquitecture from a southern perspective. |  |
| 4730 | Request #4730 ? This proposal is a response to country requests for training in support of estimation and use of National Transfer Accounts. Eight countries (Colombia, Costa Rica, Jamaica, Lao PDR, Malaysia, Maldives, Uruguay, and Viet Nam) will be participating in the 15th Tranche development account project on â€œInclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbeanâ€ â€“ jointly implemented by DESA, ECLAC, and ESCAP. A key prerequisite for successful participation in this DA project is the completion of a recent, full set of National Transfer Accounts by the end of 2023. / To this end and to strengthen the technical capacity in these 8 countries, this proposal will fund 8 participants (one from each of the DA project countries) to participate and receive training at the Fourteenth Global Meeting of the National Transfer Accounts project (NTA14): â€œBuilding Sustainable Generational Economiesâ€ which will take place 14-17 February 2023 at the UniversitÃ© Paris-Dauphine, France. DESA staff will co-organize and co-teach training workshops offered to participants from all countries (an estimated 60 to 80) participating at the global conference â€“ utilizing the UN manuals on National Transfer Accounts (DESA, 2013) and on National Time Transfer Accounts (DESA, 2023). | Completed | Population Division | 06 Jan 2023 | 14 Feb 2023 | 17 Feb 2023 | Tim Miller ¦ tim.miller@un.org | This proposal is a response to country requests for training in support of estimation and use of National Transfer Accounts. Eight countries (Colombia, Costa Rica, Jamaica, Lao PDR, Malaysia, Maldives, Uruguay, and Viet Nam) will be participating in the 15th Tranche development account project on â€œInclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbeanâ€ â€“ jointly implemented by DESA, ECLAC, and ESCAP. A key prerequisite for successful participation in this DA project is the completion of a recent, full set of National Transfer Accounts by the end of 2023. / To this end and to strengthen the technical capacity in these 8 countries, this proposal will fund 8 participants (one from each of the DA project countries) to participate and receive training at the Fourteenth Global Meeting of the National Transfer Accounts project (NTA14): â€œBuilding Sustainable Generational Economiesâ€ which will take place 14-17 February 2023 at the UniversitÃ© Paris-Dauphine, France. DESA staff will co-organize and co-teach training workshops offered to participants from all countries (an estimated 60 to 80) participating at the global conference â€“ utilizing the UN manuals on National Transfer Accounts (DESA, 2013) and on National Time Transfer Accounts (DESA, 2023). |  |
| 4234 | Request #4234 ? Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Completed | Statistics Division | 05 Jul 2022 | 08 Jan 2022 | 30 Dec 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |
| 4227 | Request #4227 ? Countries need additional materials and tools for the implementation of their national quality assurance frameworks. Specifically, / - countries are frequently unsure about the next implementation actions that should be taken - / - countries require additional guidance on the quality assurance of administrative and other data sources | Completed | Statistics Division | 30 Jun 2022 | 01 Sept 2022 | 31 Dec 2022 | Matthias Reister ¦ reister@un.org | Countries need additional materials and tools for the implementation of their national quality assurance frameworks. Specifically, / - countries are frequently unsure about the next implementation actions that should be taken - / - countries require additional guidance on the quality assurance of administrative and other data sources |  |
| 4223 | Request #4223 ? This proposal is a response to a request from UN ECLAC on behalf of Member States in the region for technical assistance in the area of population and development: on the estimation and use of National Accounts disaggregated by age and socio-economic group (National Inclusion Accounts). DESA and UN ECLAC will provide training through an in-person workshop (6-9 December 2022) to be held in conjunction with the annual meeting of the Latin American Population Association. The participants will include government officials and national professionals with prior experience in the estimation and use of National Transfer Accounts. | Completed | Population Division | 01 Jun 2022 |  |  | Zulma Sosa ¦ Zulma.SOSA@cepal.org | This proposal is a response to a request from UN ECLAC on behalf of Member States in the region for technical assistance in the area of population and development: on the estimation and use of National Accounts disaggregated by age and socio-economic group (National Inclusion Accounts). DESA and UN ECLAC will provide training through an in-person workshop (6-9 December 2022) to be held in conjunction with the annual meeting of the Latin American Population Association. The participants will include government officials and national professionals with prior experience in the estimation and use of National Transfer Accounts. |  |
| 4202 | Request #4202 ? DPIDG was requested by the City of Bogota in Colombia to provide support in strengthening capacities at the local level to deliver effective e-services to the people. Such assistance would aid in assisting smaller municipalities around the country in providing better e-services to people. / (LOSI-Venue - Thailand ) | Completed | Division for Public Institutions and Digital Government | 12 Dec 2021 | 21 Nov 2023 | 23 Nov 2023 | FELIPE GUZMÃN RAMÃREZ ¦ susar@un.org | DPIDG was requested by the City of Bogota in Colombia to provide support in strengthening capacities at the local level to deliver effective e-services to the people. Such assistance would aid in assisting smaller municipalities around the country in providing better e-services to people. / (LOSI-Venue - Thailand ) |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| 3989 | Request #3989 ? The COVID-19 pandemic presented a major challenge for household survey programmes. Traditional face-to-face survey operations have become difficult to implement in many countries due to social distancing requirements and other restriction measures as a result of the pandemic. According to a survey conducted by the United Nations Statistics Division (UNSD) and the World Bank in May 2020, 96â€¯percent of national statistical offices (NSOs) partially or fully stopped face-to-face data collection. / In response to the government requirement on social distancing, many national statistical offices (NSOs) quickly turned to telephone or web interviews as an alternative data collection mode to maintain continuity in the production of key indicators and monitor the health and socio-economic impact of the pandemic. / In the fourth round of UNSD and the World Bank survey of national statistical offices in May-June 2021, a marked increase was observed in the number of countries declaring a full resumption of face-to-face data collection activities. Globally 44 percent of the surveyed countries resumed full face-to-face data collection, compared to just four percent a year earlier. / While the adaptation of national household survey operations indicated the resilience of NSOs, such adaptation also raised challenges for countries on survey data quality. Change of survey data collection mode from face-to-face to telephone or web may impact on sample coverage, response rate and measurement error. Shortening survey questionnaires and changing question flows will also impact on the quality and comparability of survey data. / In close consultation with the Task Force on COVID-19, established by the Inter-Secretariat Working Group on Household Surveys (ISWGHS), UNSD is hiring a consultant to develop a Guidance Note on Assessing and Minimizing the COVID Impact on Survey Quality. | Completed | Statistics Division | 28 Sept 2021 | 01 Mar 2021 | 28 Feb 2022 | Haoyi Chen ¦ chen9@un.org | The COVID-19 pandemic presented a major challenge for household survey programmes. Traditional face-to-face survey operations have become difficult to implement in many countries due to social distancing requirements and other restriction measures as a result of the pandemic. According to a survey conducted by the United Nations Statistics Division (UNSD) and the World Bank in May 2020, 96â€¯percent of national statistical offices (NSOs) partially or fully stopped face-to-face data collection. / In response to the government requirement on social distancing, many national statistical offices (NSOs) quickly turned to telephone or web interviews as an alternative data collection mode to maintain continuity in the production of key indicators and monitor the health and socio-economic impact of the pandemic. / In the fourth round of UNSD and the World Bank survey of national statistical offices in May-June 2021, a marked increase was observed in the number of countries declaring a full resumption of face-to-face data collection activities. Globally 44 percent of the surveyed countries resumed full face-to-face data collection, compared to just four percent a year earlier. / While the adaptation of national household survey operations indicated the resilience of NSOs, such adaptation also raised challenges for countries on survey data quality. Change of survey data collection mode from face-to-face to telephone or web may impact on sample coverage, response rate and measurement error. Shortening survey questionnaires and changing question flows will also impact on the quality and comparability of survey data. / In close consultation with the Task Force on COVID-19, established by the Inter-Secretariat Working Group on Household Surveys (ISWGHS), UNSD is hiring a consultant to develop a Guidance Note on Assessing and Minimizing the COVID Impact on Survey Quality. |  |
| 3922 | Request #3922 ? The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ | Ongoing | Statistics Division | 01 Mar 2021 | 01 Mar 2021 | 01 Mar 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ |  |
| 3845 | Request #3845 ? National statistics office requests traning in disaggregated National Accounts by age (National Transfer Accounts) for use in their official national statistics. A joint DESA/ECLAC training workshop will be held virtually 31 May - 4 June. | Completed | Population Division | 24 Mar 2021 | 31 May 2021 | 04 Jun 2021 | Juan Camilo Mendez ¦ camendezc@dane.gov.c0o | National statistics office requests traning in disaggregated National Accounts by age (National Transfer Accounts) for use in their official national statistics. A joint DESA/ECLAC training workshop will be held virtually 31 May - 4 June. |  |
| 3540 | Request #3540 ? Request from National Statistics Office of Colombia for assistance in estimating distributional National Accounts by age (National Transfer Accounts). Request for Spanish translation of UN Manual: National Transfer Accounts. Manual will be used in subsequent capacity development work in region. Virtual training workshop held 31 May - 4 June. | Completed | Population Division | 26 Feb 2021 | 01 Apr 2021 | 30 Jun 2021 | Juan Camilo Mendez ¦ camendezc@dane.gov.co | Request from National Statistics Office of Colombia for assistance in estimating distributional National Accounts by age (National Transfer Accounts). Request for Spanish translation of UN Manual: National Transfer Accounts. Manual will be used in subsequent capacity development work in region. Virtual training workshop held 31 May - 4 June. |  |
| 3441 | Request #3441 ? Joint DESA-ECLAC initiative. Responding to a request from UN ECLAC on behalf of member states for training in forecasting the economic and fiscal impacts of population ageing. | Completed | Population Division | 19 Oct 2019 | 25 Nov 2019 | 27 Nov 2019 | Mr. Paulo Saad ¦ paulo.saad@un.org | Joint DESA-ECLAC initiative. Responding to a request from UN ECLAC on behalf of member states for training in forecasting the economic and fiscal impacts of population ageing. |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.19 | Workshop on the use of interoperability standards for the management of geographical names “Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals and the Semantic Web” | SD | 30 Jun 2026 | 30 Jun 2026 | $43,886 | Argentina, Barbados, Brazil, Colombia, Costa Rica, Dominican Republic, Ecuador, Jamaica, Mexico, Panama, Uruguay |  | Proposal past due |
| SB-001376.99.99.20 | Participation in the 2026 IAOS Conference as a panelist and resource person on the Fundamental Principles of Official Statistics (FPOS) in the context of the modernization and transformation of official statistics. | SD | 30 Jun 2026 | 30 Jun 2026 | $2,691 | Colombia, Philippines, South Africa | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.20¦row:21': 'f_cashDESA' has non-numeric value 'RPTC funding to support travel and daily subsistence allowance for one UNSD staff participation in the 2026 IAOS Conference in Vilnius, Lithuania;'. / Proposal past due |
| SB-001376.99.99.32 | Regional Workshop on the Implementation of the Revised MSITS 2026 | SD | 31 Dec 2026 | 31 Dec 2026 | $62,098 | Argentina, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Guyana, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay, Venezuela (Bolivarian Republic of) | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Venezuela' -> 'Venezuela (Bolivarian Republic of)'. | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| SB-001376.99.99.39 | International workshop on the measurement of SDG Indicator 5.4.1 and XXVII International Meeting on Gender Statistics | SD | 31 Dec 2026 | 31 Dec 2026 | $6,799 | Brazil, Chile, Colombia, Costa Rica, Democratic Republic of Timor-Leste, Dominican Republic, Ecuador, Grenada, Guatemala, Honduras, Lao People's Democratic Republic, Mexico, Morocco, Paraguay, Peru, Tunisia | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. / Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costConferenceServices' has non-numeric value '0¦¦0¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelConsultants' has non-numeric value '4,098¦¦4,098¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelParticipants' has non-numeric value '0¦¦0¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelStaff' has non-numeric value '2,701¦¦2,701¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'f_cashDESA' has non-numeric value 'US$ 6,799'. |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002257462 - Colombia | 0002257462 | Past | Colombia |  | STATISTICS DIVISION | INCEPTION WORKSHOP AND MISSION, COLOMBIA |  | 12 Apr 2026 | 17 Apr 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation | 2021 | DSDG | Algeria, Argentina, Austria, Bolivia (Plurinational State of), Bosnia and Herzegovina, Bulgaria, Colombia, Ecuador, Ethiopia, Georgia, Ghana, Guyana, Honduras, India, Italy, Kenya, Lebanon, Malawi, Morocco, Nauru, Niger, North Macedonia, Pakistan, Papua New Guinea, Poland, Portugal, Samoa, Seychelles, United Arab Emirates, United Kingdom of Great Britain and Northern Ireland, Zambia | - Future similar projects should apply a Results-Based Management approach, developing an M&E framework, plan, and data collection tools that articulate instrumental and transformational changes rather than processes. / - Additional resources should be mobilized to ensure follow-up and implementation of the commitments secured in the global roadmap and in the Energy Compacts, starting with pilot projects to determine their viability and scalability. / - Future similar projects should include studies on Cost-Benefit Analysis to determine the viability and scalability of policy changes, ranking options in the Energy Compacts according to their costs and benefits to society. / - More staff wholly dedicated to the project should be planned for at the conceptualization stage, including roles for communications and project management assistance, and a project steering committee to ensure recommendations for course corrections are followed. / - Future projects should develop a clear partnership strategy to guide implementers on where to invest in collaboration for the greatest value to the organization. / - The composition of the global Technical Advisory Group (TAG) should be replicated and cascaded to regional and national levels to ensure continuity and nuanced specificities beyond the project’s shelf life. / - Future projects should leverage United Nations Information Centers (UNICs) to develop and implement coordinated communications strategies for Member States, amplifying project achievements at the local level. | - The joint production and dissemination of knowledge products laid a strong foundation for sustainability, scaling up, replication, and future programming, increasing knowledge and capacities for accountability. / - Synergistic partnerships and multi-stakeholder participation facilitated ownership, sustainability, and coherence between national planning processes, enhancing coordination among line ministries for timely VNR production. / - Upstream activities allowed the project to adapt to challenges such as Covid-19, and partnering with the public sector leveraged government influence for mainstreaming SDG7 implementation. / - Engagement with the private sector was strategic, as private sector input and financial commitments in the Energy Compacts are essential for accelerating SDG7 implementation. / - The project was initially thinly staffed, but hiring a dedicated Project Officer after commencement improved implementation; future projects should plan for adequate dedicated staffing from the outset. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2017/2017-02 DSD SDG7/Reports/Evaluation/Final_Dec 18th_UNDESA_Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| Monitoring and reporting on sustainable development objectives, goals and targets: enhancing institutional capability in selected developing countries | 2018 | DSDG; UNSD | Belize, Colombia, Ethiopia, Honduras, Jordan | - Proceed with group training workshops at the regional level, in combination with E-learning as a complementary tool, due to resource constraints and language challenges. / - Enforce a pre-training selection of national participants with at least some basic knowledge of strategic planning and management, and allocate a longer period of time to the Training of Trainers (ToT). / - Extend the Training Curriculum beyond the pilot countries, translate it into other languages, and revise future versions to be more practical and action-oriented with concrete case studies, especially for local level planning. / - Disseminate the Training Curriculum by involving universities and other institutions in as many countries as possible to broaden its reach and impact. / - Scale up the activities of the project, such as RBM learning, to involve more officials and the right drivers in each country, and consider using a website or E-learning platform for wider dissemination. / - Involve the National Statistical Office (NSO) at an early stage and strengthen or modernize the national statistical system to improve provision, access to, and use of quality data and related technologies for SDG indicators. / - Take into account the geographic dimension of data and related geospatial information and earth observations in future projects, and collaborate with UNSD to streamline UN support for strengthening countries' information infrastructures and statistical systems. / - Increase focus on domestic resource mobilization and build partnerships with the private sector and other stakeholders within the country to support project performance and outcomes. / - Encourage countries to proactively seek counter-part funding and additional support from other donors for project activities. / - Reinforce cooperation with UN agencies and UN-DESA, and continue collaborative work with UN Country Teams and UN Regional Commissions to address challenges effectively. | - Developing country-specific implementation workplans based on capacity assessments was crucial for refining project objectives and ensuring successful execution. / - The Training Curriculum on Results-Based Management (RBM), supplemented by a facilitator manual in three languages, was highly informative and provided valuable guidance for planning, implementation, and monitoring of the SDGs. / - The International ToT Workshop was effective for sharing the curriculum widely and demonstrated the value of tailoring tools and methods to local contexts. / - Learning RBM methodology requires participants to have some basic knowledge in strategic planning and management; its application to SDGs is most effective when carried out by well-trained key representatives from government departments. / - Applying RBM at the local level requires data disaggregation by location and the collection, processing, analysis, and dissemination of large amounts of data from both official and innovative sources. / - Strong support and commitment from high-level decision makers, engagement of government departments, and involvement of all stakeholders, including civil society, private sector, and academia, are crucial for successful domestic implementation of SDGs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DSDG/ROA 265-SB-001292-1415I- 9th tranche_Monitoring and reporting on SD objectives/Evaluation/Final Evaluation Report- DA 1415I.docx |  |  |
| Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues | 2014 | FSDO | Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay | - Ensure pilot countries have all necessary data available, including up-to-date and filtered taxpayer databases and appropriate sample weighting, before selection. / - Select countries that have not recently undergone major tax reforms to avoid distortion of TTCs due to adaptation processes. / - Include qualitative aspects such as psychological costs as part of non-economic costs in future TTCs studies to better understand results. / - Adapt survey implementation methods to the context (e.g., face-to-face vs. online) and include control questions to improve data quality. / - Encourage NTAs to seek synergies with other public institutions for information gathering and fieldwork support. | - Institutional support and commitment from NTAs are decisive factors for successful project implementation and sustainability. / - A thorough methodology that includes both administrative and compliance costs, considers the taxpayer cycle, and covers all relevant taxes is effective for TTC measurement. / - Allowing each country to choose its own survey method, considering size and cultural context, can improve implementation but may affect comparability. / - CIAT's coordination and reputation are critical for engaging countries and ensuring project sustainability. / - The methodology is generally easy to apply in interested countries, but successful implementation depends on institutional support and well-designed databases. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/ROA181-6B/Evaluation/Evaluation Report- FINAL.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Supporting the establishment of a Latin American Parliamentary Knowledge Network | 2014 | DPIDG | Argentina, Barbados, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Ecuador, El Salvador, Guatemala, Guyana, Mexico, Nicaragua, Panama, Paraguay, Saint Vincent and the Grenadines, Suriname, Trinidad and Tobago, Uruguay | - Establish regional agreement and resources for hosting of the Secretariat to ensure that it is properly funded and resourced and that the commitment for this is shared amongst those parliaments that can afford it. / - Expand opportunities for take part in network activities and extend these beyond those parliaments who have formally signed up to RIPALC. / - Ensure appropriate ongoing resources are committed to the digital portal as this is a critical component of the network and vital to ensuring the ongoing operation and relevance of it. / - Participants right across the region need to be encouraged to take ownership of the communities of interest and to see RIPALC as a place to learn, share and network. Ensuring the grass-roots value and use of the network will be the single most significant factor in the networks long term sustainability. / - RIPALC needs to be flexible and responsive to the needs of the users and allow them to create new communities of interest and for the model to develop to suit their requirements, it must be driven by demand, not controlled from the top down. / - It is important that RIPALC maintains the ability to run regional workshops and meetings so that parliamentary staff can network and collaborate. Digital networks are important and they help to sustain relationships and act as timely conduits for knowledge exchange, but they do not replace face to face meetings as a way of building social capital. / - Inter-parliamentary collaboration remains a priority and was seen by participants as a key pre-requisite for democratic strengthening in the region and RIPALC is an ideal vehicle to facilitate and support this. | - The RIPALC network was a timely and appropriate development for the region and has been well received by the participants in it. / - The clear weakness in the project was to rigidly implement a governance model based on the long-established ECPRD structure. This has proved restrictive and inflexible in the case of RIPALC and it has inhibited growth. A more organic and less rigid structure would have been more appropriate. / - Projects such as this need some level of formality and process if they are to be seen as reliable and trustworthy by parliaments, but the network must develop in line with the culture and expectations of the region it covers and duplicating a model from elsewhere can limit take-up. / - The network has become a force for active parliamentary development in the region, a timely catalyst to build on a growing desire for strong parliaments and recognition that it is important for parliaments to collaborate and share ideas, knowledge and experience. / - The network has successfully delivered face-to-face meetings and workshops, which are vital for building and sustaining relationships between parliaments, and has acted as a ‘role model’ for inter-parliamentary collaboration in a region where this is a relatively new and unknown concept. / - The web portal provides a fast and easy way for parliamentary staff to stay in touch and to discuss, advise and be advised about good practice and emergent issues in their field, which is particularly important for smaller legislatures. / - Though the uptake has been slower than expected, this is seen as a result of the structural limitations of RIPALC. In the medium to long term, the Secretariat needs to ensure that the portal is able to meet the needs and demands of its stakeholders and that it is promoted to all parliaments in the region, regardless of their formal membership of RIPALC. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/7th tranche/ROA 163 (DPADM)/RIPALC.Evaluation.FinalReport-1.0.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'St Vincent and the Grenadines' -> 'Saint Vincent and the Grenadines'. | evaluations.xlsx rows 288 (archived) and 200 (retained): Review conflicts: Countries differs: archived row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; Ecuador; El Salvador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'; retained row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; El Salvador; Ecuador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'. Country lists were not merged. |
| Supporting Developing Countries Measure Progress towards Achieving a Green Economy | 2016 | UNSD | Bhutan, Chile, Colombia, Ecuador, Malaysia, Mongolia, Peru, Viet Nam | - Replicate the high rate of women's participation in workshops in other DESA projects. / - Avoid reducing project budgets after implementation has started; DESA Development Account Project Management Team in CDO should establish systems to prevent this. / - Highlight project results at the annual meetings of the High-Level Political Forum on Sustainable Development to publicize DESA/SD's work and engage policy makers. / - For future projects, consider engaging more consultants to match the number of project countries, to encourage wider sharing of ideas and innovative thinking. / - Promote stronger links between green economy indicators and indicators useful for follow-up of the SDGs and the 2030 Agenda for Sustainable Development. | - Workshops in all phases of the project were effective for knowledge sharing and experience exchange; future workshops should continue to emphasize this. / - Resource persons from DESA/SD, regional commissions, UN agencies, and other organizations contributed significantly to workshop quality. / - Involvement of regional commissions and other UN agencies contributed to both project success and sustainability of outcomes. / - The project strengthened regional networks of statisticians, increased intra-institutional and intra-regional cooperation, and raised the national profile of statistics. / - Using only one consultant for all technical assistance missions may have limited inter-regional experience sharing; involving more consultants could enrich interventions. / - Pairing resource countries with pilot countries facilitated knowledge sharing and is a best practice to replicate. / - Involving regional specialized agencies added value by providing technical assistance and supporting sustainability. / - Designating focal points in pilot countries to coordinate inputs and participation was productive and should be emulated in similar projects. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 211 - 8th tranche - Green Economy/Evaluation/Evaluation report/DA_GreenEcon_proj_eval_10Oct2016 R1.pdf |  |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 3 | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 288 (archived) and 200 (retained): Review conflicts: Countries differs: archived row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; Ecuador; El Salvador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'; retained row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; El Salvador; Ecuador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'. Country lists were not merged. |
| 5 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 6 | proposals.xlsx record 'SB-001376.99.99.20¦row:21': 'f_cashDESA' has non-numeric value 'RPTC funding to support travel and daily subsistence allowance for one UNSD staff participation in the 2026 IAOS Conference in Vilnius, Lithuania;'. |
| 7 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. |
| 8 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| 9 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costConferenceServices' has non-numeric value '0¦¦0¦¦$'. |
| 10 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelConsultants' has non-numeric value '4,098¦¦4,098¦¦$'. |
| 11 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelParticipants' has non-numeric value '0¦¦0¦¦$'. |
| 12 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelStaff' has non-numeric value '2,701¦¦2,701¦¦$'. |
| 13 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'f_cashDESA' has non-numeric value 'US$ 6,799'. |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 46 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 60 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |