Ethiopia

Africa | LDC | LLDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Ethiopia is presented in this country card as part of Africa, with Ethiopia also associated with an unspecified subregion and the LDC, LLDC grouping. The filtered data for Ethiopia highlights 15 projects for Ethiopia, including 1 active or planned projects for Ethiopia and 14 completed or closed projects for Ethiopia.

For Ethiopia, the report includes 25 requests for Ethiopia, 3 RPTC proposals for Ethiopia, 0 RPTC activities for Ethiopia, and 23 travel records for Ethiopia. Financially, Ethiopia shows USD 22,210,570 in project budget, $152,603 in proposal planned budget, and $0 in consumed RPTC activity budget for Ethiopia.

The main organizational coverage for Ethiopia points to DISD, Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, FSDO. Activity records for Ethiopia list 0 participants, including 0 women participants, the current quality review for Ethiopia includes 71 data quality notes. Current highlights for Ethiopia include a request focus for Ethiopia: Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data.

      

      

      
This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing.

      

      

      
The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint.; an RPTC proposal focus for Ethiopia: Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 15 |
| Project budget | USD 22,210,570 |
| Requests | 25 |
| RPTC proposals | 3 |
| Proposal planned budget | $152,603 |
| RPTC activities | 0 |
| Consumed RPTC budget | $0 |
| Activity participants | 0 |
| Women participants | 0 |
| Travel records | 23 |
| Evaluations | 18 |
| Data quality notes | 71 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Accelerating implementation of Data For Now in eight countries in Africa and Asia |  | country | Statistics Division | Closed | 15 Jun 2022 | 30 Jun 2024 | USD 1,500,468 | Ethiopia, Jordan, Morocco, Sierra Leone, Tunisia, Viet Nam |  |  |
| Developing institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals |  | country | Division for Public Institutions and Digital Government | Closed | 01 Oct 2021 | 31 Oct 2024 | USD 824,649 | Bangladesh, Bhutan, Cambodia, Democratic Socialist Republic of Sri Lanka, Egypt, Ethiopia, Fiji, Gambia, Ghana, Lao People's Democratic Republic, Morocco, Namibia, Rwanda, Samoa, Sierra Leone, United Republic of Tanzania, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Enhancing national statistical capacity to measure, monitor, assess and report on progress on achieving post-2015 goals and targets for sustainable development | 1415AU | country | Statistics Division | Closed | 16 Feb 2020 | 18 Jan 2020 | USD 556,000 | Cambodia, Ethiopia, Philippines, Rwanda, Uganda, Viet Nam |  | projects.csv record 'Enhancing national statistical capacity to measure, monitor, assess and report on progress on achieving post-2015 goals and targets for sustainable development ¦ 2020-02-16T00:00:00 ¦ 1415AU': End date 2020-01-18 is before start date 2020-02-16. |
| Enhancing policy coherence for the SDGs through integrated assessments and institutional strengthening | 1819C | country | Division for Public Institutions and Digital Government, Economic Analysis and Policy Division | Closed | 01 Mar 2018 | 31 Dec 2021 | USD 750,000 | Cameroon, Ethiopia, Senegal |  |  |
| Evidence-based eGovernment Policies for advancing information technology infrastructure, governmental service delivery and accountability | 1617B | country | Division for Public Institutions and Digital Government | Closed | 16 Jul 2020 | 19 Dec 2020 | USD 530,000 | Bangladesh, Ethiopia |  |  |
| Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America | 1617H | country | Division for Sustainable Development Goals | Closed | 16 Apr 2020 | 20 Mar 2020 | USD 596,800 | Costa Rica, Egypt, Ethiopia |  | projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country text 'Eastern Africa' could not be matched; no country assignment was inferred. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country text 'Latin America and the Caribbean' could not be matched; no country assignment was inferred. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country text 'Northern Africa' could not be matched; no country assignment was inferred. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country/Sub region 'Eastern Africa' was not matched to GeoData and was ignored. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country/Sub region 'Latin America and the Caribbean' was not matched to GeoData and was ignored. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': Country/Sub region 'Northern Africa' was not matched to GeoData and was ignored. / projects.csv record 'Implementation of national sustainable development strategies in selected countries in Africa, Asia and Latin America ¦ 2020-04-16T00:00:00 ¦ 1617H': End date 2020-03-20 is before start date 2020-04-16. |
| Mobilizing Science, Technology and Innovation in Developing Countries for the SDGs | 2016-03 | country | Division for Sustainable Development Goals | Closed | 01 Apr 2017 | 30 Jun 2021 | USD 1,000,000 | Ethiopia, Ghana, India, Kenya, Serbia |  |  |
| Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries | 1415I | country | Division for Sustainable Development Goals | Closed | 15 Aug 2020 | 17 Dec 2020 | USD 639,000 | Belize, Colombia, Ethiopia, Honduras, Jordan |  | projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Eastern Africa' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Latin America and the Caribbean' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'South America' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Western Asia' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Eastern Africa' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Latin America and the Caribbean' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'South America' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Western Asia' was not matched to GeoData and was ignored. |
| Monitoring the Sustainable Development Goals |  | country | Statistics Division | Closed | 01 Aug 2016 | 31 Jul 2022 | USD 9,334,229 | Bangladesh, Burundi, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Kyrgyzstan, Lao People's Democratic Republic, Liberia, Mozambique, Myanmar, Nepal, Rwanda, Tajikistan, Uganda, United Republic of Tanzania, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthened Resilience of Micro-, Small and Medium-sized Enterprises (MSMEs) in Africa and Asia | 2225C | country | Division for Sustainable Development Goals | Closed | 01 Feb 2022 | 31 Dec 2025 | USD 500,000 | Cambodia, Ethiopia, Philippines, Zimbabwe |  |  |
| Strengthening capacities of developing countries in sub-Saharan Africa to effectively produce and use population estimates and projections in policy-making for sustainable development | ROA 262 | country | Population Division | Closed | 14 Jun 2020 | 17 Dec 2020 | USD 588,000 | Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Djibouti, Ethiopia, Gabon, Ghana, Kenya, Mali, Namibia, Niger, Nigeria, Senegal, Togo, Uganda, Zambia |  |  |
| Strengthening geospatial information management in developing countries towards implementing the 2030 Agenda | 1819D | country | Statistics Division | Closed | 01 Mar 2018 | 31 Dec 2022 | USD 750,000 | Burkina Faso, Ethiopia, Fiji, Mongolia, Nepal, Tonga |  |  |
| Strengthening local and national government capacities for SDG localization in Africa |  | country | Division for Sustainable Development Goals | Active | 01 Oct 2024 | 31 Mar 2027 | USD 2,000,000 | Côte d’Ivoire, Egypt, Ethiopia, Ghana, Mozambique, Sierra Leone, South Africa | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| Strengthening national capacities for enhancing MSME resilience and building forward better to accelerate the implementation of the 2030 Agenda in developing countries participating in the Belt and Road Initiative | PDF-SDG-2021-01 | country | Division for Sustainable Development Goals | Closed | 01 Jan 2021 | 31 Dec 2024 | USD 1,663,004 | Cambodia, Democratic Socialist Republic of Sri Lanka, Ethiopia, Gambia, Kenya, Lao People's Democratic Republic, Madagascar, Philippines, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Strengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda | PDF‐SDG‐2018-02 | country | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, Economic Analysis and Policy Division, Financing for Sustainable Development Office, Statistics Division | Closed | 01 Nov 2018 | 30 Jun 2021 | USD 978,420 | Bangladesh, Ethiopia, Lao People's Democratic Republic, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5432 | Request #5432 ? The Minister of State of Industry of Ethiopia requested to continue the collaboration with DESA, in areas such as â€œconducting capacity building workshops for MSME entrepreneurs and policymakers on artificial intelligence, digital marketing, e-commerce and industrial clustering topics | Under consideration | Division for Sustainable Development Goals | 01 Jan 2026 | 01 Jan 2026 | 31 Dec 2026 | Mr. Hassan Muhumed Moalin ¦ gechandualem12@gmail.com | The Minister of State of Industry of Ethiopia requested to continue the collaboration with DESA, in areas such as â€œconducting capacity building workshops for MSME entrepreneurs and policymakers on artificial intelligence, digital marketing, e-commerce and industrial clustering topics |  |  |
| 5356 | Request #5356 ? AU-APRM has requested development of a comprehensive programme together with DESA aimed at fostering transformative governance reform across AU Member States. Particular reference is made to implementation of the CEPA principles of effective governance for sustainable development and actionable reforms in countries undergoing political transitions or recovering from conflict. | Under consideration | Division for Public Institutions and Digital Government | 03 Sept 2025 | 01 Jan 2026 | 31 Dec 2028 | Amb. Marie-Antoinette Rose-Quatre ¦ info@aprm-au.org | AU-APRM has requested development of a comprehensive programme together with DESA aimed at fostering transformative governance reform across AU Member States. Particular reference is made to implementation of the CEPA principles of effective governance for sustainable development and actionable reforms in countries undergoing political transitions or recovering from conflict. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5285 | Request #5285 ? Support the Government of Ethiopia, through Ethiopian Investment Holdings (EIH), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. | Ongoing | Financing for Sustainable Development Office | 21 May 2025 | 22 May 2025 | 31 Dec 2025 | Dagmawi Meshesha ¦ dagmawi.meshesha@eih.et | Support the Government of Ethiopia, through Ethiopian Investment Holdings (EIH), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. |  |  |
| 5235 | Request #5235 ? The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Under consideration | Statistics Division | 11 Jun 2025 | 11 Jun 2025 | 05 Dec 2025 | Matthias Reister ¦ reister@un.org | The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 4822 | Request #4822 ? The Ethiopian Federal Civil Service Commission has requested DPIDG to conduct an online Capacity Development Training Workshop on ethics and transparency. | Not fulfilled by DESA | Division for Public Institutions and Digital Government | 06 Nov 2023 | 01 Jan 2024 |  | Mr. Temesgen Mendo ¦ mendotem@gmail.com | The Ethiopian Federal Civil Service Commission has requested DPIDG to conduct an online Capacity Development Training Workshop on ethics and transparency. |  |  |
| 4680 | Request #4680 ? Ethiopia requests technical support to strengthen the capacities of its national Education and STI System through supporting the implementation of its STI for SDGs Roadmap | Completed | Division for Sustainable Development Goals | 26 Apr 2023 | 01 May 2023 | 31 Oct 2023 | Samuel Kifle Kidane ¦ na@na.na | Ethiopia requests technical support to strengthen the capacities of its national Education and STI System through supporting the implementation of its STI for SDGs Roadmap |  |  |
| 4694 | Request #4694 ? DPIDG has been requested by the Government of Ethiopiaâ€™s to continue capacity development support for the second phase of the United Nations Department of Economic and Social Affairs (UN DESA) Project â€œDeveloping institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals- National Data Governance Study (phase II). | Ongoing | Division for Public Institutions and Digital Government | 11 Apr 2023 | 01 Apr 2023 | 30 Sept 2023 | H.E. Ms. Huria Ali Mahdi ¦ kwok@un.org | DPIDG has been requested by the Government of Ethiopiaâ€™s to continue capacity development support for the second phase of the United Nations Department of Economic and Social Affairs (UN DESA) Project â€œDeveloping institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals- National Data Governance Study (phase II). |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4234 | Request #4234 ? Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Completed | Statistics Division | 05 Jul 2022 | 08 Jan 2022 | 30 Dec 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 2580 | Request #2580 ? Technical assistance with CLEWS | Completed | Economic Analysis and Policy Division | 21 May 2018 |  |  |  | Technical assistance with CLEWS |  |  |
| 4097 | Request #4097 ? DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Completed | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals | 15 Feb 2022 | 28 Mar 2022 | 29 Mar 2022 | Eddy Maloka ¦ eddy.maloka@aprm-au.org | DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 4001 | Request #4001 ? EAPP is requesting collaboration and support in hosting and conducting the Public Administration Capacity Development Conference-"Resolving the Grand Challenges for Sustainable Development in Ethiopia", 15-18 June 2022. | Not fulfilled by DESA | Division for Public Institutions and Digital Government | 19 Oct 2021 | 15 Jun 2022 | 18 Jun 2022 | Dr. Bacha Kebede Debela ¦ debela76@gmail.com | EAPP is requesting collaboration and support in hosting and conducting the Public Administration Capacity Development Conference-"Resolving the Grand Challenges for Sustainable Development in Ethiopia", 15-18 June 2022. |  |  |
| 3900 | Request #3900 ? DPIDG was requested by the International Association of Schools and Institutes of Administration (IASIA) to provide support in enhancing the capacities of governments in Africa to promote public service innovation and digital government for SDGs. | Completed | Division for Public Institutions and Digital Government | 07 Feb 2019 | 26 Jul 2021 | 30 Jul 2021 | Garegin Manukyan ¦ manukyan@un.org | DPIDG was requested by the International Association of Schools and Institutes of Administration (IASIA) to provide support in enhancing the capacities of governments in Africa to promote public service innovation and digital government for SDGs. |  |  |
| 3886 | Request #3886 ? DPIDG was requested by the Ministry of Technology and Innovation of the Government of Ethiopia to provide support on capacity development, experience sharing in financial and technical areas as Ethiopia has embarked on an implementation of the National Digital Transformation Strategy 2025. | Completed | Division for Public Institutions and Digital Government | 19 Oct 2020 | 15 Jun 2021 |  | Mesfin Belachew Tefera (PhD) ¦ mesfin.belachew@mint.gov.et | DPIDG was requested by the Ministry of Technology and Innovation of the Government of Ethiopia to provide support on capacity development, experience sharing in financial and technical areas as Ethiopia has embarked on an implementation of the National Digital Transformation Strategy 2025. |  |  |
| 3679 | Request #3679 ? The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators. As a response to this, the Data for Now initiative was established in 2019 with strong endorsement and support from the UN Statistical Commission in 2020 and 2021. / The Data for Now initiative aims to develop countriesâ€™ capacities to deliver the information needed by local and national policy and decision makers to achieve the 2030 Agenda and make a positive difference in peopleâ€™s lives. To this end, it supports members of the national statistical systems in primarily developing countries to collaborate more effectively with local, national and global partners to leverage innovative sources, technologies and methods for the streamlined production and dissemination of better, more timely and disaggregated data for sustainable development. This initiative is coordinated by the United Nations Statistics Division (UNSD), the World Bank, the Global Partnership for Sustainable Development Data (GPSDD), and the Sustainable Development Solutions Network (SDSN TReNDS). For more information, visit UNSDs project website: https://unstats.un.org/capacity-development/data-for-now/ / In addition to the overall mandate, there are a number of concrete country requests submitted, some still in the process of being formalized, which are or will be attached to this overall demand/request. | Ongoing | Statistics Division | 05 Mar 2021 | 05 Mar 2021 | 01 Mar 2030 | UN Statistical Commission ¦ vibeke.nielsen@un.org | The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators. As a response to this, the Data for Now initiative was established in 2019 with strong endorsement and support from the UN Statistical Commission in 2020 and 2021. / The Data for Now initiative aims to develop countriesâ€™ capacities to deliver the information needed by local and national policy and decision makers to achieve the 2030 Agenda and make a positive difference in peopleâ€™s lives. To this end, it supports members of the national statistical systems in primarily developing countries to collaborate more effectively with local, national and global partners to leverage innovative sources, technologies and methods for the streamlined production and dissemination of better, more timely and disaggregated data for sustainable development. This initiative is coordinated by the United Nations Statistics Division (UNSD), the World Bank, the Global Partnership for Sustainable Development Data (GPSDD), and the Sustainable Development Solutions Network (SDSN TReNDS). For more information, visit UNSDs project website: https://unstats.un.org/capacity-development/data-for-now/ / In addition to the overall mandate, there are a number of concrete country requests submitted, some still in the process of being formalized, which are or will be attached to this overall demand/request. |  |  |
| 3526 | Request #3526 ? The governments of these eight countries expressed interest in participating in a potential project on MSMEs. The Government of Zimbabwe requested to be added to the list of target countries. Request number 3959 refers. | Completed | Division for Sustainable Development Goals | 01 Feb 2021 | 01 Jan 2022 | 31 Dec 2025 | various ¦ var@var.var | The governments of these eight countries expressed interest in participating in a potential project on MSMEs. The Government of Zimbabwe requested to be added to the list of target countries. Request number 3959 refers. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 2737 | Request #2737 ? Capacity Building in designing a project proposal on sustainable forest management | Completed | United Nations Forum on Forest | 01 Feb 2019 | 01 Sept 2020 | 31 Dec 2023 | N/A ¦ yan.lang@un.org | Capacity Building in designing a project proposal on sustainable forest management |  |  |
| 2626 | Request #2626 ? DPIDG was requested by the Ministry of Innovation and Technology of the Government of Ethiopia (as part of the DA1617B) / to assist in the development and successful implementation of e-government in the following major constraining areas: / > Development of the national ICT infrastructure. / > Development of national e-government strategy and National enterprise architecture standard / > Human capital development. / > Development of e-government solutions. / > Implementation experience and expertise from other exposed countries. | Completed | Division for Public Institutions and Digital Government | 30 Jan 2018 | 10 Oct 2018 | 11 Oct 2018 | na ¦ na@gmail.com | DPIDG was requested by the Ministry of Innovation and Technology of the Government of Ethiopia (as part of the DA1617B) / to assist in the development and successful implementation of e-government in the following major constraining areas: / > Development of the national ICT infrastructure. / > Development of national e-government strategy and National enterprise architecture standard / > Human capital development. / > Development of e-government solutions. / > Implementation experience and expertise from other exposed countries. |  |  |
| 2627 | Request #2627 ? The Government of Ethiopia request support in developing institutional capacities of national and sectoral implementing bodies of the SDGs | Completed | Division for Public Institutions and Digital Government | 07 Nov 2018 |  |  | na ¦ na@gmail.com | The Government of Ethiopia request support in developing institutional capacities of national and sectoral implementing bodies of the SDGs |  |  |
| 2628 | Request #2628 ? DPIDG was requested by the Government of Ethiopia to provide support in strengthening institutional arrangements to embed CLEWS. | Completed | Division for Public Institutions and Digital Government | 10 Apr 2019 | 24 Jun 2019 | 28 Jun 2019 | na ¦ na@na | DPIDG was requested by the Government of Ethiopia to provide support in strengthening institutional arrangements to embed CLEWS. |  |  |
| 2590 | Request #2590 ? The Government of Ethiopia requested DPIDG to hold the First National Workshop, Addis Ababa, 10-11 October 2018 to support strengthening institutional capacity in target countries to implement evidence-based government policies and strategies, in support of selected SDGs and Targets. , | Completed | Division for Public Institutions and Digital Government | 03 May 2018 | 10 Oct 2018 | 11 Oct 2018 | na ¦ na@na | The Government of Ethiopia requested DPIDG to hold the First National Workshop, Addis Ababa, 10-11 October 2018 to support strengthening institutional capacity in target countries to implement evidence-based government policies and strategies, in support of selected SDGs and Targets. , |  |  |
| 2581 | Request #2581 ? Description not provided | Completed | Economic Analysis and Policy Division |  |  |  |  |  |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001379.99.30 | Strengthening Inclusive and Shock-Responsive Social Protection Systems in Africa | DISD | 31 Dec 2026 | 31 Dec 2026 | $40,889 | Djibouti, Ethiopia, Ghana, Kenya, Namibia, Rwanda, Senegal, Uganda, United Republic of Tanzania, Zambia |  | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| SB-001376.99.99.31 | Securing the Future of Demographic and Health Data: Country Pathways and a Global Blueprint / | SD | 30 Sept 2026 | 31 Dec 2026 | $86,714 | Bangladesh, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Jordan, Kenya, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Papua New Guinea, Senegal, Tajikistan | Region standardized: 'global' -> 'Global'. |  |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women |
| --- | --- | --- | --- | --- | --- | --- | --- |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002036693 - Ethiopia | 0002036693 | Past | Ethiopia |  | DIVISION FOR SUSTAINABLE DEVELOPMENT GOALS | ORGANIZE CAPACITY BUILDING WORKSHOP IN ETHIOPIA |  | 04 Apr 2025 | 11 Apr 2025 |
| 0002049198 - Ethiopia | 0002049198 | Past | Ethiopia |  | STATISTICS DIVISION | PARTICIPATE AT AFRICA CAPACITY DEVELOPMENT WORKSHOP |  | 18 May 2025 | 23 May 2025 |
| 0002055426 - Ethiopia | 0002055426 | Past | Ethiopia |  | STATISTICS DIVISION | WORKSHOP |  | 04 May 2025 | 10 May 2025 |
| 0002077824 - Ethiopia | 0002077824 | Past | Ethiopia |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | TO ORGANIZE WORKSHOP |  | 18 Jun 2025 | 24 Jun 2025 |
| 0002088581 - Ethiopia | 0002088581 | Past | Ethiopia |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | ATTEND THE AFRICA REGIONAL FORUM ON GOVERNANCE INNOVATION |  | 19 Jun 2025 | 25 Jun 2025 |
| 0002091852 - Ethiopia | 0002091852 | Past | Ethiopia |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | ORGANIZE AND DELIVER CAPACITY DEVELOPMENT ON INNOVATION |  | 19 Jun 2025 | 28 Jun 2025 |
| 0002092693 - Ethiopia | 0002092693 | Past | Ethiopia |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | TO FACILITATE THE AFRICA REGIONAL FORUM ON INNOVATION |  | 18 Jun 2025 | 24 Jun 2025 |
| 0002093240 - Ethiopia | 0002093240 | Past | Ethiopia |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | AFRICA REGIONAL FORUM ON GOVERNANCE INNOVATION: ADVANCING |  | 19 Jun 2025 | 09 Jul 2025 |
| 0002101514 - Ethiopia | 0002101514 | Past | Ethiopia |  | EXECUTIVE OFFICE | SUPPORT TO FOURTH UN CONFERENCE FINANCING FOR DEVELOPMENT |  | 27 Jun 2025 | 12 Jul 2025 |
| 0002263969 - Ethiopia | 0002263969 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | HLAB ON ECONOMIC AND SOCIAL AFFAIRS MEETING ADDIS MAY 2026 |  | 04 May 2026 | 13 May 2026 |
| 0002264573 - Ethiopia | 0002264573 | Past | Ethiopia |  | STATISTICS DIVISION | SD/RPTC RESOURCE PERSON AT CLASSIFICATION REGIONAL WORKSHOP |  | 02 May 2026 | 09 May 2026 |
| 0002265228 - Ethiopia | 0002265228 | Past | Ethiopia |  | DIVISION FOR SUSTAINABLE DEVELOPMENT GOALS | TO PARTICIPATE IN THE ARFSD12 |  | 25 Apr 2026 | 05 May 2026 |
| 0002266011 - Ethiopia | 0002266011 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSGXB: THIRD HLAB MEETING, THIRD TERM |  | 05 May 2026 | 09 May 2026 |
| 0002266149 - Ethiopia | 0002266149 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSG: THIRD UN HLAB MEETING, THIRD TERM |  | 04 May 2026 | 11 May 2026 |
| 0002267860 - Ethiopia | 0002267860 | Past | Ethiopia |  | STATISTICS DIVISION | SDRPTC RESOURCE PERSON ISC REGIONAL WORKSHOP |  | 02 May 2026 | 09 May 2026 |
| 0002268237 - Ethiopia | 0002268237 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSG: THIRD UN HLAB MEETING, THIRD TERM |  | 05 May 2026 | 12 May 2026 |
| 0002269007 - Ethiopia | 0002269007 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSG: THIRD UN HLAB MEETINGTHIRD TERM |  | 03 May 2026 | 11 May 2026 |
| 0002269077 - Ethiopia | 0002269077 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | HLAB SUPPORT AND TO DELIVER WORKSHOPS IN ETHIOPIA |  | 05 May 2026 | 16 May 2026 |
| 0002269101 - Ethiopia | 0002269101 | Past | Ethiopia |  | DEVELOPMENT POLICY AND ANALYSIS DIVISION | HLAB SUPPORT AND TO DELIVER WORKSHOPS IN ETHIOPIA |  | 05 May 2026 | 16 May 2026 |
| 0002272438 - Ethiopia | 0002272438 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSG/XB: HLAB 3RD MEETING IN ADDIS ABABA, 68 MAY 2026 |  | 05 May 2026 | 09 May 2026 |
| 0002278138 - Ethiopia | 0002278138 | Past | Ethiopia |  | OFFICE OF THE UNDER-SECRETARY-GENERAL | OUSB HLAB ADDISABABA & SG DELEGATION NAIROBI 513MAY 2026 |  | 05 May 2026 | 13 May 2026 |
| 0002285004 - Ethiopia | 0002285004 | Past | Ethiopia |  | STATISTICS DIVISION | FIG 2026 EGM ON LAND ADMINISTRATION |  | 24 May 2026 | 31 May 2026 |
| 0002297085 - Ethiopia | 0002297085 | Past | Ethiopia |  | DIVISION FOR SUSTAINABLE DEVELOPMENT GOALS | NATIONAL CAPACITY BUILDING WORKSHOP IN NAMIBIA |  | 14 Jun 2026 | 18 Jun 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 Agenda | 2021 | DSDG; EAPD; UNSD; DPIDG; FSDO; UNFFS; CDPMO; DISD; PD | Bangladesh, Ethiopia, Lao People's Democratic Republic, United Republic of Tanzania | - Prioritize countries which are in the process of preparing their Common Country Analysis (CCA) or other needs assessment processes. / - Increase the visibility of DESA’s capacity building work in its contributions to the CCA to ensure the UN Country Team better understands DESA’s products and services. / - Concentrate on substantive areas in countries where there is already clear demand. / - Convene a group of representatives from the divisions if considering delivery of a monitoring and evaluation product in another interdivisional project. / - Budget for a Coordinator role to help DESA’s divisions plan, implement, and execute operational activities jointly. / - Organize a facilitated workshop during the introductory phase of an interdivisional project to support building collaborative competencies within the divisions. / - Develop a Theory of Change or engage in a process that clarifies concrete outcomes intended to lead to institutional change. / - Develop multiple modalities of capacity building assistance, including working with national consultants to support country level implementation, to mitigate the effects of limited international travel. / - Continue to provide support to access multiple funding sources to support sustainable forest management in LDCs. | - The timing of project activities is instrumental; aligning support with the CCA process creates stronger entry points and partnerships. / - Having a national consultant on the ground greatly facilitates implementation and coordination with UN Country Teams and government. / - The Project Coordinator role is critical for effective communication and leveraging DESA’s expertise across divisions. / - Government capacity to absorb new assistance can be limited by internal hierarchies, competing priorities, and the need for leadership buy-in. / - DESA’s interdivisional projects benefit from an introductory phase where divisions can identify natural synergies and plan joint activities. / - A lack of a Theory of Change limited the ability to outline how intended institutional changes would occur and to track results effectively. / - DESA’s buy-in from the UN Country Team can be enhanced by increasing visibility and clarifying its added value during the CCA phase. / - Ambitious outcome statements in the logical framework should be matched with realistic timeframes and resources for sustainability. / - Gender and human rights mainstreaming require more than tracking participation rates; intentional planning and understanding are needed for effective integration. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_PDF-SDG-2018-02_Eval_DESA_15Dec21.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx rows 268 (archived) and 5 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening national capacities for enhancing Micro-, Small and Medium -sized Enterprise (MSME) resilience and building forward better to accelerate the implementation of the 2030 agenda in developing countries participating in the Belt and Road Initiative | 2025 | DSDG | Cambodia, Democratic Socialist Republic of Sri Lanka, Ethiopia, Gambia, Kenya, Lao People's Democratic Republic, Madagascar, Philippines, Zimbabwe | - Prioritise policy engagement as the primary pathway to scale by supporting policy development and implementation, using entrepreneurs as informants and validators, and convening joint forums for policymakers and entrepreneurs. / - Support the operationalisation of draft policy products by maintaining engagement with national counterparts beyond drafting, providing targeted technical or coordination support, and tracking the status and institutionalisation of policy products. / - Align project scope with available resources and delivery capacity by ensuring ambitions are realistically matched with resources, staffing, and timeframes, and focusing on a manageable number of impactful deliverables. / - Continue leveraging UN DESA’s convening role to connect policymakers and entrepreneurs through joint forums for dialogue, training, and policy validation, ensuring inclusive multi-stakeholder workshops. / - Strengthen outcome-focused, adaptive project design and management by adopting demand-driven and flexible planning focused on meaningful outcomes and allowing adaptation to evolving partner needs. / - Strengthen indicator-based monitoring and follow-up systems by systematically tracking progress against indicators, conducting data collection at multiple points, and establishing follow-up systems for tracking engagement and uptake. | - Drafting policies is not enough—continued engagement is essential to ensure validated drafts are formally adopted and integrated into national systems. / - Convening policymakers and entrepreneurs together in joint workshops creates two-way learning, improves relevance, and increases ownership of training materials and toolkits. / - Adaptive, demand-driven capacity building tailored to country-specific needs and delivered with local partners increases satisfaction and readiness to apply lessons learned. / - Overambitious design limited delivery under constrained resources, highlighting the need to align project ambitions with available capacities and resources. / - Missed monitoring opportunities limited evidence of results, as planned monitoring tools and follow-up surveys were not consistently implemented. / - Policy work scales better than direct training of entrepreneurs, as direct capacity-building activities have limited reach compared to policy interventions that can benefit a larger number of MSMEs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2021/PDF-2021-01 DESA-DSDG/Reports/Final Report and Evaluation/MSME project DESA - evaluation report.docx | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'The Gambia' -> 'Gambia'. |  |
| Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals | 2022 | UNSD | Burkina Faso, Cameroon, Comoros, Eswatini, Ethiopia, Kenya, Niger | - Enhance the availability of geospatial data and information as well as ease of access and regular application of results for evidence-based decision-making through adoption of the manual on standard guiding principles on a global statistical and geospatial framework. / - Continue support to ECA, including funding to select countries despite challenges brought about by the Covid-19 pandemic that contributed to implementation delays and a change in strategy. / - ECA should review future project designs to ensure that all information is accurate and complete, and propose alternative approaches to mitigate against unexpected events that may limit the use of proposed methods. / - The implementor should put in adequate effort to generate high-quality outputs, especially with the extended period, and support learning by the ECA Project team by revisiting key lessons learned through project performance review meetings. / - The ACS team should discuss the project's learning arc and the entire learning outcomes to help ECA and the Center in the design and management of similar future projects. | - The project should seek to strengthen the capacities of ECA Member States in production, utilization, and management of geospatial information for the measuring, monitoring and implementing SDGs through capacity building, developing policy guidelines, and promoting adoption by Member States with technical and political strategy. Lack of official buy-in of the project deliverables indicates that there are political issues to be considered. / - There is a need for greater realism regarding the establishment of structures/institutions, as demonstrated by the non-completion of some outputs. Lobbying relevant government departments and institutions through involvement of national strategies and institutional frameworks for geospatial data infrastructure is necessary. / - Unforeseen delays related to the unprecedented COVID-19 outbreak and affecting the original project design must be given due attention. Expected or planned project outputs and outcomes should be reviewed against what would be realistic to achieve within the No Cost Extension timeframe. / - Inclusion of special interest groups (women) should not be just at the level of data collection; they should be deliberately targeted for technical consultancies and workshop training. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2018-09 Eval_UNECA 2 Dec 2022 (CLEAN).docx |  | evaluations.xlsx rows 42 (archived) and 19 (retained): Review conflicts: Divisions differs: archived row has ''; retained row has 'UNSD'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Implementation of national sustainable development strategies in selected countries in Africa and Latin America | 2020 | DSDG | Costa Rica, Egypt, Ethiopia | - Improve the quality of monitoring, data management and progress reporting so that the project's logical framework is more attune with implemented activities and reflects revisions or adaptations of program strategies. Develop a theory of change and update the project's log-frame with SMART indicators at output, outcome and goal levels for greater monitoring and impact measurement. / - Continue to refine the methodology and analytical tools to enhance their utility and continued use by relevant planning professionals from government and non-government sectors. Develop a clear value proposition, user-friendly toolkit, and online training module, and synthesize feedback and lessons learned from different rounds of methodology implementation. / - Strengthen results-based budgeting and financial metrics to help the project measure both efficiency and value for money. Introduce performance-based budgeting to support monitoring and tracking of expenditures per outcome. / - Enhance the provision, monitoring and reporting of technical assistance activities and advisory missions that complement trainings and consultative workshops. Widen the tools available to national governments beyond training workshops to include technical assistance, advisory missions, diagnostic assessments or policy studies. / - Continue to support member states in the localization of the SDGs by engaging and defining the contribution of subnational government levels in the achievement of the 2030 Agenda. Support national authorities to develop or sustain permanent platforms for sub-national level coordination, engagement, monitoring and reporting on SDS implementation. / - Consider supporting formal and permanent mechanisms for multi-stakeholder collaboration in the context of SDS implementation by supporting and activating existing ones, developing governance frameworks, procedures and rules of engagement, and an enabling environment. / - Enhance the sustainability of future trainings through a comprehensive training strategy including the cascading and roll-out of the training programme. Encourage the use of tools in professional training or degree programs for planning professionals and government executives. / - Continue to engage the private sector while investing more effort in creating a shared understanding around the concept of inclusive business partnerships. Provide stakeholders with knowledge and capacities to effectively engage the private sector through sustainable business practices and inclusive business partnerships. | - Aligning the project interventions and scope of the national workshops with government priorities was conducive to addressing needs and priorities across different national contexts and was well perceived by stakeholders. / - Good coordination with other UN agencies in member states supported the successful execution of activities, providing operational and logistical support as well as continuity with previous efforts in SDGs policy analysis. / - Recruitment of local consultants with subject matter expertise in SDGs proved successful, providing adequate knowledge of local contexts, mobilizing government counterparts’ engagement, and facilitating identification of relevant stakeholders. / - Localization of SDGs through engaging government executives at sub-national levels has proven useful, but further engagement is needed to support governments in prioritizing SDGs in local contexts, target setting, developing sub-national governance and follow-up frameworks, and building capacities for monitoring and reporting progress. / - Knowledge acquisition through national workshops can be optimized by integrating more mentoring processes and post-workshop technical assistance to generate enduring learning curves within national planning institutions. / - Indicators used to measure or demonstrate the effectiveness and impact of capacity building need more consideration and articulation during the design phase. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/10th tranche/DSDG/Final Report_Evaluation of the 10th Tranche DA Project_1617H.pdf |  | evaluations.xlsx rows 106 (archived) and 88 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Accelerating implementation of Data for Now in eight countries in Africa and Asia | 2025 | UNSD | Ethiopia, Jordan, Morocco, Sierra Leone, Tunisia, Viet Nam | - Leverage a wide range of paths to produce desired effects, such as capacity building, increased interactions, and production of better indicators, instead of targeting isolated actions; encourage positioning local resources at country-level to foster coordination and holistic change; place greater emphasis on raising awareness on IT implications of mobilising new techniques. / - Adopt a more structured, wide and long-term approach to capacity building, including clear training plans, performance monitoring, and milestones; ensure training accommodates local realities, particularly language arrangements; use tools like the Statistical Training needs Assessment Tool to streamline structured capacity building. / - During assessment and prioritisation, provide more information on prerequisites for specific innovative techniques, such as access to data, required skills, IT capacities, and potential for application to new areas, to help countries determine the most applicable tools and methods. / - Offer guidance and documentation on optimal organisational and institutional arrangements between NSOs and NSS members, such as exposure to success stories, inspiration workshops, peer reviews, and production of guidelines and methodological frameworks. / - Adopt a 'sandboxing' approach by creating an environment where participants can test new approaches and gain knowledge on innovative methods; this environment should be freely accessible, use open-source services, and complement the production-ready approach. / - Compile a deck of innovative use cases to present project actions in a standardised way, including policy issues, prerequisites, steps, tools, challenges, mitigation strategies, achievements, and testimonies; make resources available on a freely accessible repository along with notebooks, code, and training resources. / - Develop a stronger monitoring and evaluation framework to better capture, in real time, effects and impact generated by the project, including more comprehensive indicators, indicator sheets, and data collection and analysis plans; consider evaluation exercises on the D4N initiative as a whole for more holistic insights. | - Country ownership drives sustainability; countries actively involved in setting priorities and tailoring training content demonstrate higher engagement and a stronger likelihood of sustaining outcomes. / - Tailored technical support yields better results; countries benefit most when technical assistance responds directly to their needs and existing capacities. / - Flexible project design supports responsiveness; the ability to adapt plans in response to emerging needs or challenges is a major strength. / - Strategic partnerships enhance impact; collaboration with international organisations and academic experts brings high-quality, context-specific support and avoids duplication of efforts. / - Dedicated focal points improve coordination; appointing national coordinators or focal persons leads to better planning, faster response times, and improved follow-up. / - Peer learning can accelerate progress; structured opportunities for cross-country experience sharing enable participants to learn from peers’ successes and challenges. / - Monitoring and evaluation mechanisms should be embedded early; a robust M&E system from the start facilitates evidence-based learning and decision-making throughout the project lifecycle. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Active Projects/4 UNSD/D4N M1-60 SB-020332 ITALY/Evaluation/D4N - evaluation report.pdf | Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Evidence-based e-government policies for advancing governmental service delivery and accountability in support of the Sustainable Development Goals | 2019 | DPIDG | Bangladesh, Ethiopia | - Continue discussions with interested parties on the handover of the LDC toolkit and ensure all workshop materials are fully uploaded to the project website for broader access. / - Monitor the pilot initiatives in Bangladesh to draw lessons for organizing future pilots. / - Organize more experience-sharing events focused on e-government, targeting events to specific contexts such as post-conflict or small island states, and create synergies with development banks and the private sector, including exploring public-private partnerships in ICT and e-government. / - Focus more on the gender dimension in future projects, establishing monitoring mechanisms to track and report on how women and men benefit from project activities in a gender-disaggregated manner. / - Give greater attention to implementation in future interventions, ensuring a combination of training, awareness raising, and practical piloting, and link policy proposals in e-government with requisite financial resources and closer partnerships with ministries of finance. | - Country context matters significantly, even for moderate-sized projects; interventions may have greater value-added in environments with less progress but strong political commitment to reform. / - E-Government is a cross-cutting tool with implications for all sectors; cross-sectoral approaches and awareness-raising among officials are essential, but sustained resources and efforts are required for effective sensitization. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DPIDG/1617B SB-006615 10th tranche - eGov Indicators/EVALUATION/Report/Evaluation Report - UNDESA.docx |  |  |
| Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level | 2015 | UNSD | Algeria, Argentina, Bangladesh, Bolivia (Plurinational State of), Botswana, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Chile, Costa Rica, Côte d’Ivoire, Ecuador, Egypt, Ethiopia, Guyana, Jordan, Kenya, Korea, Lebanon, Madagascar, Morocco, Nigeria, South Africa, State of Palestine, Sudan, Togo, Tunisia, Uganda, Uruguay | - Create conditions to improve the technological and knowledge transfer from developed to developing countries. / - Widely promote the adoption of internationally accepted standards related to the generation, process, dissemination and use of geospatial information, created by major standards organizations such as ISO/TC211, OGC, and IHO. / - Include the integration of statistical and geospatial information as a core issue in the UN-GGIM plan work for developing countries, especially in support of the 2020 Round of Censuses and Big Data. / - Continue the work with support of the regional committees of UN-GGIM and the countries themselves to encourage the building of spatial data infrastructures. / - Raise the awareness of the importance of geospatial information at the policy and decision making levels, and strengthen human capacities in developing countries through comprehensive trainings on geodesy, cartography, remote sensing, GIS, and geostatistical mapping. | - The Steering Committee and UNSD/DESA played an important role in aligning the deliveries of the project. / - UNSD/DESA-led projects are effective in connecting experts with organizations and countries interested in geospatial knowledge. / - At a global level, only an organization such as the UN through UNSD/DESA has the capacity to convene and lead projects of this magnitude. / - Developing countries need to increase their technological capacities, which requires more financial resources. / - Improving geospatial information management requires the creation of policies, rules, and methods for information generation, management, dissemination, and use. / - Increasing awareness and support for geospatial and statistical activities among high-level politicians and decision makers is necessary. / - Specialized human resources training is essential for functional geospatial information, beyond just technical, financial, and methodological resources. / - The information exchange mechanism used in this project was effective, allowing developing countries to learn from best practices. / - Institutional coordination between geospatial and statistical offices is still a work in progress and needs to be strengthened. / - Significant gaps in geospatial data and infrastructure exist in developing countries, and this project has helped indicate the right direction. / - There is a lack of economic resources to keep information updated in some developing countries. / - Technological capacities related to geospatial information need to be upgraded. / - There is still a lack of policies, rules, and methods for geospatial information management in some developing countries. / - Specialized human resources training in geospatial disciplines and statistics is essential. / - Strong efforts are needed to create and maintain spatial data infrastructures at all levels, considering the Global Geodetic Reference Frame. / - Awareness and support for geospatial and statistical activities from high-level decision makers need improvement. / - The 2030 Sustainable Development agenda and the 2020 Round of Censuses should be leveraged to reinforce the use of geospatial and statistical data, with executional and follow-up mechanisms for expected outcomes. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 212 - 8th tranche - Geospatial/Evaluation report/Evaluation Report- DA Project-212-8.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Cote d’Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Mobilizing Science, Technology and Innovation in developing countries for the SDGs | 2022 | DSDG | Belgium, Brazil, Cambodia, China, Ethiopia, Ghana, India, Japan, Kenya, Korea, Madagascar, Mozambique, Myanmar, Pakistan, Philippines, Rwanda, Serbia, Thailand, Uganda, United States of America, Zambia | - DESA should ensure that projects are based on clear objectives and SMART, relevant indicators which better help measure the impact of activities. / - DESA should ensure regular and efficient monitoring throughout the project, based on thorough monitoring plans. / - DESA should ensure the continuation of the Innovation Competition and participation in the STI Forum for the winners, and develop a longer term programme of Capacity Building and support for these winners. / - DESA should build on the Capacity Building events, Study Visits, STI Roadmaps work and the Ghana Pilot Programme, which were all highly relevant to STI in developing countries. / - DESA should focus on strengthening the OLP, which currently has a low level of relevance to STI in developing countries. DESA should revisit the Independent Technical Assessment and R4D’s recent report ‘UN 2030 Connect Report’ and integrate the prototypes into the OLP. / - If the OLP and associated capacity building activities are to continue, DESA should look carefully at the human and financial resources behind the work, ensuring that there is enough capacity to deliver meaningful results. DESA should consider the financial recommendations made in the Independent Technical Assessment. Resources available must match the ambition for the work, and the level of ambition should be clarified asap. / - Any future project should include longer term support for innovators on the ground, over a period of at least a year. This could focus on the winners of Innovation Competitions. / - Any future project should build on the successes and the lessons learned of the Ghana Pilot Project, which could be scaled to other countries in partnership with R4D. / - DESA should improve the ongoing monitoring around such projects, strengthening the indicators (ensure SMART and relevant indicators) and ensuring that questionnaires are provided to participants following relevant activities (Capacity Building sessions, Study Visits etc). / - DESA should spend more time persuading and convincing partners of the value of integrating their databases with that of the OLP, in order to address the perceived incoherence with OLP partners. / - DESA and partners should consider the viability of one overarching STI project / work stream which incorporates the various streams of work being undertaken - the STI Forum, STI Roadmaps for SDGs, 2030 Connect, Capacity Building etc. The possibility of a joint funding mechanism – an STI Trust Fund – should be explored in order to reduce inefficiencies. / - DESA should allocate meaningful human resources (at least 60% of a full time role) to ensure the success of the OLP and associated Capacity Building activities. / - DESA should ensure that resources allocated to the OLP match the ambition for the OLP. / - DESA should consider allocating more funds for longer term Capacity Building support to innovators across target countries. / - DESA should consider replicating / adapting the relationship with R4D, recognising the importance of having local partners to work with local innovators. This could either be done with R4D, other relevant CSOs or UNCTs (UN Country Teams). / - DESA should ensure there is enough time available for meaningful work to be completed, avoiding last minute rushes. / - DESA should systematically work through tools like Exit strategies, succession planning and cases for financial support before the end of a project, in order to ensure sustainability, whether a project is designed to continue or not. / - DESA, with the IATT, should revisit the Independent Technical Assessment, as well as the recent recommendations by R4D for the OLP, in order to be very clear about the ambition and strategic direction of the OLP before developing the case for support. / - Given the clear mandate provided by MS for the OLP, DESA should attempt to secure a mixture of UN regular budget and voluntary/extra-budgetary funds to finance the OLP. / - DESA should ensure that capacity building activities take place over a longer period, and provide more sustained support for innovators. This should be built into the case for support. / - The UN should integrate the principle of Leave No-One Behind into all its STI related work, ensuring that it does not inadvertently enhance the digital divide. This could be done in the context of this project by offering capacity building activities in different languages, offering interpretation, and ensuring translation of the OLP. / - DESA should consider scaling up the Ghana Pilot Project into other countries, specifically the Technical Support offered to local innovators. / - DESA should build on the momentum around the STI Roadmaps for SDGs and investigate whether a coherent package of work can be built around the Roadmaps, the OLP and the capacity building activities. / - DESA and OICT should consider structuring the OLP (specifically the Search Engine) around the SDGs in order to facilitate closer linkages between STI and HR & GE. / - DESA, and the UN more widely, should strengthen the focus on HR & GE in the project design and monitoring, including concrete details of how HR & GE issues will be addressed. UNEG’s guidance on this should be considered. / - DESA, and the UN more widely, should respect the SDG principle of LNOB by ensuring Capacity Building activities include interpretation, and official sites are available in at least the 6 official languages of the UN. / - DESA should consider contributing to tackling the existing gender inequality in STI by insisting on having at least 50% of women as speakers, moderators and participants in events. / - DESA should incorporate HR & GE specific indicators in its project design. Again, UNEG’s guidance on this should be considered. / - DESA should commit to gathering disaggregated data throughout its projects, starting with clear participant lists for every activity. / - The UN PDF should ensure that the recently developed form which collects HR & GE data is consistently used across all projects which it supports. / - DESA should build on the good practise of the Study Visits, Capacity Building Sessions and Ghana Project, linking STI to specific SDGs and gender issues in order to ensure a meaningful focus on HR & GE. / - DESA should use its position as implementer of this project and Co-Convenor of the IATT to work closely with the IATT to consider the ambition and funding for the OLP, ensuring coherence with the mandate given by MS in Agenda 2030, the AAAA and the Independent Assessment. / - DESA should continue the practise of piggybacking on other meetings and cost-sharing when organising activities. | - The project design could have been improved by developing stronger and more relevant indicators which better help measure the impact of the activities, and by ensuring regular and efficient monitoring throughout the project. / - Insufficient human and financial resources can significantly limit the effectiveness and efficiency of project implementation. / - A lack of clear exit planning, succession planning, and fundraising strategy can undermine the sustainability of project outcomes. / - Longer-term engagement and support for innovators, rather than one-off events or competitions, are valued and more likely to lead to sustained impact. / - Capacity building activities are more inclusive and effective when offered in multiple languages and with interpretation, supporting the Leave No-One Behind principle. / - Partnerships with local organizations, such as R4D in Ghana, enhance the relevance and effectiveness of capacity building for local innovators. / - Integrating gender and human rights considerations from the project design stage, with specific indicators and disaggregated data, leads to better outcomes and more inclusive participation. / - Administrative and technical barriers to integrating partner databases can undermine the effectiveness and coherence of online platforms. / - Piggybacking on existing meetings and cost-sharing with partners increases efficiency and reach. / - Clear political mandates and alignment with broader UN strategies facilitate project relevance and coherence, but must be matched by adequate resources and stakeholder engagement. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2016/PDF-2016-03 DSD internal STI/Reports/Final report & Eva/fisrt ver. 18 Mar 22/STI Evaluation LW final.pdf | Country standardized: 'USA' -> 'United States of America'. | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation | 2021 | DSDG | Algeria, Argentina, Austria, Bolivia (Plurinational State of), Bosnia and Herzegovina, Bulgaria, Colombia, Ecuador, Ethiopia, Georgia, Ghana, Guyana, Honduras, India, Italy, Kenya, Lebanon, Malawi, Morocco, Nauru, Niger, North Macedonia, Pakistan, Papua New Guinea, Poland, Portugal, Samoa, Seychelles, United Arab Emirates, United Kingdom of Great Britain and Northern Ireland, Zambia | - Future similar projects should apply a Results-Based Management approach, developing an M&E framework, plan, and data collection tools that articulate instrumental and transformational changes rather than processes. / - Additional resources should be mobilized to ensure follow-up and implementation of the commitments secured in the global roadmap and in the Energy Compacts, starting with pilot projects to determine their viability and scalability. / - Future similar projects should include studies on Cost-Benefit Analysis to determine the viability and scalability of policy changes, ranking options in the Energy Compacts according to their costs and benefits to society. / - More staff wholly dedicated to the project should be planned for at the conceptualization stage, including roles for communications and project management assistance, and a project steering committee to ensure recommendations for course corrections are followed. / - Future projects should develop a clear partnership strategy to guide implementers on where to invest in collaboration for the greatest value to the organization. / - The composition of the global Technical Advisory Group (TAG) should be replicated and cascaded to regional and national levels to ensure continuity and nuanced specificities beyond the project’s shelf life. / - Future projects should leverage United Nations Information Centers (UNICs) to develop and implement coordinated communications strategies for Member States, amplifying project achievements at the local level. | - The joint production and dissemination of knowledge products laid a strong foundation for sustainability, scaling up, replication, and future programming, increasing knowledge and capacities for accountability. / - Synergistic partnerships and multi-stakeholder participation facilitated ownership, sustainability, and coherence between national planning processes, enhancing coordination among line ministries for timely VNR production. / - Upstream activities allowed the project to adapt to challenges such as Covid-19, and partnering with the public sector leveraged government influence for mainstreaming SDG7 implementation. / - Engagement with the private sector was strategic, as private sector input and financial commitments in the Energy Compacts are essential for accelerating SDG7 implementation. / - The project was initially thinly staffed, but hiring a dedicated Project Officer after commencement improved implementation; future projects should plan for adequate dedicated staffing from the outset. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2017/2017-02 DSD SDG7/Reports/Evaluation/Final_Dec 18th_UNDESA_Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| Monitoring and reporting on sustainable development objectives, goals and targets: enhancing institutional capability in selected developing countries | 2018 | DSDG; UNSD | Belize, Colombia, Ethiopia, Honduras, Jordan | - Proceed with group training workshops at the regional level, in combination with E-learning as a complementary tool, due to resource constraints and language challenges. / - Enforce a pre-training selection of national participants with at least some basic knowledge of strategic planning and management, and allocate a longer period of time to the Training of Trainers (ToT). / - Extend the Training Curriculum beyond the pilot countries, translate it into other languages, and revise future versions to be more practical and action-oriented with concrete case studies, especially for local level planning. / - Disseminate the Training Curriculum by involving universities and other institutions in as many countries as possible to broaden its reach and impact. / - Scale up the activities of the project, such as RBM learning, to involve more officials and the right drivers in each country, and consider using a website or E-learning platform for wider dissemination. / - Involve the National Statistical Office (NSO) at an early stage and strengthen or modernize the national statistical system to improve provision, access to, and use of quality data and related technologies for SDG indicators. / - Take into account the geographic dimension of data and related geospatial information and earth observations in future projects, and collaborate with UNSD to streamline UN support for strengthening countries' information infrastructures and statistical systems. / - Increase focus on domestic resource mobilization and build partnerships with the private sector and other stakeholders within the country to support project performance and outcomes. / - Encourage countries to proactively seek counter-part funding and additional support from other donors for project activities. / - Reinforce cooperation with UN agencies and UN-DESA, and continue collaborative work with UN Country Teams and UN Regional Commissions to address challenges effectively. | - Developing country-specific implementation workplans based on capacity assessments was crucial for refining project objectives and ensuring successful execution. / - The Training Curriculum on Results-Based Management (RBM), supplemented by a facilitator manual in three languages, was highly informative and provided valuable guidance for planning, implementation, and monitoring of the SDGs. / - The International ToT Workshop was effective for sharing the curriculum widely and demonstrated the value of tailoring tools and methods to local contexts. / - Learning RBM methodology requires participants to have some basic knowledge in strategic planning and management; its application to SDGs is most effective when carried out by well-trained key representatives from government departments. / - Applying RBM at the local level requires data disaggregation by location and the collection, processing, analysis, and dissemination of large amounts of data from both official and innovative sources. / - Strong support and commitment from high-level decision makers, engagement of government departments, and involvement of all stakeholders, including civil society, private sector, and academia, are crucial for successful domestic implementation of SDGs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DSDG/ROA 265-SB-001292-1415I- 9th tranche_Monitoring and reporting on SD objectives/Evaluation/Final Evaluation Report- DA 1415I.docx |  |  |
| Strengthening Capacities of the Public Sector in least developing countries to deliver quality services equitably through the transfer and adaptation of innovative practices | 2016 | DPIDG | Bahrain, China, Ethiopia | - DPADM should consider creating a blog to post updates on research material on recommended best practices and the progress made by various LDCs in implementing practices learned. / - For future technical cooperation projects, DPADM should consider constituting a Steering Group made of various experts and possibly select members of EGM and a representative of CDO to provide advice and support throughout project implementation. / - DPADM should take a more active role in the selection of participants by issuing clear criteria for who should apply, including required level of authority and gender representation, clarifying expected outputs, and vetting candidates based on those criteria. / - DPADM should take a more active role in the selection of lecturers, considering quality and background. / - Inform and discuss with host country coordinators and lecturers the participants’ background before the workshop to ensure more relevant information for participants. / - DPADM should vet and validate all documents and learning material in advance of the visit, prioritizing inclusion of case studies on best practices and how challenges were solved, and ensure quality and readability of documents such as training slides in proper translation. / - Organize at the beginning of the workshop a few presentations and facilitated discussions by participants of their country’s situation and challenges, with all lecturers present. / - Involve UNDP country representatives at an early stage and seek their advice on identifying additional resources for project delivery, including the implementation phase. | - Selecting LDCs based on demonstrated potential and commitment to engage in innovation relevant to their context may require closer analysis of specific needs and engagement with potential partners, leading to different implementation paths. / - The peer-to-peer method is valuable but was not consistently implemented throughout the project. / - Outcomes of the first two study tours should have been monitored more effectively by DPADM, and lessons learned and recommendations applied with greater timeliness to improve subsequent events. / - DPADM should have recognized early that the adaptation process between host and recipient governments was not proceeding as planned and encouraged adoption of less formal agreements. / - The project design underestimated the complexity of government-to-government partnerships and the level of decision-making authority needed by delegates; selection criteria should include technical skills, authority, and gender representation. / - UNDP resources could have been mobilized more effectively during the Bahrain study tours for delivery, follow-up, and possibly additional funding of national participants. / - There was lack of participation by some collaborators identified in the TORs, such as UNODC, UN Women, and UN Habitat, whose advice and support could have been better mobilized. / - Internal resources of DPADM, particularly eGB, could have been leveraged more effectively during the first two years of the project. / - The 'Guide for the Transfer and Adaptation of Innovation in Governance' should have been shared with all relevant partners, such as the Chinese Academy of Governance, to facilitate preparations. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 206 - DPADM Final Evaluation Report.pdf |  |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Development Account Project -8th Tranche “Strengthening the capacity of selected developing countries to mainstream sustainable development into national development strategies” | 2016 | DSDG | Belize, Costa Rica, Ethiopia, Honduras, Togo, Uganda, Viet Nam | - Continue to focus on the DA-8 project achievements, especially through the appropriate mix of approaches established and fine-tuned during the past two years. Higher Management needs to decide sooner than later the fate of the global learning network as well as critical means for DESA/DSD to maintain its natural niche and preserve its comparative advantage toward the 2030 Agenda on sustainable development. / - Facilitate the conduct of more intra-regional workshops and training among neighboring countries to create greater opportunities for synergy of actions and for sharing best practices from a regional perspective. Such an approach would enhance regional sustainability and allow economy of scale for DESA/DSD. / - Enhance the capacity of civil society organizations and multi-stakeholders (other than Government representatives) to play a more active role in policy dialogue designed to integrate sustainable development into national policies and strategies. Strong participation of multiple stakeholders will ensure greater local ownership and increase the potential viability of these activities after DESA/DSD involvement ends. / - Focus more on results in gender related issues and sustainable development; greater participation of women organizations in policy dialogue on sustainable development will ensure greater attention of ministries involved in this cross-cutting issue. / - Consider developing an exit strategy as part of the approach for supporting selected countries in a time limit and identifying ways of not abandoning those in more urgent needs. The exit strategy should be supported by incentives to encourage recipient countries to explore other sources of funding and other means for resource mobilization. / - Explore effective mechanisms to develop partnerships, coordinate and harmonize more its actions in the field with other like-minded donors and UN Agencies on sustainable development; joint funding should be considered given DESA/DSD limited budget and the accomplishments and relevance of the DA-8 activities. / - Facilitate better internal synergy between Divisions and services (Financial, HR, Technology) at HQ in terms of sequential actions between Tranches: 8, 9 and 10. This will require developing and strengthening monitoring and evaluation mechanisms, making evaluation an integral part of the project design, greater involvement of partners/stakeholders throughout the evaluation process, and sharing evaluation results, progress reports as well as shortfalls. / - Encourage countries to establish, with existing expertise, an administrative structure that would facilitate better synergy and coordination within the government, national ownership and appropriation, involving multiple Ministries and state institutions. | - The DA-8 project evolved in very challenging and complex environments as it was implemented simultaneously in seven different countries, but proved relevant to all selected countries. Project design and implementation processes need to be flexible enough to adapt to each country’s evolving context and environment. / - The establishment of a very inclusive stakeholder platform, complemented by strong political will, high-level commitment, political stability or continuity, and clear definition of roles and responsibilities, creates favorable conditions for successful implementation of sustainable development strategies. / - Developing strategic alliances or partnering with other like-minded institutions is crucial for successful coordination and implementation in the field. Clear terms and roles between partner UN agencies and other donors are important before implementation. / - High-level government officials need to be engaged in every phase of the project, including broad consultation and policy dialogue, to ensure buy-in and ownership. Commitment of resources and time is essential to secure broad societal support. / - Scoping analysis, missions, and annual reports on project implementation are good practices for learning and provide critical information for current and future projects, but need to be transformed into more strategic tools for decision making. / - National and regional workshops and expert group meetings are effective consultation mechanisms, but should be truly representative and inclusive by facilitating participation of a broader spectrum of stakeholders, including civil society organizations, private sector, and women organizations. / - Guidance Notes and Training Manuals produced in partnership with UNITAR are effective tools for raising awareness and sharing lessons learned, but need to be adapted to local and municipal realities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 208 - DSD Final Evaluation Report.pdf | Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Development Account Project - 8th Tranche: Strengthening the capacity of selected developing countries to mainstream sustainable development into national development strategies | 2016 | DSDG | Belize, Costa Rica, Ethiopia, Honduras, Togo, Uganda, Viet Nam | - Continue to focus on the DA-8 project achievements, especially through the appropriate mix of approaches established and fine-tuned during the past two years. Higher Management needs to decide sooner than later the fate of the global learning network as well as critical means for DESA/DSD to maintain its natural niche and preserve its comparative advantage toward the 2030 Agenda on sustainable development. / - Facilitate the conduct of more intra-regional workshops and training among neighboring countries to create greater opportunities for synergy of actions and for sharing best practices from a regional perspective. Such an approach would enhance regional sustainability and allow economy of scale for DESA/DSD. / - Enhance the capacity of civil society organizations and multi-stakeholders (other than Government representatives) to play a more active role in policy dialogue designed to integrate sustainable development into national policies and strategies. Strong participation of multiple stakeholders will ensure greater local ownership and increase the potential viability of these activities after DESA/DSD involvement ends. / - Focus more on results in gender related issues and sustainable development; greater participation of women organizations in policy dialogue on sustainable development will ensure greater attention of ministries involved in this cross-cutting issue. / - Consider developing an exit strategy as part of the approach for supporting selected countries in a time limit and identifying ways of not abandoning those in more urgent needs. The exit strategy should be supported by incentives to encourage recipient countries to explore other sources of funding and other means for resource mobilization. / - Explore effective mechanisms to develop partnerships, coordinate and harmonize more actions in the field with other like-minded donors and UN Agencies on sustainable development; joint funding should be considered given DESA/DSD limited budget and the accomplishments and relevance of the DA-8 activities. / - Facilitate better internal synergy between Divisions and services (Financial, HR, Technology) at HQ in terms of sequential actions between Tranches 8, 9 and 10. This will require developing and strengthening monitoring and evaluation mechanisms, making evaluation an integral part of the project design, greater involvement of partners/stakeholders throughout the evaluation process, and sharing evaluation results, progress reports as well as shortfalls. / - Encourage countries to establish, with existing expertise, an administrative structure that would facilitate better synergy and coordination within the government, national ownership and appropriation, involving multiple Ministries and state institutions. | - The DA-8 project evolved in very challenging and complex environments as it was implemented simultaneously in seven different countries, but proved relevant to all selected countries. Project design and implementation need to be flexible enough to adapt to each country’s evolving context and environment. / - The establishment of a very inclusive stakeholder platform, complemented by strong political will, high-level commitment, political stability or continuity, and clear definition of roles and responsibilities, creates favorable conditions for successful implementation of sustainable development strategies. / - Developing strategic alliances or partnering with other like-minded institutions is crucial for successful coordination and implementation in the field. Clear terms and roles between partner UN agencies and other donors are important before implementation. / - High-level government officials need to be engaged in every phase of the project, including broad consultation and policy dialogue, to ensure buy-in and ownership. Commitment of resources and time is essential for securing broad societal support. / - Project management should ensure that government is accountable for engaging broader CSO participation and coordinate with existing national development efforts. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/Word docs/ROA 208 - DSD Final Evaluation Report.docx | Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities | 2014 | DSPD | Ethiopia, Kenya, South Africa, Zambia | - Schedule a further phase of collaboration to implement activities that were planned but not completed, including follow up visits to project countries. / - Introduce former participants to the new Toolkit modules and updated package developed. / - Support the establishment or development of national multi-stakeholder committees to monitor, report and implement provisions of the CRPD. / - Work with participants of the ToT Workshops to support them to develop training plans and strategies. / - Support training of key target groups identified by local stakeholders including parliamentarians and the judiciary. / - Appoint and agree terms of reference for a national consultant in each country to support training activities. / - Follow up with local UN agencies to ensure their involvement in customising the toolkit for the local context. / - Further develop the Toolkit, including making it user friendly, adding video resources, developing detailed session plans, and creating trainers and participant manuals. / - Carry out a review process involving experts on each topic to ensure and improve the quality of the Toolkit content. / - Request relevant UN agencies and DPO experts to review specific Toolkit modules for quality and completeness. / - Include references to key websites within each module topic to allow trainers to expand their knowledge. / - Develop and implement a strategy for introducing the Toolkit to new countries, including establishing a local working group and understanding local coordination mechanisms. / - Extend the ToT by at least one day and consider a further stage where trainees train others under observation. / - Develop 'Master Trainers' in each country or region to carry out training of trainers and monitor training quality. / - Develop accessible multimedia training materials and make modules available through an e-learning tool. / - Simplify the language and structure of the Toolkit and provide materials in alternative and accessible formats. / - Engage with DPOs and provide resources for their involvement. / - Follow up with organizations and departments after training to assess changes made. | - A clear brief for the toolkit style at the outset could have saved time and resources and made it easier to use multiple consultants. / - Developing one initial module and reviewing it to agree on style, language, and complexity could have benefited the development process. / - UNDESA is now well positioned to develop a strategy for introducing the Toolkit to new countries and guiding local customisation. / - Strong local counterparts are essential to ensure activities can progress, as shown by challenges in Ethiopia due to lack of local commitment. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/ROA-180-CRP with Disabilities/Final & evaluation reports/EvalReport_UNDESA_FINAL_CC_140111.pdf |  | evaluations.xlsx rows 299 (archived) and 283 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Ethiopia; Kenya; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DSPD'; Evaluation Year differs: archived row has ''; retained row has '2014'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Enhancing National Statistical Capacity to Measure, Monitor, Assess and Report on Progress on Achieving Post-2015 Goals and Targets for Sustainable Development | 2018 | UNSD; DSD | Cambodia, Ethiopia, Philippines, Rwanda, Uganda, Viet Nam | - Future projects in the African region should encourage more equal gender participation in the workshops. / - UNSD may consider devoting a few sessions in future training workshops on steps and good practices on streamlining the use of administrative data sources for compilation of SDG indicators. / - Engage a local national consultant to pursue follow-up actions on the recommendations of the country missions before the next mission is undertaken by the regional consultant. / - Discussions should be undertaken with the participating countries to assess what future support is needed and is available, particularly to assist with meeting the objectives of their national action plans. | - All workshops organized as part of the national statistical system’s assessment, capacity building phase and concluding phase of the project played a significant role in the successful achievement of the project objectives. / - Engagement of the NSO and other data producers in subject matter ministries with the UNSD regional consultant during his/her country mission provided an opportunity for better awareness and understanding of data for compilation, monitoring and reporting requirements of the SDG indicators. / - Without the support of the regional consultants and the guidance and feedback provided by the UNSD through the process, it would have been extremely difficult for countries to develop meaningful national action plans. / - The involvement and support of regional, international organizations and other United Nations agencies contributed to the success of the project and the sustainability of the outcomes. / - Results of the work on an integrated regional indicator frameworks and related methodological work being undertaken by ESCAP and ECA should be shared with countries as soon as they become available. The UN country teams were seen by the participants as the important players as well, especially in improving the coordination of technical assistance provided by the UN agencies to the NSO and other members of NSS. / - Countries are fully aware of the need to establish proper institutional arrangements for coordination of the statistical activities to ensure a successful compilation of the SDG indicators. In most countries the concrete steps are made in this direction include establishing special SDGs dedicated task forces, working groups or by amending TORs of the existing bodies. Still, the task is not yet completed for the following main reasons: (a) frequently, NSOs do not have enough authority, resources and (in a number of statistical domains) professional expertise to ensure proper coordination, (b) statistical activities in many line ministries are still fragmented, underfunded and are planned without proper coordination with NSOs, (c) prioritizing and scheduling of the assistance by the UN System Agencies and other development partners to various members of the national statistical system is not sufficiently transparent which makes coordination more difficult and less efficient. / - Many global indicators are not applicable at a developing country level due to the global nature of the data sources needed for their compilation or country specific circumstances (e.g. geographical location). The number of such indicators varies from country to country, but it is estimated to be about 10 per cent of all global indicators. This meaning that about 10 per cent of the global SDG indicators will not be considered for compilation by the national statistical systems. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 303 1415 AU SB-001291 - SDG Post 2015/Evaluation/FINAL Evaluation Report 2018 (final - Nov 2018).pdf | Country standardized: 'Vietnam' -> 'Viet Nam'. |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 2 | evaluations.xlsx rows 106 (archived) and 88 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 3 | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 268 (archived) and 5 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 8 | evaluations.xlsx rows 299 (archived) and 283 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Ethiopia; Kenya; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DSPD'; Evaluation Year differs: archived row has ''; retained row has '2014'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | evaluations.xlsx rows 42 (archived) and 19 (retained): Review conflicts: Divisions differs: archived row has ''; retained row has 'UNSD'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 10 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 11 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. |
| 12 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. |
| 13 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. |
| 14 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. |
| 15 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| 16 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 17 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 18 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 19 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 20 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 21 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 22 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 23 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 24 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 57 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 62 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 65 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 66 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 67 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 68 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 69 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 70 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 71 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |