Fiji

Oceania | SIDS

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Fiji is presented in this country card as part of Oceania, with Fiji also associated with an unspecified subregion and the SIDS grouping. The filtered data for Fiji highlights 12 projects for Fiji, including 4 active or planned projects for Fiji and 6 completed or closed projects for Fiji.

For Fiji, the report includes 26 requests for Fiji, 3 RPTC proposals for Fiji, 2 RPTC activities for Fiji, and 4 travel records for Fiji. Financially, Fiji shows USD 15,477,455 in project budget, $275,690 in proposal planned budget, and $194,900 in consumed RPTC activity budget for Fiji.

The main organizational coverage for Fiji points to DISD, Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, DPIDG. Activity records for Fiji list 89 participants, including 47 women participants, the current quality review for Fiji includes 87 data quality notes. Current highlights for Fiji include a request focus for Fiji: Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data.

      

      

      
This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing.

      

      

      
The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint.; an RPTC proposal focus for Fiji: Pacific SIDS Regional Energy Statistics Training Workshop
; an activity focus for Fiji: Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 12 |
| Project budget | USD 15,477,455 |
| Requests | 26 |
| RPTC proposals | 3 |
| Proposal planned budget | $275,690 |
| RPTC activities | 2 |
| Consumed RPTC budget | $194,900 |
| Activity participants | 89 |
| Women participants | 47 |
| Travel records | 4 |
| Evaluations | 5 |
| Data quality notes | 87 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Developing institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals |  | country | Division for Public Institutions and Digital Government | Closed | 01 Oct 2021 | 31 Oct 2024 | USD 824,649 | Bangladesh, Bhutan, Cambodia, Democratic Socialist Republic of Sri Lanka, Egypt, Ethiopia, Fiji, Gambia, Ghana, Lao People's Democratic Republic, Morocco, Namibia, Rwanda, Samoa, Sierra Leone, United Republic of Tanzania, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Enhancing national capacities for unleashing full potentials of micro-, small- and medium-enterprises (MSMEs) in achieving sustainable development goals in developing countries | 2016-04 | country | Division for Sustainable Development Goals | Closed | 31 May 2017 | 31 Dec 2021 | USD 1,652,296 | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Institutional arrangements for policy integration, coordination and stakeholder engagement in SDG implementation and reviews in Asia, and Asia and the Pacific | 1819G | country | Division for Public Institutions and Digital Government | Closed | 01 Apr 2018 | 31 Dec 2021 | USD 600,000 | Bhutan, Fiji, Lao People's Democratic Republic, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. |  |
| Integrated and coherent national recovery strategies promoting social inclusion, macroeconomic stability, effective governance and protection of the environment for selected small island developing states | 2326B | country | Economic Analysis and Policy Division | Active | 01 Feb 2023 | 31 Dec 2026 | USD 700,000 | Dominican Republic, Fiji, Guinea-Bissau, Mauritius, Seychelles |  | projects.csv record 'Integrated and coherent national recovery strategies promoting social inclusion, macroeconomic stability, effective governance and protection of the environment for selected small island developing states ¦ 2023-02-01T00:00:00 ¦ 2326B': Possible duplicate project code '2326B'. Both records retained pending review: projects.csv: Integrated and coherent national recovery strategies promoting social inclusion, macroeconomic stability, effective governance and protection of the environment for selected small island developing states; projects - the one.xlsx: Integrated and Coherent National Recovery Strategies Promoting Social Inclusion, Macroeconomic Stability, Effective Governance, and Protection of the Environment for Selected SIDS |
| Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure |  | country | Financing for Sustainable Development Office | Active | 01 Mar 2026 | 01 Mar 2029 | USD 2,510,310 | Fiji, Gambia, Kenya, Senegal, Uganda, Zambia |  |  |
| Accelerating SDGs in Developing Countries: Promoting Juncao Technology for Resilient Food Systems, Poverty Eradication and Climate Adaptation |  | country | Division for Sustainable Development Goals | Ongoing | 01 Jul 2025 | 30 Jun 2028 | USD 2,721,400 | Democratic Socialist Republic of Sri Lanka, Fiji, Kenya, Nepal, Nigeria, Papua New Guinea, Rwanda, United Republic of Tanzania | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Harnessing Synergies Between Climate Action, Energy, and Sustainable Development for Delivering the Paris Agreement and the SDGs |  | country | Division for Sustainable Development Goals | Under development | 01 Jan 2027 | 31 Dec 2030 | USD 696,000 | Democratic Socialist Republic of Sri Lanka, Fiji, Nepal | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Integrating Macroeconomy and Resource Systems for Country Planning in Asia-Pacific |  | country | Economic Analysis and Policy Division | Under development | 01 Jan 2027 | 31 Dec 2030 | USD 622,800 | Cambodia, Fiji, Nepal, Philippines |  |  |
| Statistics and Data Project ‐ Resilient and agile National Statistical Systems (NSS) to meet post COVID‐19 data needs to recover better | 2225A | country | Statistics Division | Closed | 01 Sept 2022 | 31 Oct 2025 | USD 3,000,000 | Bhutan, Burundi, Dominican Republic, Ecuador, Eritrea, Fiji, Georgia, Indonesia, Jamaica, Jordan, Kazakhstan, Namibia, Republic of Moldova, Senegal, State of Palestine, Tunisia |  |  |
| Strengthening geospatial information management in developing countries towards implementing the 2030 Agenda | 1819D | country | Statistics Division | Closed | 01 Mar 2018 | 31 Dec 2022 | USD 750,000 | Burkina Faso, Ethiopia, Fiji, Mongolia, Nepal, Tonga |  |  |
| Support to Integrated National Financing Frameworks (INFFs) in SIDS |  | country | Financing for Sustainable Development Office | Closed | 01 Nov 2022 | 31 Dec 2025 | USD 800,000 | Dominican Republic, Fiji, Mauritius, Seychelles |  |  |
| Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases | 2326C | country | United Nations Forum on Forest | Active | 01 Feb 2024 | 31 Dec 2024 | USD 600,000 | Fiji, Malawi, Uganda, Viet Nam |  |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |  |
| 5565 | Request #5565 ? Fiji is formally requesting to join the UN DESA integrated macroeconomic and resources modeling initiative to build local capacity for analyzing climate, energy, and economic policies. / Key Objectives: / Policy Assessment: Analyze trade-offs across energy, agriculture, industry, and economic sectors. / Resource Planning: Assess land-use impacts on agriculture and determine optimal renewable energy mixes. / Financial Evaluation: Analyze national debt challenges and showcase the return on investment for climate adaptation. / Climate Resilience: Model short-term extreme weather impacts and long-term climate change effects on the economy. / Funding Access: Leverage data and modeling to facilitate access to critical climate funding. | Under consideration | Economic Analysis and Policy Division | 15 Jul 2026 | 03 Aug 2026 | 31 Dec 2026 | Filipo Tarakinikini ¦ mission@fijiprun.org | Fiji is formally requesting to join the UN DESA integrated macroeconomic and resources modeling initiative to build local capacity for analyzing climate, energy, and economic policies. / Key Objectives: / Policy Assessment: Analyze trade-offs across energy, agriculture, industry, and economic sectors. / Resource Planning: Assess land-use impacts on agriculture and determine optimal renewable energy mixes. / Financial Evaluation: Analyze national debt challenges and showcase the return on investment for climate adaptation. / Climate Resilience: Model short-term extreme weather impacts and long-term climate change effects on the economy. / Funding Access: Leverage data and modeling to facilitate access to critical climate funding. |  |  |
| 5406 | Request #5406 ? In the context of DA15 project "Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases", the UNFF Secretariat will organize a multi- stakeholder workshop in Fiji with the purpose of i) building the skills of national stakeholders on integrated forest landscape restoration (IFLR) concepts and practices, and ii) finalize and validate the draft national IFLR strategy | Completed | United Nations Forum on Forest | 22 Oct 2025 | 15 Nov 2025 | 28 Feb 2026 | Ms. Sanjana D. Lal ¦ tfong@mff.gov.fj | In the context of DA15 project "Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases", the UNFF Secretariat will organize a multi- stakeholder workshop in Fiji with the purpose of i) building the skills of national stakeholders on integrated forest landscape restoration (IFLR) concepts and practices, and ii) finalize and validate the draft national IFLR strategy |  |  |
| 5387 | Request #5387 ? Transitioning to renewable energy is one of the most pressing policy issues in the Pacific region. Pacific SIDS face distinct challenges in transitioning to renewable energy, including limited resources and infrastructure, high dependence on imported fossil fuels and vulnerability to climate change. High-quality energy statistics and balances and GHG inventories play an important role in providing the data needed for effective policies for renewable energy transitions and climate change mitigation in Pacific SIDS. / Pacific SIDS requested the Pacific Community and the United Nations Statistical Institute for Asia and the Pacific (SIAP), with who we are organizing the workshop, to provide assistance on energy statistics and balances. The workshop aims to further build capacities in the region for the compilation of energy information in support of just energy transitions and climate change policies. | Under consideration | Statistics Division | 25 Nov 2025 | 25 Mar 2026 | 27 Mar 2026 | Jessica Ying Chan ¦ jessica.chan@un.org | Transitioning to renewable energy is one of the most pressing policy issues in the Pacific region. Pacific SIDS face distinct challenges in transitioning to renewable energy, including limited resources and infrastructure, high dependence on imported fossil fuels and vulnerability to climate change. High-quality energy statistics and balances and GHG inventories play an important role in providing the data needed for effective policies for renewable energy transitions and climate change mitigation in Pacific SIDS. / Pacific SIDS requested the Pacific Community and the United Nations Statistical Institute for Asia and the Pacific (SIAP), with who we are organizing the workshop, to provide assistance on energy statistics and balances. The workshop aims to further build capacities in the region for the compilation of energy information in support of just energy transitions and climate change policies. |  | requests.xlsx record '5387': Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5387': Country 'Tokelau' could not be matched to an ISO3 value. |
| 5380 | Request #5380 ? UNDESA/DISD is supporting the growth of the creative economy in South / East Asia and the Pacific, with a focus on social inclusion and in the context / of AI and digital transformation, with the aim to leave no one behind, / especially women, youth and persons with disabilities. / This initiative emanates from the decision to support UNGA resolution / A/RES/78/133 (2023) on promoting the creative economy for sustainable / development, which UNDESA/DISD has already followed up on with two / initial National and Regional interventions in Indonesia 2024 and in 2025. / Following the two technical workshops, and in the anticipation of an / upcoming Development Account project, UNDESA/DISD is planning a policy / advisory mission to Cambodia, Indonesia and Fiji. Whereas Indonesia is a / key partner which has led the way with the adoption of the UNGA / resolution, Cambodia and Fiji have expressed their interest to encourage / social inclusion through the growth of the creative economy. / The policy advisory mission will be a unique opportunity to exchange with / key strategic stakeholders from Government, the private sector, workersâ€™ / organizations, civil society and development partners of the three / countries and to explore potential for further collaboration, notably in the / aftermath of the second world summit for social development. / Critically, the mission will 1/ serve as an opportunity to identify local focal / points for the implementation of future activities; 2/ review the plan / activities on the creative economy with UNRCs, line ministries (Culture, / Creative Economy, Labour etc); and 3/ align workplans with UNESCO, ILO, / UNCTAD and other key development partners. It will serve as a be a unique / opportunity to explore potential for further collaboration, notably in followup / to the Second World Summit for Social Development. | Under consideration | Division for Inclusive Social Development | 13 Nov 2025 | 08 Dec 2025 | 17 Dec 2025 | Ambassador Tri Tharyat ¦ ppkki@kemlu.go.id | UNDESA/DISD is supporting the growth of the creative economy in South / East Asia and the Pacific, with a focus on social inclusion and in the context / of AI and digital transformation, with the aim to leave no one behind, / especially women, youth and persons with disabilities. / This initiative emanates from the decision to support UNGA resolution / A/RES/78/133 (2023) on promoting the creative economy for sustainable / development, which UNDESA/DISD has already followed up on with two / initial National and Regional interventions in Indonesia 2024 and in 2025. / Following the two technical workshops, and in the anticipation of an / upcoming Development Account project, UNDESA/DISD is planning a policy / advisory mission to Cambodia, Indonesia and Fiji. Whereas Indonesia is a / key partner which has led the way with the adoption of the UNGA / resolution, Cambodia and Fiji have expressed their interest to encourage / social inclusion through the growth of the creative economy. / The policy advisory mission will be a unique opportunity to exchange with / key strategic stakeholders from Government, the private sector, workersâ€™ / organizations, civil society and development partners of the three / countries and to explore potential for further collaboration, notably in the / aftermath of the second world summit for social development. / Critically, the mission will 1/ serve as an opportunity to identify local focal / points for the implementation of future activities; 2/ review the plan / activities on the creative economy with UNRCs, line ministries (Culture, / Creative Economy, Labour etc); and 3/ align workplans with UNESCO, ILO, / UNCTAD and other key development partners. It will serve as a be a unique / opportunity to explore potential for further collaboration, notably in followup / to the Second World Summit for Social Development. |  |  |
| 5352 | Request #5352 ? The Financing for Sustainable Development Office (FSDO) of the United Nations Department of Economic and Social Affairs (DESA) organized a Regional Workshop on Transfer Pricing in Asia-Pacific, held from 25 to 29 August 2025 in Incheon, Republic of Korea. / The workshop responded directly to countries' demand for practical tools and training on transfer pricing, aimed at strengthening domestic resource mobilization to support sustainable development. Transfer pricing â€” the pricing of cross-border transactions involving goods, services, or intangibles between related entitiesâ€” has gained increasing global attention due to its significant implications for equitable taxation and sustainable development. / Developing countries face considerable challenges in this area, including a high risk of profit shifting and limited access to specialized training and resources available to policy makers and tax administrations. The workshop brought together 23 participants (39% female) from 23 countries across the Asia-Pacific region, including least developed countries (LDCs), landlocked developing countries (LLDCs), and small island developing states (SIDS). Participants engaged in hands-on training on transfer pricing principles, using practical case studies to illustrate challenges frequently encountered by tax officials during audits of real-life transfer pricing cases. / Delivered in English, the workshop contributed to ongoing capacity-building efforts, enhancing the ability of tax officials to effectively address complex international tax issues. | Under consideration | Financing for Sustainable Development Office | 27 May 2025 | 25 Aug 2025 | 29 Aug 2025 | FSDO following request from Member States ¦ fsdcapdev@un.org | The Financing for Sustainable Development Office (FSDO) of the United Nations Department of Economic and Social Affairs (DESA) organized a Regional Workshop on Transfer Pricing in Asia-Pacific, held from 25 to 29 August 2025 in Incheon, Republic of Korea. / The workshop responded directly to countries' demand for practical tools and training on transfer pricing, aimed at strengthening domestic resource mobilization to support sustainable development. Transfer pricing â€” the pricing of cross-border transactions involving goods, services, or intangibles between related entitiesâ€” has gained increasing global attention due to its significant implications for equitable taxation and sustainable development. / Developing countries face considerable challenges in this area, including a high risk of profit shifting and limited access to specialized training and resources available to policy makers and tax administrations. The workshop brought together 23 participants (39% female) from 23 countries across the Asia-Pacific region, including least developed countries (LDCs), landlocked developing countries (LLDCs), and small island developing states (SIDS). Participants engaged in hands-on training on transfer pricing principles, using practical case studies to illustrate challenges frequently encountered by tax officials during audits of real-life transfer pricing cases. / Delivered in English, the workshop contributed to ongoing capacity-building efforts, enhancing the ability of tax officials to effectively address complex international tax issues. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 5319 | Request #5319 ? This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Completed | Statistics Division | 18 Aug 2025 | 15 Dec 2025 | 17 Dec 2025 | Sokunpanha You ¦ sokunpanha.you@un.org | This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 5242 | Request #5242 ? The request is for a capacity building workshop to prepare census managers in Pacific countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the Pacific Community (SPC), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 16 Jun 2025 | 13 Oct 2025 | 17 Oct 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Pacific countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the Pacific Community (SPC), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  | requests.xlsx record '5242': Countries Country text 'American Samoa' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'French Polynesia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Guam' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'New Caledonia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Pitcairn' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country 'American Samoa' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'French Polynesia' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Guam' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'New Caledonia' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Northern Mariana Islands' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Pitcairn' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country text 'American Samoa' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'French Polynesia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Guam' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'New Caledonia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Pitcairn' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country 'Tokelau' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Wallis and Futuna Islands' could not be matched to an ISO3 value. |
| 5145 | Request #5145 ? Climate change is one of the most pressing issues in the Asia-Pacific region. Countries requested the United Nations Statistical Institute for Asia and the Pacific (SIAP) to provide assistance on energy statistics, balances and accounts. UNSD co-organized a workshop with UNSIAP , with the support of the Office of the Director-General for Policy Planning on Statistical Policy, Ministry of Internal Affairs and Communications of the Government of Japan, focusing on the compilation of energy information in support of climate change policies The workshop took place on 13-16 May 2025 in Chiba, Japan. Nearly 30 people participated in the workshop, including 11 countries and the Asia Pacific Energy Research Centre. During the workshop, participants from national statistical offices and line ministries increased their capacity to compile and use energy statistics, balances and accounts according to international statistical methodology. | Completed | Statistics Division | 06 Feb 2025 | 13 May 2025 | 16 May 2025 | Jessica Ying Chan ¦ jessica.chan@un.org | Climate change is one of the most pressing issues in the Asia-Pacific region. Countries requested the United Nations Statistical Institute for Asia and the Pacific (SIAP) to provide assistance on energy statistics, balances and accounts. UNSD co-organized a workshop with UNSIAP , with the support of the Office of the Director-General for Policy Planning on Statistical Policy, Ministry of Internal Affairs and Communications of the Government of Japan, focusing on the compilation of energy information in support of climate change policies The workshop took place on 13-16 May 2025 in Chiba, Japan. Nearly 30 people participated in the workshop, including 11 countries and the Asia Pacific Energy Research Centre. During the workshop, participants from national statistical offices and line ministries increased their capacity to compile and use energy statistics, balances and accounts according to international statistical methodology. |  |  |
| 5032 | Request #5032 ? Training workshop for Pacific SIDS Students who are visiting UNHQ during 18 to 28 June 2024. | Completed | Division for Sustainable Development Goals | 28 Mar 2024 | 18 Jun 2024 | 28 Jun 2024 | Ambassador Filipo Tarakinikini ¦ mission@fijiprun.org | Training workshop for Pacific SIDS Students who are visiting UNHQ during 18 to 28 June 2024. |  |  |
| 4902 | Request #4902 ? Following a request from the Ministry of Trade, Cooperatives, Small and Medium Enterprises and Communication of the government of Fiji, DISD/DESA is organising an international training workshop in Fiji to support cooperatives in Pacific Island Countries and Territories to professionalise their operations and support their countries in accelerating the achievement of the sustainable development goals. / This workshop will enhance the capacities of cooperatives to support their governments in achieving the sustainable development goals. | Completed | Division for Inclusive Social Development | 21 Dec 2023 | 07 May 2024 | 09 May 2024 | Manoa Kamikamica ¦ ajohn@moc.gov.fj | Following a request from the Ministry of Trade, Cooperatives, Small and Medium Enterprises and Communication of the government of Fiji, DISD/DESA is organising an international training workshop in Fiji to support cooperatives in Pacific Island Countries and Territories to professionalise their operations and support their countries in accelerating the achievement of the sustainable development goals. / This workshop will enhance the capacities of cooperatives to support their governments in achieving the sustainable development goals. |  |  |
| 4871 | Request #4871 ? Support for INFF implementation through Financing for SIDS (FINS) | Ongoing | Division for Sustainable Development Goals, Financing for Sustainable Development Office | 26 Oct 2023 | 01 Nov 2022 | 01 Aug 2026 | Shiri Gounder ¦ kamal.gounder@finance.gov.fj | Support for INFF implementation through Financing for SIDS (FINS) |  |  |
| 4847 | Request #4847 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for one resource expert and for two UNSD staff to co-organize and co-lead a Regional Course on Statistical Business Registers that will be hosted by the Statistical Institute for Asia and the Pacific in Chiba, Japan, on 11-14 March 2024. / This regional course aims to help participants acquire knowledge and skills to deepens their understanding on the principles and methodology on statistical business registers. The course will review international recommendations and standards on Statistical Business Registers and provide guidance on the implementation of the Maturity Model for Statistical Business Registers. / The proposal concerns a total budget of US$15,783.00 covering the participation of a resource expert from Statistics Netherlands. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the course. | Completed | Statistics Division | 22 Jan 2024 |  | 14 Mar 2024 | Pedro Farinas ¦ farinas@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for one resource expert and for two UNSD staff to co-organize and co-lead a Regional Course on Statistical Business Registers that will be hosted by the Statistical Institute for Asia and the Pacific in Chiba, Japan, on 11-14 March 2024. / This regional course aims to help participants acquire knowledge and skills to deepens their understanding on the principles and methodology on statistical business registers. The course will review international recommendations and standards on Statistical Business Registers and provide guidance on the implementation of the Maturity Model for Statistical Business Registers. / The proposal concerns a total budget of US$15,783.00 covering the participation of a resource expert from Statistics Netherlands. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the course. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 4674 | Request #4674 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Completed | Statistics Division | 02 Aug 2023 | 02 Oct 2023 | 06 Oct 2023 | Ilaria di Matteo ¦ dimatteo@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 4731 | Request #4731 ? FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. | Completed | Financing for Sustainable Development Office | 31 Jan 2022 | 01 Jun 2022 | 12 Jan 2022 | Daniel Platz ¦ platz@un.org | FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. |  | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. / requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 4234 | Request #4234 ? Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Completed | Statistics Division | 05 Jul 2022 | 08 Jan 2022 | 30 Dec 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 2694 | Request #2694 ? Capacity building for Blue Growth | Outdated | Division for Sustainable Development Goals | 01 Jan 2019 |  |  | na ¦ na@na.na | Capacity building for Blue Growth |  |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 3860 | Request #3860 ? This initiative aims to strengthen UNRC/UNCT capacities for / the analyses of transboundary economic risks, economic / transformation, debt management and fiscal issues reflected / in CCAs in selected countries. It will leverage DESAâ€™s / analytical tools and products - including economic forecasting / and policy messages of the World Economic Situation / Prospects (WESP) and the World Social Report (WSR) - and / the regional outlooks and analyses produced by the UN / Regional Commissions (RECs) to strengthen macroeconomic / analyses relevant for CCAs. The analyses of the socioeconomic / impact of COVID-19 conducted by both DESA and / RECs will also be a major input to this effort. / The overall goal is to support the UNRC/UNCT to effectively / use and translate global and regional economic outlooks and / risks to develop country specific policy guidance. DESA will / work in partnership with interested RECs to deploy respective / knowledge, expertise and analytical capacities first to support / the RC/UNCT in the selected countries and then to scale up / support to other countries across regions. | Completed | Economic Analysis and Policy Division | 07 May 2020 |  |  | Monica Noagara ¦ noagara@un.org | This initiative aims to strengthen UNRC/UNCT capacities for / the analyses of transboundary economic risks, economic / transformation, debt management and fiscal issues reflected / in CCAs in selected countries. It will leverage DESAâ€™s / analytical tools and products - including economic forecasting / and policy messages of the World Economic Situation / Prospects (WESP) and the World Social Report (WSR) - and / the regional outlooks and analyses produced by the UN / Regional Commissions (RECs) to strengthen macroeconomic / analyses relevant for CCAs. The analyses of the socioeconomic / impact of COVID-19 conducted by both DESA and / RECs will also be a major input to this effort. / The overall goal is to support the UNRC/UNCT to effectively / use and translate global and regional economic outlooks and / risks to develop country specific policy guidance. DESA will / work in partnership with interested RECs to deploy respective / knowledge, expertise and analytical capacities first to support / the RC/UNCT in the selected countries and then to scale up / support to other countries across regions. |  |  |
| 3632 | Request #3632 ? In response to the invitation of DESA to participate in the Retreat of the Pacific UNCT (which includes the Samoa and Fiji MCOs) for the preparation of the CCA/CF, DESA offered to support the development of the Pacific CCA macroeconomic pillar. At the outset of the COVID-19 crisis, both RCs requested DESA support to contribute to the preparation of their respective socio-economic impact assessment of COVID-19 | Completed | Economic Analysis and Policy Division | 24 Apr 2020 | 27 Apr 2020 | 30 Nov 2020 | Sanaka Kumara Samarasinha ¦ sanaka.samarasinha@un.org | In response to the invitation of DESA to participate in the Retreat of the Pacific UNCT (which includes the Samoa and Fiji MCOs) for the preparation of the CCA/CF, DESA offered to support the development of the Pacific CCA macroeconomic pillar. At the outset of the COVID-19 crisis, both RCs requested DESA support to contribute to the preparation of their respective socio-economic impact assessment of COVID-19 |  |  |
| 3566 | Request #3566 ? To establish a SIDS Biodiveristy Coalition and develop a 10-year capacity development roadmap on Biodiversity for SIDS, in the margins of CDB COP 15 | Completed | Division for Sustainable Development Goals | 22 Mar 2021 | 01 Apr 2021 | 31 Dec 2022 | Satyendra Prasad ¦ na@na.na | To establish a SIDS Biodiveristy Coalition and develop a 10-year capacity development roadmap on Biodiversity for SIDS, in the margins of CDB COP 15 |  |  |
| 3432 | Request #3432 ? Joint DESA-ESCAP initiative in support of the Madrid International Plan of Action on Ageing (MIPAA) and the regional outcome document of the Third Review and Appraisal of the Madrid International Plan of Action on Ageing. Held training workshop on forecasting the national economic and fiscal impacts of population ageing. | Completed | Population Division | 07 Jan 2019 | 24 Jun 2019 | 27 Jun 2019 | Ms. Sabine Henning ¦ hennings@un.org | Joint DESA-ESCAP initiative in support of the Madrid International Plan of Action on Ageing (MIPAA) and the regional outcome document of the Third Review and Appraisal of the Madrid International Plan of Action on Ageing. Held training workshop on forecasting the national economic and fiscal impacts of population ageing. |  |  |
| 3381 | Request #3381 ? Contribution of Cooperatives to Sustainable Development in the South Pacific | Completed | Division for Inclusive Social Development | 01 Feb 2020 | 25 Feb 2020 | 27 Feb 2020 | Registrar of Cooperatives Fiji ¦ na@na | Contribution of Cooperatives to Sustainable Development in the South Pacific |  |  |
| 2738 | Request #2738 ? Support for capacity building and development of a project proposal on sustainable forest management | Completed | United Nations Forum on Forest | 28 Jul 2016 |  |  | N/A ¦ Na@na | Support for capacity building and development of a project proposal on sustainable forest management |  |  |
| 2709 | Request #2709 ? Institutional arrangements for policy integration, coordination, and stakeholder engagement in Sustainable Development Goals (SDGs) implementation and reviews in Asia-Pacificâ€ / At the invitation of the Government of Fiji, a Scoping Mission was undertaken by UN-DESAâ€™s Officials, Mr. Jonas Rabinovitch, Senior Advisor, Innovation and Public Service Delivery, Division for Public Institutions and Digital Government (DPIDG) and Mr. Sainivalati S. Navoti (Sai), Chief, SIDS Unit, Division for Sustainable Development (DSDG). The Mission took place from 7 to 15 March 2020. / The objective of the Scoping Mission was for the DESA Officials to meet with representatives of key government institutions (Ministries and Departments), to discuss and identify priorities, gaps, challenges, good practices, mo-dus operandi and other aspects on how institutional arrangements in Fiji were addressing the coordination and implementation of the SDGs, the 2030 Agenda, SAMOA Pathway and other internationally agreed agendas, with the view to recommending a mechanism or a roadmap for improvement and further enhanced action. | Completed | Division for Public Institutions and Digital Government | 11 Feb 2020 | 07 Mar 2020 | 15 Mar 2020 | Makerata Konrote ¦ economuinformation@economy.gov.fj | Institutional arrangements for policy integration, coordination, and stakeholder engagement in Sustainable Development Goals (SDGs) implementation and reviews in Asia-Pacificâ€ / At the invitation of the Government of Fiji, a Scoping Mission was undertaken by UN-DESAâ€™s Officials, Mr. Jonas Rabinovitch, Senior Advisor, Innovation and Public Service Delivery, Division for Public Institutions and Digital Government (DPIDG) and Mr. Sainivalati S. Navoti (Sai), Chief, SIDS Unit, Division for Sustainable Development (DSDG). The Mission took place from 7 to 15 March 2020. / The objective of the Scoping Mission was for the DESA Officials to meet with representatives of key government institutions (Ministries and Departments), to discuss and identify priorities, gaps, challenges, good practices, mo-dus operandi and other aspects on how institutional arrangements in Fiji were addressing the coordination and implementation of the SDGs, the 2030 Agenda, SAMOA Pathway and other internationally agreed agendas, with the view to recommending a mechanism or a roadmap for improvement and further enhanced action. |  |  |
| 2629 | Request #2629 ? DPIDG/ UNPOG was requested by the Ministry of Rural and Maritime Development of the Government of Fiji to provide capacity development support on governance issues related to Fijiâ€™s Voluntary National Review process, to present during the 2019 HLPF as an outcome of the August 2018 Island States Forum in Sri Lanka. | Completed | Division for Public Institutions and Digital Government | 02 Aug 2018 | 23 Jan 2019 | 24 Jan 2019 | na ¦ na@gmail.com | DPIDG/ UNPOG was requested by the Ministry of Rural and Maritime Development of the Government of Fiji to provide capacity development support on governance issues related to Fijiâ€™s Voluntary National Review process, to present during the 2019 HLPF as an outcome of the August 2018 Island States Forum in Sri Lanka. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.17 | Pacific SIDS Regional Energy Statistics Training Workshop / | SD | 30 Jun 2026 | 30 Jun 2026 | $59,546 | Democratic Republic of Timor-Leste, Fiji, Kiribati, Marshall Islands, Micronesia (Federated States of), Nauru, Palau, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashDESA' has non-numeric value 'Total: $187,996 UNSD: $59,546 (RPTC) and $16,685 (XB); DSDG: $111,766'. / proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashOther' has non-numeric value '$30,000 (UN SIAP)'. / Proposal past due |
| SB-001377.99.11 | Integrated OG–CLEWs model for Fiji | EAPD | 30 Sept 2026 | 31 Dec 2026 | $143,000 | Fiji |  |  |
| SB-001379.99.29 | Strengthening Pacific Cooperatives through Education, Training and Regional Cooperation | DISD | 30 Sept 2026 | 30 Sept 2026 | $73,144 | Fiji |  | proposals.xlsx record 'SB-001379.99.29¦row:57': 'f_cashDESA' has non-numeric value '$ 73,144 for staff travel, funding of participants’ travel and venue services'. / Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001374.99.35 | Strengthening the capacity of Supreme Audit Institutions (SAIs) from Small Island Developing States (SIDS) to audit the implementation of the Sustainable Development Goals (SDGs) | DPIDG | 03 Aug 2026 | 05 Aug 2026 | $0 | 7 | 3 | Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. / activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002059860 - Fiji | 0002059860 | Past | Fiji |  | STATISTICS DIVISION | INITIATE THE DATAS INITIATIVE IN FIJI AND CONDUCT EVENTS |  | 01 May 2025 | 11 May 2025 |
| 0002059884 - Fiji | 0002059884 | Past | Fiji |  | STATISTICS DIVISION | SERVE AS RESOURCE PERSON FOR DATAS PROJECT |  | 01 May 2025 | 11 May 2025 |
| 0002282449 - Fiji | 0002282449 | Past | Fiji |  | DIVISION FOR SUSTAINABLE DEVELOPMENT GOALS | SIDS REG'L WSHOP ON DEEPSEA MINERALS,1921MAY,SUVA |  | 13 May 2026 | 25 May 2026 |
| S9AC0003_DSDG - Fiji | S9AC0003_DSDG | Forecast | Fiji | Suva | DSDG | ABAS M&E Capacity Building Workshop - Part of the Pacific Integrated Regional Planning Forum | International Workshop | 02 Nov 2026 | 06 Nov 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries | 2021 | DSDG; CDPMO | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | - Build on the momentum and lessons from this Project in the design of a follow-on project. / - Ensure engagement at the senior policy level at project commencement and maintain or renew engagement as required to avoid loss of momentum. / - Include assistance for network mapping, activation, and strengthening in each country, with a project contacts database to support ongoing engagement. / - Invest in establishing and expanding the knowledge management aspects of the Project, including improved logical frameworks, performance indicators, and strengthened monitoring systems. / - Support critical pilot sub-projects with potential for both policy and inclusive MSME sector impact, ensuring sufficient resources and targeted technical support for implementation and scaling up. | - The Project entry point at a senior policy level activates national coordination and prioritization. / - A targeted, meso-level approach towards programming contributes towards a stronger MSME enabling environment. / - Active engagement and networking opportunities contribute to immediate and longer-term results, but contacts must be retained to maintain momentum. / - A flexible approach helps to optimize results, allowing activities to be adjusted to local context and requirements. / - National consultants and credible focal points in key ministries are important drivers of success. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2016-04_Eval_DSDG_17Mar22.docx | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'The Gambia' -> 'Gambia'. | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Evaluation of the United Nations Centre for Regional Development (UNCRD) | 2023 | DSDG; CDPMO | Afghanistan, Australia, Bangladesh, Bhutan, Brunei Darussalam, Cambodia, China, Democratic Republic of Timor-Leste, Democratic Socialist Republic of Sri Lanka, Fiji, India, Indonesia, Iran (Islamic Republic of), Japan, Kiribati, Korea, Lao People's Democratic Republic, Malaysia, Maldives, Marshall Islands, Micronesia (Federated States of), Mongolia, Myanmar, Nepal, New Zealand, Palau, Papua New Guinea, Philippines, Russian Federation, Samoa, Singapore, Solomon Islands, Thailand, Tonga, Tuvalu, Viet Nam | - Develop a strategic vision for UNCRD that is closely aligned with UN DESA’s mandate and the priorities of the donor and that articulates its added value, comparative advantages, and strengths. / - Secure additional core funding to ensure UNCRD’s sustainability. / - Take actionable concrete steps to support more holistic office management. / - Strengthen collaboration between UN DESA and UNCRD. / - Develop a technical assistance programme to support member state capacity development throughout the year. | - Visibility and effective communication with donors along with intentional alignment with donor priorities are essential components to ensuring programme sustainability. / - When more than one donor funds programming, staff cohesion and teamwork can be promoted by ensuring that each donor funds a portion of each staff position. / - Generating partner buy-in and leveraging that buy-in through in-kind and financial contributions can significantly increase an office’s capacity to achieve greater results. / - UN DESA’s project offices require investment from UN DESA to support their strategic work and not only their administrative work. / - Focusing on specific thematic areas can provide excellent added value to overall efforts to achieve the SDGs. However, programming must be centered within the wider SDG context and be aligned with DESA and donor priorities in order to demonstrate its relevance. / - Supporting intra-governmental collaboration across government ministries is a highly valued contribution towards achieving the complexity of the SDGs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Active Projects/6 DSDG (DSD)/UNCRD/All UNCRD projects/Audit & Evaluation/Evaluation 2023/Final Evaluation Report June 26 2023/UNCRD Evaluation Final Report June 26 2023.docx | Country standardized: 'Federated States of Micronesia' -> 'Micronesia (Federated States of)'. / Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | evaluations.xlsx rows 282 (archived) and 127 (retained): Review conflicts: Countries differs: archived row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Korea; Lao People’s Democratic Republic; Malaysia; Maldives; Marshall Islands; Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'; retained row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Republic of Korea; Lao People's Democratic Republic; Lao PDR; Malaysia; Maldives; Marshall Islands; Federated States of Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'. Country lists were not merged. |
| Developing a Public‐Private Partnerships (PPP) and Infrastructure Financing Network in Asia and the Pacific | 2022 |  | Afghanistan, Bangladesh, Cambodia, Democratic Republic of Timor-Leste, Fiji, India, Indonesia, Kazakhstan, Kyrgyzstan, Lao People's Democratic Republic, Malaysia, Mongolia, Nepal, Pakistan, Papua New Guinea, Philippines, Russian Federation, Tajikistan, Thailand, Türkiye, Viet Nam | - The project team should further clarify the end-purpose of the Network to its key internal and external stakeholders, establish a clear theory of change and results matrix, and set measurable targets to assess its performance. / - Increase attention to collecting data on key outcomes and impacts to document and learn about changes occurring at different levels, and develop a clear M&E plan involving national partners. / - Further incorporate human rights, gender equality, and related issues in key priority areas by systematically collecting disaggregated data and arranging training on mainstreaming gender and human rights issues in project design and implementation. / - Seek additional resources for building on the results achieved so far and diversify the donor base for sustainability and expansion. / - Enhance collaboration with other ESCAP divisions and sections to offer deeper expertise and build on collaboration with related units and networks such as the ESCAP Sustainable Business Network (ESBN). | - Involving private sector entities and carefully selecting local and international partnerships contributed to the successful establishment and operationalization of the network and should be replicated in other projects where relevant. / - Remote collaboration, while necessary during the pandemic, limited deeper engagement critical for higher-order outcomes such as building trust and making investments; future phases should emphasize site visits and in-person networking to facilitate more meaningful connections. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2018/PDF-2018-06 ESCAP/Reports/Final Report & Evaluation/PPP Project Evaluation Report _formatted 17Nov.pdf | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | evaluations.xlsx row 214: Divisions not provided. |
| Strengthening national capacities to develop Action Plans to Implement the United Nations Forest Instrument (UNFI) | 2018 | UNFFS | Ecuador, Fiji, Gabon, India, Jamaica, Mongolia | - Developing countries must take advantage of the opportunity offered through the NAP development process to integrate the NAP for UNFI into existing forest programmes and sustainable development strategies. / - Promote public awareness and education on the UNFI, UNSPF at the country level to ensure the operationalisation of SFM policies and measures. / - Draw on lessons learned from the pilot countries on methodology and its broad stakeholder engagement in internalising the benefits of strong multi-stakeholder dialogues in the forestry and other related sectors. / - The Forum must commit time for discussion on progress on the NAP development at the UNFF13 in May 2018 and include reporting on progress of NAP development and implementation as a part of the requirements for national reports at its sessions. / - Develop a communications plan for creating awareness on the UNFI at the global, regional and national levels and undertake activities that would create political visibility for its work and in particular the UNFI, Global Objectives on Forests, UNSPF and their contribution to the SDGs. / - Promote the collaboration of CPF member organisations at the country level for the development and implementation of NAPs. / - UNFFS should prepare policy briefs out of the experiences and lessons learned for dissemination to member countries and the general public in creating awareness on the UNFI and the process for developing NAPs. / - UNFFS to finalise the draft guidelines developed from the project to serve as guidance to member countries desirous of developing NAPs and ensure continued support for the uptake of the guidelines in the member countries. / - UNFFS should consider providing support to member states that have expressed interest in developing NAPs, including the development of financial proposals to attract funding for NAP development and implementation, with strong linkage to the Global Forest Financing Facilitation Network. / - Explore the possibility of building partnerships with other projects within the UN system to ensure broader access to funding. / - Adopt guidelines developed through the project and pilot the implementation phase in select countries, maintaining regional/group balance. | - The project implementation and management was good because of the level of collaboration between the UNFFS and the leadership from the national Forestry Departments/Agencies, and a well-designed logical framework approach is critical in supporting evaluation of the project. / - A broad multi-stakeholder deliberative process is critical for good outcomes in project implementation and promoted ownership of the NAP process in the pilot countries, enabling engagement of sectors outside the forest sector. / - Mobilizing leadership of high level personnel in the countries for the NAP development process results in stronger political support for the forest sector, while changes in focal points or leadership can negatively impact the project. / - A communications strategy is required for creating awareness on the UNFI at the country level, including in sectors outside forestry, and there is a need to widely disseminate the Guidelines on NAP development. / - The depth and breadth of knowledge of the international consultant that facilitated the workshops enriched the process and allowed for effective engagement by participants in drafting the NAP Guidelines. / - Countries appreciated the opportunity to share experiences and lessons learned, and future projects should include appropriate tools for sharing information. / - Possibilities for creating effective partnerships should always be considered during project planning/design to enhance participation of CPF memberships and provide opportunities for wider collaboration within the UN System. / - Integrating NAPs into existing processes for developing National Forestry Policies was a positive approach to internalizing the prioritization of the UNFI Policies and Measures and creating a link between the UNFI, UNSPF and national policies and strategies. / - NAP development process enabled countries to reflect on potential sources of financial resources for implementation, including domestic sources, and to package their NAPs to attract different fund donors. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 266 - UNFF Final Evaluation Report.pdf |  |  |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. |
| 2 | activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |
| 3 | evaluations.xlsx row 214: Divisions not provided. |
| 4 | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 282 (archived) and 127 (retained): Review conflicts: Countries differs: archived row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Korea; Lao People’s Democratic Republic; Malaysia; Maldives; Marshall Islands; Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'; retained row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Republic of Korea; Lao People's Democratic Republic; Lao PDR; Malaysia; Maldives; Marshall Islands; Federated States of Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'. Country lists were not merged. |
| 7 | evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 8 | evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 10 | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashDESA' has non-numeric value 'Total: $187,996 UNSD: $59,546 (RPTC) and $16,685 (XB); DSDG: $111,766'. |
| 11 | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashOther' has non-numeric value '$30,000 (UN SIAP)'. |
| 12 | proposals.xlsx record 'SB-001379.99.29¦row:57': 'f_cashDESA' has non-numeric value '$ 73,144 for staff travel, funding of participants’ travel and venue services'. |
| 13 | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. |
| 14 | requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 15 | requests.xlsx record '5242': Countries Country text 'American Samoa' could not be matched; no country assignment was inferred. |
| 16 | requests.xlsx record '5242': Countries Country text 'French Polynesia' could not be matched; no country assignment was inferred. |
| 17 | requests.xlsx record '5242': Countries Country text 'Guam' could not be matched; no country assignment was inferred. |
| 18 | requests.xlsx record '5242': Countries Country text 'New Caledonia' could not be matched; no country assignment was inferred. |
| 19 | requests.xlsx record '5242': Countries Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. |
| 20 | requests.xlsx record '5242': Countries Country text 'Pitcairn' could not be matched; no country assignment was inferred. |
| 21 | requests.xlsx record '5242': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 22 | requests.xlsx record '5242': Countries Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. |
| 23 | requests.xlsx record '5242': Country 'American Samoa' could not be matched to an ISO3 value. |
| 24 | requests.xlsx record '5242': Country 'French Polynesia' could not be matched to an ISO3 value. |
| 25 | requests.xlsx record '5242': Country 'Guam' could not be matched to an ISO3 value. |
| 26 | requests.xlsx record '5242': Country 'New Caledonia' could not be matched to an ISO3 value. |
| 27 | requests.xlsx record '5242': Country 'Northern Mariana Islands' could not be matched to an ISO3 value. |
| 28 | requests.xlsx record '5242': Country 'Pitcairn' could not be matched to an ISO3 value. |
| 29 | requests.xlsx record '5242': Country 'Tokelau' could not be matched to an ISO3 value. |
| 30 | requests.xlsx record '5242': Country 'Wallis and Futuna Islands' could not be matched to an ISO3 value. |
| 31 | requests.xlsx record '5242': Country text 'American Samoa' could not be matched; no country assignment was inferred. |
| 32 | requests.xlsx record '5242': Country text 'French Polynesia' could not be matched; no country assignment was inferred. |
| 33 | requests.xlsx record '5242': Country text 'Guam' could not be matched; no country assignment was inferred. |
| 34 | requests.xlsx record '5242': Country text 'New Caledonia' could not be matched; no country assignment was inferred. |
| 35 | requests.xlsx record '5242': Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. |
| 36 | requests.xlsx record '5242': Country text 'Pitcairn' could not be matched; no country assignment was inferred. |
| 37 | requests.xlsx record '5242': Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 38 | requests.xlsx record '5242': Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. |
| 39 | requests.xlsx record '5387': Country 'Tokelau' could not be matched to an ISO3 value. |
| 40 | requests.xlsx record '5387': Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 57 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 58 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 59 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 60 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 61 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 62 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 63 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 64 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 65 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 66 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 67 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 68 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 69 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 70 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 71 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 72 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 73 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 74 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 75 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 76 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 77 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 78 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 79 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 80 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 81 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 82 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 83 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 84 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 85 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 86 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 87 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |