Ghana

Africa

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Ghana is presented in this country card as part of Africa, with Ghana also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Ghana highlights 8 projects for Ghana, including 2 active or planned projects for Ghana and 6 completed or closed projects for Ghana.

For Ghana, the report includes 23 requests for Ghana, 7 RPTC proposals for Ghana, 2 RPTC activities for Ghana, and 0 travel records for Ghana. Financially, Ghana shows USD 15,916,674 in project budget, $466,062 in proposal planned budget, and $201,588 in consumed RPTC activity budget for Ghana.

The main organizational coverage for Ghana points to DISD, Division for Inclusive Social Development, Division for Sustainable Development Goals, FSDO. Activity records for Ghana list 1,381 participants, including 709 women participants, the current quality review for Ghana includes 76 data quality notes. Current highlights for Ghana include a request focus for Ghana: Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data.

      

      

      
This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing.

      

      

      
The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint.; an RPTC proposal focus for Ghana: Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.||Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.; an activity focus for Ghana: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 8 |
| Project budget | USD 15,916,674 |
| Requests | 23 |
| RPTC proposals | 7 |
| Proposal planned budget | $466,062 |
| RPTC activities | 2 |
| Consumed RPTC budget | $201,588 |
| Activity participants | 1,381 |
| Women participants | 709 |
| Travel records | 0 |
| Evaluations | 9 |
| Data quality notes | 76 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Developing institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals |  | country | Division for Public Institutions and Digital Government | Closed | 01 Oct 2021 | 31 Oct 2024 | USD 824,649 | Bangladesh, Bhutan, Cambodia, Democratic Socialist Republic of Sri Lanka, Egypt, Ethiopia, Fiji, Gambia, Ghana, Lao People's Democratic Republic, Morocco, Namibia, Rwanda, Samoa, Sierra Leone, United Republic of Tanzania, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Mobilizing Science, Technology and Innovation in Developing Countries for the SDGs | 2016-03 | country | Division for Sustainable Development Goals | Closed | 01 Apr 2017 | 30 Jun 2021 | USD 1,000,000 | Ethiopia, Ghana, India, Kenya, Serbia |  |
| Monitoring progress towards sustainable forest management | 1617F | country | United Nations Forum on Forest | Closed | 16 Jun 2020 | 19 Dec 2020 | USD 709,000 | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines |  |
| Monitoring the Sustainable Development Goals |  | country | Statistics Division | Closed | 01 Aug 2016 | 31 Jul 2022 | USD 9,334,229 | Bangladesh, Burundi, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Kyrgyzstan, Lao People's Democratic Republic, Liberia, Mozambique, Myanmar, Nepal, Rwanda, Tajikistan, Uganda, United Republic of Tanzania, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Promoting agricultural cooperatives in sub-Saharan Africa to enhance resilience and adaptation of small-holder farmers to climate change | 2528C | country | Division for Inclusive Social Development | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 647,400 | Botswana, Cameroon, Ghana, United Republic of Tanzania | Duplicate review: selected this entry and excluded projects.csv row 71. |
| Strengthening capacities of developing countries in sub-Saharan Africa to effectively produce and use population estimates and projections in policy-making for sustainable development | ROA 262 | country | Population Division | Closed | 14 Jun 2020 | 17 Dec 2020 | USD 588,000 | Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Djibouti, Ethiopia, Gabon, Ghana, Kenya, Mali, Namibia, Niger, Nigeria, Senegal, Togo, Uganda, Zambia |  |
| Strengthening local and national government capacities for SDG localization in Africa |  | country | Division for Sustainable Development Goals | Active | 01 Oct 2024 | 31 Mar 2027 | USD 2,000,000 | Côte d’Ivoire, Egypt, Ethiopia, Ghana, Mozambique, Sierra Leone, South Africa | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |
| Time-use data for better policies in Africa, Western Asia and Latin America | 2023A | country | Statistics Division | Closed | 01 Jan 2020 | 30 Jun 2023 | USD 813,396 | Burkina Faso, Chile, Dominican Republic, Egypt, El Salvador, Ghana, Iraq, Lesotho, Libya, Mexico, Morocco, Sierra Leone, South Africa, State of Palestine |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |  |
| 5478 | Request #5478 ? Requested a strengthened partnership to co-design and upscale activities to accelerate the attainment of the SDGs in Ghana under the Localisation of the 2030 Agenda programme â€œStrengthening Local and National Government Capacities for SDG Localisation in Africaâ€ | Under consideration | Division for Sustainable Development Goals | 03 Mar 2026 | 03 Mar 2026 | 31 Dec 2026 | Audrey Smock Amoah ¦ philip.acheampong@ndpc.gov.gh | Requested a strengthened partnership to co-design and upscale activities to accelerate the attainment of the SDGs in Ghana under the Localisation of the 2030 Agenda programme â€œStrengthening Local and National Government Capacities for SDG Localisation in Africaâ€ |  |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5361 | Request #5361 ? The Partnership in Statistics for Development in the 21st Century (PARIS21) aims to improve the production, quality, availability and use of statistics for informed decision-making and sustainable development. Established in 1999 by the United Nations, the European Commission, the Organisation for Economic Co-operation and Development (OECD), the International Monetary Fund and the World Bank, PARIS21 works with governments, international organizations, civil society and other stakeholders to strengthen national statistical systems, particularly in low- and middle-income countries. / The 2025 PARIS21 Annual Board and Partnership Meetings, to be held in Paris on 5â€“6 November 2025, - preparatory meetings are taking place on 4 November 2025 - will provide a platform to discuss coordinated and sustainable support for statistical capacity development, with a focus on Least Developed Countries (LDCs), Landlocked Developing Countries (LLDCs) and Small Island Developing States (SIDS). / Participation by the United Nations Statistics Division (UNSD) will ensure the Department of Economic and Social Affairsâ€™ (DESA) continued engagement in aligning international cooperation, strengthening partnerships and advancing coherence across global capacity building initiatives. / PARIS21 partner countries, who will participate in the meetings, are: / 1. Rwanda / 2. Bhutan / 3. Colombia / 4. Ghana / 5. Honduras / 6. Jamaica / 7. Kenya / 8. Kyrgyz Republic / 9. Lao PDR / 10. Malawi / 11. Mongolia / 12. Niger / 13. Palestine / 14. Paraguay / 15. Philippines / 16. Tunisia | Completed | Statistics Division | 13 Oct 2025 | 05 Nov 2025 | 06 Nov 2025 | Abdulla Gozalov ¦ gozalov@un.org | The Partnership in Statistics for Development in the 21st Century (PARIS21) aims to improve the production, quality, availability and use of statistics for informed decision-making and sustainable development. Established in 1999 by the United Nations, the European Commission, the Organisation for Economic Co-operation and Development (OECD), the International Monetary Fund and the World Bank, PARIS21 works with governments, international organizations, civil society and other stakeholders to strengthen national statistical systems, particularly in low- and middle-income countries. / The 2025 PARIS21 Annual Board and Partnership Meetings, to be held in Paris on 5â€“6 November 2025, - preparatory meetings are taking place on 4 November 2025 - will provide a platform to discuss coordinated and sustainable support for statistical capacity development, with a focus on Least Developed Countries (LDCs), Landlocked Developing Countries (LLDCs) and Small Island Developing States (SIDS). / Participation by the United Nations Statistics Division (UNSD) will ensure the Department of Economic and Social Affairsâ€™ (DESA) continued engagement in aligning international cooperation, strengthening partnerships and advancing coherence across global capacity building initiatives. / PARIS21 partner countries, who will participate in the meetings, are: / 1. Rwanda / 2. Bhutan / 3. Colombia / 4. Ghana / 5. Honduras / 6. Jamaica / 7. Kenya / 8. Kyrgyz Republic / 9. Lao PDR / 10. Malawi / 11. Mongolia / 12. Niger / 13. Palestine / 14. Paraguay / 15. Philippines / 16. Tunisia |  |  |
| 5257 | Request #5257 ? The request from the countries is to supporting countries to (1) facilitate access to existing DHS data, (2) support the completion of interrupted DHS activities, (3) assess the impact from the termination of the DHS program, and (4) propose sustainable long-term solutions to demographic and health data production. | Ongoing | Statistics Division | 07 Mar 2025 | 07 Mar 2025 | 26 Mar 2027 | Haoyi Chen ¦ chen9@un.org | The request from the countries is to supporting countries to (1) facilitate access to existing DHS data, (2) support the completion of interrupted DHS activities, (3) assess the impact from the termination of the DHS program, and (4) propose sustainable long-term solutions to demographic and health data production. |  |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 5207 | Request #5207 ? The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Completed | Statistics Division | 09 May 2025 | 30 Sept 2025 | 03 Oct 2025 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Country standardized: 'Republic of Korea' -> 'Korea'. |  |
| 5129 | Request #5129 ? The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Completed | Population Division, Statistics Division | 28 Mar 2025 | 16 Jun 2025 | 20 Jun 2025 | Maria Isabel Cobos ¦ cobos@un.org | The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5139 | Request #5139 ? The Ghana Revenue Authority (GRA) requested FSDO's technical assistance to strengthen the capacity of its newly established International Tax Office (ITO). Given the complexity of international tax matters, targeted training is needed to equip staff with the skills to manage tax treaty negotiations, administration, dispute resolution, exchange of information, and the taxation of the digitalised economy, including crypto and digital assets. | Ongoing | Financing for Sustainable Development Office | 10 Sept 2024 | 07 Jan 2025 | 09 Oct 2024 | Nana Mensah Otoo ¦ nana.otoo@gra.gov.gh | The Ghana Revenue Authority (GRA) requested FSDO's technical assistance to strengthen the capacity of its newly established International Tax Office (ITO). Given the complexity of international tax matters, targeted training is needed to equip staff with the skills to manage tax treaty negotiations, administration, dispute resolution, exchange of information, and the taxation of the digitalised economy, including crypto and digital assets. |  | requests.xlsx record '5139': End date 2024-10-09 is before start date 2025-01-07. |
| 5083 | Request #5083 ? Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. | Completed | Statistics Division | 20 Sept 2024 | 21 Sept 2024 | 31 Jan 2025 | Camilo Andres Mendez Coronado ¦ camendezc@dane.gov.co | Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. |  |  |
| 4942 | Request #4942 ? Policy support to address the challenges posed by the end-of-life secondhand textile industry in Ghana - Waste Management | Completed | Division for Sustainable Development Goals | 19 Mar 2024 | 25 Aug 2024 | 29 Aug 2024 | Noah Tumfo ¦ info@mswr.gov.gh | Policy support to address the challenges posed by the end-of-life secondhand textile industry in Ghana - Waste Management |  |  |
| 4796 | Request #4796 ? Ghana is requesting, through AU/APRM, DESA's support in carrying out VLRs | Completed | Division for Sustainable Development Goals | 14 Apr 2023 | 01 Sept 2023 | 31 Mar 2024 | Eddy Maloka ¦ na@na.na | Ghana is requesting, through AU/APRM, DESA's support in carrying out VLRs |  |  |
| 3977 | Request #3977 ? The provisional weblink to the Handbook is available here: https://unstats.un.org/capacity-development/handbook/index.cshtml | Completed | Statistics Division | 23 Sept 2021 | 10 Jan 2021 | 31 Dec 2021 | Jurgen Gafke ¦ gafke@un.org | The provisional weblink to the Handbook is available here: https://unstats.un.org/capacity-development/handbook/index.cshtml |  |  |
| 4679 | Request #4679 ? Ghana is requesting the support to strengthen national capacities of the National STI System, including the development and implementation of its national STI4SDG Roadmap | Completed | Division for Sustainable Development Goals | 17 Apr 2023 | 01 May 2023 | 31 Oct 2023 | Dr Wilhelmina Quaye ¦ na@na.na | Ghana is requesting the support to strengthen national capacities of the National STI System, including the development and implementation of its national STI4SDG Roadmap |  |  |
| 4736 | Request #4736 ? project proposal Ministry of Youth Ghana to be signed by CDPMO | Completed | Division for Inclusive Social Development | 15 Dec 2022 | 01 Jan 2022 | 31 Oct 2023 | Ministry of Youth and Sports ¦ info@moys.gov.gh | project proposal Ministry of Youth Ghana to be signed by CDPMO |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4234 | Request #4234 ? Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Completed | Statistics Division | 05 Jul 2022 | 08 Jan 2022 | 30 Dec 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4115 | Request #4115 ? project proposal to be signed | Completed | Division for Inclusive Social Development | 24 Mar 2022 | 01 Apr 2022 | 31 Oct 2022 | n/a ¦ na@na.com | project proposal to be signed |  |  |
| 4097 | Request #4097 ? DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Completed | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals | 15 Feb 2022 | 28 Mar 2022 | 29 Mar 2022 | Eddy Maloka ¦ eddy.maloka@aprm-au.org | DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 3654 | Request #3654 ? The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" | Completed | Division for Public Institutions and Digital Government | 16 Feb 2021 | 11 Nov 2021 | 25 Nov 2021 | Jan Magoro ¦ JanMa@presidency.gov.za | The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" |  |  |
| 3841 | Request #3841 ? The request is to conduct an assessment on the impact of COVID-19 on the sustainable management on forests in Africa. | Completed | United Nations Forum on Forest | 25 Apr 2020 | 01 Jul 2020 | 31 Dec 2021 | Almami Dampha ¦ DamphaA@africa-union.org | The request is to conduct an assessment on the impact of COVID-19 on the sustainable management on forests in Africa. |  |  |
| 3384 | Request #3384 ? Building Capacities of Governments to advance SDG implementation through sport for development and peace, Phase I | Completed | Division for Inclusive Social Development | 01 Jun 2020 |  |  | UNDESA mandate ¦ na@na | Building Capacities of Governments to advance SDG implementation through sport for development and peace, Phase I |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.14 | Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.¦¦Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026. | SD | 30 Jun 2026 | 31 Dec 2026 | $67,832 | Burkina Faso, Cameroon, Chad, Eritrea, Ghana, Liberia, Malawi, Mali, Mauritius, Niger, Sao Tome and Principe, Senegal |  |  |
| SB-001376.99.99.23 | Trade Data Tools Implementation and Maintenance 2026 | SD | 30 Sept 2026 | 31 Dec 2026 | $140,387 | Eswatini, Ghana, Guyana, Papua New Guinea, Saint Lucia, Zambia | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.23¦row:30': 'f_cashOther' has non-numeric value 'Eurostat provides a grant of 53,000 USD to improve and maintain TDT in 2026. The African Union Commission (AUC) will cover the participation cost of its selected member states.'. |
| SB-001379.99.30 | Strengthening Inclusive and Shock-Responsive Social Protection Systems in Africa | DISD | 31 Dec 2026 | 31 Dec 2026 | $40,889 | Djibouti, Ethiopia, Ghana, Kenya, Namibia, Rwanda, Senegal, Uganda, United Republic of Tanzania, Zambia |  | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| SB-001380.92 | Practical Workshops on the Negotiation of Tax Treaties – Seoul (2-6 November 2026) and Madrid (23-27 November 2026) | FSDO | 30 Sept 2026 | 31 Dec 2026 | $0 | Algeria, Bahamas, Belize, Côte d’Ivoire, Democratic Socialist Republic of Sri Lanka, Ghana, Guinea-Bissau, Guyana, Lao People's Democratic Republic, Lesotho, Mozambique, North Macedonia, Peru, Trinidad and Tobago, Tunisia, Zimbabwe | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashDESA' has non-numeric value 'USD XX,XXX to cover travel of FSDO staff and experts, and contractor services (for translation of training materials into Spanish for the Madrid workshop)'. / proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashOther' has non-numeric value 'Organzing partners will fund the travel of participants to the workshops.'. / proposals.xlsx record 'SB-001380.92¦row:48': 'Total Budget' is blank. |
| SB-001376.99.99.31 | Securing the Future of Demographic and Health Data: Country Pathways and a Global Blueprint / | SD | 30 Sept 2026 | 31 Dec 2026 | $86,714 | Bangladesh, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Jordan, Kenya, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Papua New Guinea, Senegal, Tajikistan | Region standardized: 'global' -> 'Global'. |  |
| SB-001376.99.99.24 | International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity¦¦International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity | SD | 30 Sept 2026 | 30 Sept 2026 | $50,630 | Ghana, Indonesia, Jordan, Lao People's Democratic Republic, Lesotho, Madagascar, Philippines, Viet Nam | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. / Proposal past due |
| SB-001376.99.99.22 | Title of the activity | SD | 30 Sept 2026 | 30 Sept 2026 | $79,609 | Benin, Burkina Faso, Cabo Verde, Cameroon, Central African Republic, Congo, Côte d’Ivoire, Equatorial Guinea, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Liberia, Mali, Niger, Nigeria, Senegal, Sierra Leone, Togo | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. | proposals.xlsx record 'SB-001376.99.99.22¦row:73': 'f_cashDESA' has non-numeric value '$79,609.47: Airfare*, Terminal expenses, DSA for staff (resource persons) and international participants, interpretation and coffee-breaks'. / Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth | 2022 | DISD | Ghana, Liberia, Nigeria, Sierra Leone | - Continue the project and scale it up to a small group of countries in West Africa to promote South-South cooperation in a coordinated manner. / - Promote further coordination between subnational and federal levels to align efforts and tailor the implementation of youth employment policies. Create a list of projects or dashboard at the State Action Committee to systematize and follow up on the proposals of stakeholders with innovative ideas and projects. / - Encourage the implementation of strategies rather than action plans. Strategies should have a limited number of strong projects with the potential to achieve overall goals and trickle-down effects to the smaller initiatives. / - Develop specific goals or activities to strengthen capacities linked to the needs of specific groups of young people, such as youth with disabilities and young women. / - Formulate actions linked to the technical skills instruction of young people so that they can adapt to the new paradigms of the labor market and insert themselves into quality employment in high productivity sectors. | - Concrete and direct channels for the participation of young people in the design of public policies can generate valuable information to fine-tune policy formulation and implementation. / - Bringing together ministries and stakeholders at the same table can foster coordination, synergies, and complementarities in youth employment strategies. / - Inducing ministries to interact and align actions with regional and local decision-making bodies promotes participatory and coherent operationalization of youth employment policies. / - Introducing training in project evaluation and monitoring at the local level is essential for reinforcing implementation capacities. / - Interventions that seek to strengthen national capacities for operationalizing public policies need continuity over time to solidify knowledge and practices imparted. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2019-02.2-1 Eval_ILO-DESA.pdf |  | evaluations.xlsx rows 158 (archived) and 30 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Monitoring Progress towards Sustainable Forest Management (2016-2019) | 2019 | UNFFS | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines | - The project document should be used as the reference as much as possible for the implementation and monitoring of the project. A provision for mid-term review is also worthwhile in future projects. / - The Project should maintain better coordination between the country national focal points and UNFF Secretariat, and among the pilot countries for inter-pilot country cross-fertilization of ideas and sharing of experiences in designing and operationalizing monitoring frameworks. / - The UNFF Secretariat should explore more effective cooperation and coordination with CPF members that are key forest-related data generators and users (e.g., FAO, Rio Convention Secretariats, and the International Tropical Timber Organization). / - Pilot countries should make every effort to continue moving forward in designing, improving and utilizing their national forest monitoring frameworks, based on the building blocks generated through the project. | - Developing monitoring frameworks would require a longer term commitment from both the project and pilot countries. / - The project intervention in a pilot country should not have ended after the national consultant’s study on ‘data sources and gaps’ and two national workshops; not having any follow-up process after the national workshops broke the momentum the project had built. / - Perhaps, limiting the number of pilot countries to a lower number in the project and increasing the duration of the project would have provided more resources and attention in going beyond the national studies and consultation workshops, leading to a successful monitoring framework development processes and models that can be scaled up to a larger number of countries. / - The project should be flexible for course correction based on the ground realities. Not being able to initiate project activities in all pilot countries simultaneously impacts not only the efficiency but the effectiveness of the project. / - The project should have an item in its key activities to synthesize the experiences from its pilot countries and present a toolkit of recommendations for developing, maintaining and utilizing a national monitoring framework to monitor progress on SFM in the country, and report to forest-related and relevant international and regional processes such as FAO/FRA, CBD, UNCCD, UNFCCC and UNFF. / - Maintaining record of participants of national workshops is crucial for project management and for gathering post-workshop feedback as an indicator of capacity building. / - If an evaluation-related activity (such as interviews, focus group or panel discussions) is to be attached to a future meeting or workshop, then it should be appropriately included in the programme of the meeting/workshop, and the participants should be notified in advance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/10th tranche/UNFF/UNFF Project Evaluation Report_24Dec2019.docx |  |  |
| Mobilizing Science, Technology and Innovation in developing countries for the SDGs | 2022 | DSDG | Belgium, Brazil, Cambodia, China, Ethiopia, Ghana, India, Japan, Kenya, Korea, Madagascar, Mozambique, Myanmar, Pakistan, Philippines, Rwanda, Serbia, Thailand, Uganda, United States of America, Zambia | - DESA should ensure that projects are based on clear objectives and SMART, relevant indicators which better help measure the impact of activities. / - DESA should ensure regular and efficient monitoring throughout the project, based on thorough monitoring plans. / - DESA should ensure the continuation of the Innovation Competition and participation in the STI Forum for the winners, and develop a longer term programme of Capacity Building and support for these winners. / - DESA should build on the Capacity Building events, Study Visits, STI Roadmaps work and the Ghana Pilot Programme, which were all highly relevant to STI in developing countries. / - DESA should focus on strengthening the OLP, which currently has a low level of relevance to STI in developing countries. DESA should revisit the Independent Technical Assessment and R4D’s recent report ‘UN 2030 Connect Report’ and integrate the prototypes into the OLP. / - If the OLP and associated capacity building activities are to continue, DESA should look carefully at the human and financial resources behind the work, ensuring that there is enough capacity to deliver meaningful results. DESA should consider the financial recommendations made in the Independent Technical Assessment. Resources available must match the ambition for the work, and the level of ambition should be clarified asap. / - Any future project should include longer term support for innovators on the ground, over a period of at least a year. This could focus on the winners of Innovation Competitions. / - Any future project should build on the successes and the lessons learned of the Ghana Pilot Project, which could be scaled to other countries in partnership with R4D. / - DESA should improve the ongoing monitoring around such projects, strengthening the indicators (ensure SMART and relevant indicators) and ensuring that questionnaires are provided to participants following relevant activities (Capacity Building sessions, Study Visits etc). / - DESA should spend more time persuading and convincing partners of the value of integrating their databases with that of the OLP, in order to address the perceived incoherence with OLP partners. / - DESA and partners should consider the viability of one overarching STI project / work stream which incorporates the various streams of work being undertaken - the STI Forum, STI Roadmaps for SDGs, 2030 Connect, Capacity Building etc. The possibility of a joint funding mechanism – an STI Trust Fund – should be explored in order to reduce inefficiencies. / - DESA should allocate meaningful human resources (at least 60% of a full time role) to ensure the success of the OLP and associated Capacity Building activities. / - DESA should ensure that resources allocated to the OLP match the ambition for the OLP. / - DESA should consider allocating more funds for longer term Capacity Building support to innovators across target countries. / - DESA should consider replicating / adapting the relationship with R4D, recognising the importance of having local partners to work with local innovators. This could either be done with R4D, other relevant CSOs or UNCTs (UN Country Teams). / - DESA should ensure there is enough time available for meaningful work to be completed, avoiding last minute rushes. / - DESA should systematically work through tools like Exit strategies, succession planning and cases for financial support before the end of a project, in order to ensure sustainability, whether a project is designed to continue or not. / - DESA, with the IATT, should revisit the Independent Technical Assessment, as well as the recent recommendations by R4D for the OLP, in order to be very clear about the ambition and strategic direction of the OLP before developing the case for support. / - Given the clear mandate provided by MS for the OLP, DESA should attempt to secure a mixture of UN regular budget and voluntary/extra-budgetary funds to finance the OLP. / - DESA should ensure that capacity building activities take place over a longer period, and provide more sustained support for innovators. This should be built into the case for support. / - The UN should integrate the principle of Leave No-One Behind into all its STI related work, ensuring that it does not inadvertently enhance the digital divide. This could be done in the context of this project by offering capacity building activities in different languages, offering interpretation, and ensuring translation of the OLP. / - DESA should consider scaling up the Ghana Pilot Project into other countries, specifically the Technical Support offered to local innovators. / - DESA should build on the momentum around the STI Roadmaps for SDGs and investigate whether a coherent package of work can be built around the Roadmaps, the OLP and the capacity building activities. / - DESA and OICT should consider structuring the OLP (specifically the Search Engine) around the SDGs in order to facilitate closer linkages between STI and HR & GE. / - DESA, and the UN more widely, should strengthen the focus on HR & GE in the project design and monitoring, including concrete details of how HR & GE issues will be addressed. UNEG’s guidance on this should be considered. / - DESA, and the UN more widely, should respect the SDG principle of LNOB by ensuring Capacity Building activities include interpretation, and official sites are available in at least the 6 official languages of the UN. / - DESA should consider contributing to tackling the existing gender inequality in STI by insisting on having at least 50% of women as speakers, moderators and participants in events. / - DESA should incorporate HR & GE specific indicators in its project design. Again, UNEG’s guidance on this should be considered. / - DESA should commit to gathering disaggregated data throughout its projects, starting with clear participant lists for every activity. / - The UN PDF should ensure that the recently developed form which collects HR & GE data is consistently used across all projects which it supports. / - DESA should build on the good practise of the Study Visits, Capacity Building Sessions and Ghana Project, linking STI to specific SDGs and gender issues in order to ensure a meaningful focus on HR & GE. / - DESA should use its position as implementer of this project and Co-Convenor of the IATT to work closely with the IATT to consider the ambition and funding for the OLP, ensuring coherence with the mandate given by MS in Agenda 2030, the AAAA and the Independent Assessment. / - DESA should continue the practise of piggybacking on other meetings and cost-sharing when organising activities. | - The project design could have been improved by developing stronger and more relevant indicators which better help measure the impact of the activities, and by ensuring regular and efficient monitoring throughout the project. / - Insufficient human and financial resources can significantly limit the effectiveness and efficiency of project implementation. / - A lack of clear exit planning, succession planning, and fundraising strategy can undermine the sustainability of project outcomes. / - Longer-term engagement and support for innovators, rather than one-off events or competitions, are valued and more likely to lead to sustained impact. / - Capacity building activities are more inclusive and effective when offered in multiple languages and with interpretation, supporting the Leave No-One Behind principle. / - Partnerships with local organizations, such as R4D in Ghana, enhance the relevance and effectiveness of capacity building for local innovators. / - Integrating gender and human rights considerations from the project design stage, with specific indicators and disaggregated data, leads to better outcomes and more inclusive participation. / - Administrative and technical barriers to integrating partner databases can undermine the effectiveness and coherence of online platforms. / - Piggybacking on existing meetings and cost-sharing with partners increases efficiency and reach. / - Clear political mandates and alignment with broader UN strategies facilitate project relevance and coherence, but must be matched by adequate resources and stakeholder engagement. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2016/PDF-2016-03 DSD internal STI/Reports/Final report & Eva/fisrt ver. 18 Mar 22/STI Evaluation LW final.pdf | Country standardized: 'USA' -> 'United States of America'. | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation | 2021 | DSDG | Algeria, Argentina, Austria, Bolivia (Plurinational State of), Bosnia and Herzegovina, Bulgaria, Colombia, Ecuador, Ethiopia, Georgia, Ghana, Guyana, Honduras, India, Italy, Kenya, Lebanon, Malawi, Morocco, Nauru, Niger, North Macedonia, Pakistan, Papua New Guinea, Poland, Portugal, Samoa, Seychelles, United Arab Emirates, United Kingdom of Great Britain and Northern Ireland, Zambia | - Future similar projects should apply a Results-Based Management approach, developing an M&E framework, plan, and data collection tools that articulate instrumental and transformational changes rather than processes. / - Additional resources should be mobilized to ensure follow-up and implementation of the commitments secured in the global roadmap and in the Energy Compacts, starting with pilot projects to determine their viability and scalability. / - Future similar projects should include studies on Cost-Benefit Analysis to determine the viability and scalability of policy changes, ranking options in the Energy Compacts according to their costs and benefits to society. / - More staff wholly dedicated to the project should be planned for at the conceptualization stage, including roles for communications and project management assistance, and a project steering committee to ensure recommendations for course corrections are followed. / - Future projects should develop a clear partnership strategy to guide implementers on where to invest in collaboration for the greatest value to the organization. / - The composition of the global Technical Advisory Group (TAG) should be replicated and cascaded to regional and national levels to ensure continuity and nuanced specificities beyond the project’s shelf life. / - Future projects should leverage United Nations Information Centers (UNICs) to develop and implement coordinated communications strategies for Member States, amplifying project achievements at the local level. | - The joint production and dissemination of knowledge products laid a strong foundation for sustainability, scaling up, replication, and future programming, increasing knowledge and capacities for accountability. / - Synergistic partnerships and multi-stakeholder participation facilitated ownership, sustainability, and coherence between national planning processes, enhancing coordination among line ministries for timely VNR production. / - Upstream activities allowed the project to adapt to challenges such as Covid-19, and partnering with the public sector leveraged government influence for mainstreaming SDG7 implementation. / - Engagement with the private sector was strategic, as private sector input and financial commitments in the Energy Compacts are essential for accelerating SDG7 implementation. / - The project was initially thinly staffed, but hiring a dedicated Project Officer after commencement improved implementation; future projects should plan for adequate dedicated staffing from the outset. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2017/2017-02 DSD SDG7/Reports/Evaluation/Final_Dec 18th_UNDESA_Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Monitoring Progress towards Sustainable Forest Management | 2019 | UNFFS | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines | - The project document should be used as the reference as much as possible for the implementation and monitoring of the project. A provision for mid-term review is also worthwhile in future projects. / - The Project should maintain better coordination between the country national focal points and UNFF Secretariat, and among the pilot countries for inter-pilot country cross-fertilization of ideas and sharing of experiences in designing and operationalizing monitoring frameworks. / - The UNFF Secretariat should explore more effective cooperation and coordination with CPF members that are key forest-related data generators and users (e.g., FAO, Rio Convention Secretariats, and the International Tropical Timber Organization). / - Pilot countries should make every effort to continue moving forward in designing, improving and utilizing their national forest monitoring frameworks, based on the building blocks generated through the project. | - Developing monitoring frameworks would require a longer term commitment from both the project and pilot countries. / - The project intervention in a pilot country should not have ended after the national consultant’s study on ‘data sources and gaps’ and two national workshops; not having any follow-up process after the national workshops broke the momentum the project had built. This should be a lesson to apply in designing future projects with similar themes. / - Perhaps, limiting the number of pilot countries to a lower number in the project and increasing the duration of the project would have provided more resources and attention in going beyond the national studies and consultation workshops, leading to a successful monitoring framework development processes and models that can be scaled up to a larger number of countries. / - The project should be flexible for course correction based on the ground realities. Not being able to initiate project activities in all pilot countries simultaneously, as was evident in this project, impacts not only the efficiency but the effectiveness of the project. / - The project should have an item in its key activities to synthesize the experiences from its pilot countries and present a toolkit of recommendations for developing, maintaining and utilizing a national monitoring framework to monitor progress on SFM in the country, and report to forest-related and relevant international and regional processes such as FAO/FRA, CBD, UNCCD, UNFCCC and UNFF. / - Maintaining record of participants of national workshops is crucial for project management and for gathering post-workshop feedback as an indicator of capacity building. / - If an evaluation-related activity (such as interviews, focus group or panel discussions) is to be attached to a future meeting or workshop, then it should be appropriately included in the programme of the meeting/workshop, and the participants should be notified in advance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FF/1617F SB-006014 10th tranche - Monitoring of Sus For Mgmt/Final evaluation/Report/UNFF Project Evaluation Report_24Dec2019.docx.pdf |  |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 3 | evaluations.xlsx rows 158 (archived) and 30 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 8 | proposals.xlsx record 'SB-001376.99.99.22¦row:73': 'f_cashDESA' has non-numeric value '$79,609.47: Airfare*, Terminal expenses, DSA for staff (resource persons) and international participants, interpretation and coffee-breaks'. |
| 9 | proposals.xlsx record 'SB-001376.99.99.23¦row:30': 'f_cashOther' has non-numeric value 'Eurostat provides a grant of 53,000 USD to improve and maintain TDT in 2026. The African Union Commission (AUC) will cover the participation cost of its selected member states.'. |
| 10 | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. |
| 11 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. |
| 12 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. |
| 13 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. |
| 14 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. |
| 15 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| 16 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashDESA' has non-numeric value 'USD XX,XXX to cover travel of FSDO staff and experts, and contractor services (for translation of training materials into Spanish for the Madrid workshop)'. |
| 17 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashGov' has non-numeric value 'N/A'. |
| 18 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashOther' has non-numeric value 'Organzing partners will fund the travel of participants to the workshops.'. |
| 19 | proposals.xlsx record 'SB-001380.92¦row:48': 'Total Budget' is blank. |
| 20 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 21 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 22 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 23 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 24 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 25 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 26 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 27 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 28 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 29 | requests.xlsx record '5139': End date 2024-10-09 is before start date 2025-01-07. |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 57 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 58 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 59 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 60 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 61 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 62 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 65 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 66 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 67 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 68 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 69 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 70 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 71 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 72 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 73 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 74 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 75 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 76 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |