Jordan

Asia

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Jordan is presented in this country card as part of Asia, with Jordan also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Jordan highlights 6 projects for Jordan, including 0 active or planned projects for Jordan and 6 completed or closed projects for Jordan.

For Jordan, the report includes 17 requests for Jordan, 7 RPTC proposals for Jordan, 0 RPTC activities for Jordan, and 1 travel records for Jordan. Financially, Jordan shows USD 20,260,468 in project budget, $401,654 in proposal planned budget, and $0 in consumed RPTC activity budget for Jordan.

The main organizational coverage for Jordan points to Division for Sustainable Development Goals, DSDG, Economic Analysis and Policy Division, Financing for Sustainable Development Office. Activity records for Jordan list 0 participants, including 0 women participants, the current quality review for Jordan includes 53 data quality notes. Current highlights for Jordan include a request focus for Jordan: Request #5576 ? This proposal is for an international workshop on geostatistical integration for population and housing censuses, incorporating the ninth meeting of the United Nations Expert Group on the Integration of Statistical and Geospatial Information, to prepare national experts to operationalize the Global Statistical Geospatial Framework (GSGF) Second Edition and advance the revision of the UN Handbook on Geospatial Infrastructure in Support of Census Activities. The primary objectives of the meeting include defining a future-facing value proposition for statistical-geospatial integration as shared national data infrastructure beyond 2030, establishing an inclusive 2027â€“2029 workplan aligned with Statistical Commission and UN-GGIM decisions, providing practical guidance on addresses, building and dwelling registers, geocoding, common geographies, and dissemination under the five GSGF Principles, and scoping country pilots and regional support mechanisms. The workshop is organized by the United Nations Statistics Division (UNSD) in collaboration with regional and international partners. Participants will include members of the Expert Group, representatives of Member States from national statistical offices and national geospatial information agencies (paired where possible), relevant United Nations entities, and technical and development partners. The workshop is planned to take place from 30 November to 4 December 2026 at the United Nations Conference Centre (UNCC) at the United Nations Economic and Social Commission for Asia and the Pacific (ESCAP) in Bangkok, Thailand.; an RPTC proposal focus for Jordan: Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF .

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 6 |
| Project budget | USD 20,260,468 |
| Requests | 17 |
| RPTC proposals | 7 |
| Proposal planned budget | $401,654 |
| RPTC activities | 0 |
| Consumed RPTC budget | $0 |
| Activity participants | 0 |
| Women participants | 0 |
| Travel records | 1 |
| Evaluations | 8 |
| Data quality notes | 53 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Accelerating implementation of Data For Now in eight countries in Africa and Asia |  | country | Statistics Division | Closed | 15 Jun 2022 | 30 Jun 2024 | USD 1,500,468 | Ethiopia, Jordan, Morocco, Sierra Leone, Tunisia, Viet Nam |  |
| Collection and use of international migration data in the context of the 2030 Agenda | 1819E | country | Statistics Division | Closed | 01 Jan 2018 | 31 Dec 2021 | USD 800,000 | Argentina, Dominican Republic, Georgia, Jordan, Mexico, Thailand |  |
| Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries | 1415I | country | Division for Sustainable Development Goals | Closed | 15 Aug 2020 | 17 Dec 2020 | USD 639,000 | Belize, Colombia, Ethiopia, Honduras, Jordan | projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Eastern Africa' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Latin America and the Caribbean' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'South America' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country text 'Western Asia' could not be matched; no country assignment was inferred. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Eastern Africa' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Latin America and the Caribbean' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'South America' was not matched to GeoData and was ignored. / projects.csv record 'Monitoring and reporting on sustainable development objectives, goals and targets; enhancing institutional capability in selected developing countries ¦ 2020-08-15T00:00:00 ¦ 1415I': Country/Sub region 'Western Asia' was not matched to GeoData and was ignored. |
| Programme for Statistics and Data | 1617A | country | Statistics Division | Closed | 01 Jan 2018 | 31 Dec 2021 | USD 12,000,000 | Gambia, Japan, Jordan, Kazakhstan, Namibia, Philippines, Saudi Arabia, Thailand |  |
| Statistics and Data Project ‐ Resilient and agile National Statistical Systems (NSS) to meet post COVID‐19 data needs to recover better | 2225A | country | Statistics Division | Closed | 01 Sept 2022 | 31 Oct 2025 | USD 3,000,000 | Bhutan, Burundi, Dominican Republic, Ecuador, Eritrea, Fiji, Georgia, Indonesia, Jamaica, Jordan, Kazakhstan, Namibia, Republic of Moldova, Senegal, State of Palestine, Tunisia |  |
| Towards integrated national financing framework | 2124A | country | Financing for Sustainable Development Office | Closed | 01 Mar 2021 | 28 Jun 2024 | USD 2,321,000 | Belarus, Burkina Faso, Colombia, Costa Rica, Egypt, Indonesia, Jordan, Kyrgyzstan, Pakistan, Zambia |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5576 | Request #5576 ? This proposal is for an international workshop on geostatistical integration for population and housing censuses, incorporating the ninth meeting of the United Nations Expert Group on the Integration of Statistical and Geospatial Information, to prepare national experts to operationalize the Global Statistical Geospatial Framework (GSGF) Second Edition and advance the revision of the UN Handbook on Geospatial Infrastructure in Support of Census Activities. The primary objectives of the meeting include defining a future-facing value proposition for statistical-geospatial integration as shared national data infrastructure beyond 2030, establishing an inclusive 2027â€“2029 workplan aligned with Statistical Commission and UN-GGIM decisions, providing practical guidance on addresses, building and dwelling registers, geocoding, common geographies, and dissemination under the five GSGF Principles, and scoping country pilots and regional support mechanisms. The workshop is organized by the United Nations Statistics Division (UNSD) in collaboration with regional and international partners. Participants will include members of the Expert Group, representatives of Member States from national statistical offices and national geospatial information agencies (paired where possible), relevant United Nations entities, and technical and development partners. The workshop is planned to take place from 30 November to 4 December 2026 at the United Nations Conference Centre (UNCC) at the United Nations Economic and Social Commission for Asia and the Pacific (ESCAP) in Bangkok, Thailand. | Under consideration | Statistics Division | 11 Sept 2026 | 30 Nov 2026 | 04 Dec 2026 | Seiffe Tadesse ¦ tadesse5@un.org | This proposal is for an international workshop on geostatistical integration for population and housing censuses, incorporating the ninth meeting of the United Nations Expert Group on the Integration of Statistical and Geospatial Information, to prepare national experts to operationalize the Global Statistical Geospatial Framework (GSGF) Second Edition and advance the revision of the UN Handbook on Geospatial Infrastructure in Support of Census Activities. The primary objectives of the meeting include defining a future-facing value proposition for statistical-geospatial integration as shared national data infrastructure beyond 2030, establishing an inclusive 2027â€“2029 workplan aligned with Statistical Commission and UN-GGIM decisions, providing practical guidance on addresses, building and dwelling registers, geocoding, common geographies, and dissemination under the five GSGF Principles, and scoping country pilots and regional support mechanisms. The workshop is organized by the United Nations Statistics Division (UNSD) in collaboration with regional and international partners. Participants will include members of the Expert Group, representatives of Member States from national statistical offices and national geospatial information agencies (paired where possible), relevant United Nations entities, and technical and development partners. The workshop is planned to take place from 30 November to 4 December 2026 at the United Nations Conference Centre (UNCC) at the United Nations Economic and Social Commission for Asia and the Pacific (ESCAP) in Bangkok, Thailand. | Country standardized: 'Turkey' -> 'Türkiye'. |
| 5573 | Request #5573 ? The SDMx Experts workshop is a biennial event that brings together practitioners of the Standard for Statistical Data and Metadata (SDMx), who share knowledge and experience, learn about latest developments and discuss common challenges and their resolutions in the area of automated data reporting and dissemination. The event is jointly organized by the eight SDMx Sponsor Agencies: BIS, ECB, Eurostat, ILO, IMF, OECD, UNSD, and the World Bank. The event is hosted by OECD, TurkStat and Central Bank of the Republic of TÃ¼rkiye. / The 13th SDMx Experts Workshop will take place in Ankara, TÃ¼rkiye, from 30 Nov â€“ 4 Dec 2026. The participants include representatives of National Statistical Offices, Central Banks, international organizations, academia, and the private sector from across the globe. / The Experts Workshop will feature a 4-day plenary and 1-day capacity building session. The plenary will focus on knowledge and experience sharing. The capacity-building session will focus on advanced and emerging topics including integration with Artificial Intelligence; advanced data modeling, validation, and transformation; automated data pipelines, and related topics. / A total of up to 100 participants are expected to attend the workshop, of whom 6 are to be funded by DESA. | Under consideration | Statistics Division | 27 Aug 2026 | 30 Nov 2026 | 04 Dec 2026 | Abdulla Gozalov ¦ gozalov@un.org | The SDMx Experts workshop is a biennial event that brings together practitioners of the Standard for Statistical Data and Metadata (SDMx), who share knowledge and experience, learn about latest developments and discuss common challenges and their resolutions in the area of automated data reporting and dissemination. The event is jointly organized by the eight SDMx Sponsor Agencies: BIS, ECB, Eurostat, ILO, IMF, OECD, UNSD, and the World Bank. The event is hosted by OECD, TurkStat and Central Bank of the Republic of TÃ¼rkiye. / The 13th SDMx Experts Workshop will take place in Ankara, TÃ¼rkiye, from 30 Nov â€“ 4 Dec 2026. The participants include representatives of National Statistical Offices, Central Banks, international organizations, academia, and the private sector from across the globe. / The Experts Workshop will feature a 4-day plenary and 1-day capacity building session. The plenary will focus on knowledge and experience sharing. The capacity-building session will focus on advanced and emerging topics including integration with Artificial Intelligence; advanced data modeling, validation, and transformation; automated data pipelines, and related topics. / A total of up to 100 participants are expected to attend the workshop, of whom 6 are to be funded by DESA. |  |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |
| 5368 | Request #5368 ? UNSD is preparing a use case to demonstrate the dissemination of data and the integration of SDG metadata into statistical outputs using the SDMX standard. This initiative focuses on linking SDG metadata with the UNdata mobile applications to enhance the accessibility and usability of statistical information. This use case can be used in workshops and guide participants through the process of extracting SDG data and metadata and integrating them into digital products. To support this, UNSD plans to update both UNdata Android and iOS apps with the latest available 2025 data - these updates will mirror the content of the printed Pocketbook publication. For each included SDG indicator, the apps will feature direct links to corresponding metadata, enabling users to explore definitions, methodologies, and sources seamlessly. / To ensure a fully functional and user-friendly experience, UNSD also plans to address several technical issues identified by both internal and external users in the SDG user interface, APIs and metadata related components of the system. This project not only enhances the visibility and utility of SDG data and metadata but also promotes best practices in data and metadata integration and digital dissemination using SDMX standards. / The proposal covers the contractual services needed to update the UNdata apps and fix some components in the SDG infrastructure, including SDG metadata. | Under consideration | Statistics Division | 30 Oct 2025 | 03 Nov 2025 | 27 Feb 2026 | Harumi Shibata Salazar ¦ shibata@un.org | UNSD is preparing a use case to demonstrate the dissemination of data and the integration of SDG metadata into statistical outputs using the SDMX standard. This initiative focuses on linking SDG metadata with the UNdata mobile applications to enhance the accessibility and usability of statistical information. This use case can be used in workshops and guide participants through the process of extracting SDG data and metadata and integrating them into digital products. To support this, UNSD plans to update both UNdata Android and iOS apps with the latest available 2025 data - these updates will mirror the content of the printed Pocketbook publication. For each included SDG indicator, the apps will feature direct links to corresponding metadata, enabling users to explore definitions, methodologies, and sources seamlessly. / To ensure a fully functional and user-friendly experience, UNSD also plans to address several technical issues identified by both internal and external users in the SDG user interface, APIs and metadata related components of the system. This project not only enhances the visibility and utility of SDG data and metadata but also promotes best practices in data and metadata integration and digital dissemination using SDMX standards. / The proposal covers the contractual services needed to update the UNdata apps and fix some components in the SDG infrastructure, including SDG metadata. |  |
| 5280 | Request #5280 ? UNSD conducts an annual Global Assessment of Environmental-Economic Accounting and Supporting Statistics (https://seea.un.org/content/global-assessment-environmental-economic-accounting) to monitor the implementation of the System of Environmental-Economic Accounting (SEEA) in countries. This assessment provides critical insights into global progress and challenges in integrating environmental and economic data and is the basis for the monitoring of SDG indicator 15.9.1(b). While the number of countries implementing the SEEA has steadily increased since 2014, recent assessments indicate that this growth has plateaued, suggesting that many countries may be encountering persistent barriers to further implementation. / This stagnation underscores the urgent need to strengthen national capacities for compiling SEEA accounts. Many countries, particularly those in the early stages of implementation, face challenges related to technical expertise, institutional coordination, data availability, and methodological understanding. Addressing these challenges requires targeted support and knowledge exchange. The proposed activity will facilitate peer learning and collaboration among countries. Through the sharing of practical experiences, lessons learned, and innovative approaches, countries will gain valuable insights into overcoming common obstacles and advancing their SEEA implementation. / Target countries will learn from the sharing of country experiences in the compilation of environmental accounts of other countries and how those countries have addressed challenges both in the implementation of the accounts and in the developments of concepts, methods and tools to address these challenges. / This activity also facilitates South-South cooperation, enabling countries with similar development contexts to support one another. It promotes mutual learning, strengthens regional and global networks, and builds lasting partnerships. The London Group meetings, which attract a wide range of countries at various stages of SEEA implementation as well as key international organizations, provide an ideal platform for such an engagement. These meetings facilitate dialogue, encourage innovation, and help align national efforts with global standards and best practices. By building capacity through collaboration and shared learning, it empowers countries to produce high-quality environmental-economic accounts that inform sustainable development policies and contribute to achieving the SDGs. | Under consideration | Statistics Division | 04 Aug 2025 | 22 Sept 2025 | 25 Sept 2025 | Marko Javorsek ¦ marko.javorsek@un.org | UNSD conducts an annual Global Assessment of Environmental-Economic Accounting and Supporting Statistics (https://seea.un.org/content/global-assessment-environmental-economic-accounting) to monitor the implementation of the System of Environmental-Economic Accounting (SEEA) in countries. This assessment provides critical insights into global progress and challenges in integrating environmental and economic data and is the basis for the monitoring of SDG indicator 15.9.1(b). While the number of countries implementing the SEEA has steadily increased since 2014, recent assessments indicate that this growth has plateaued, suggesting that many countries may be encountering persistent barriers to further implementation. / This stagnation underscores the urgent need to strengthen national capacities for compiling SEEA accounts. Many countries, particularly those in the early stages of implementation, face challenges related to technical expertise, institutional coordination, data availability, and methodological understanding. Addressing these challenges requires targeted support and knowledge exchange. The proposed activity will facilitate peer learning and collaboration among countries. Through the sharing of practical experiences, lessons learned, and innovative approaches, countries will gain valuable insights into overcoming common obstacles and advancing their SEEA implementation. / Target countries will learn from the sharing of country experiences in the compilation of environmental accounts of other countries and how those countries have addressed challenges both in the implementation of the accounts and in the developments of concepts, methods and tools to address these challenges. / This activity also facilitates South-South cooperation, enabling countries with similar development contexts to support one another. It promotes mutual learning, strengthens regional and global networks, and builds lasting partnerships. The London Group meetings, which attract a wide range of countries at various stages of SEEA implementation as well as key international organizations, provide an ideal platform for such an engagement. These meetings facilitate dialogue, encourage innovation, and help align national efforts with global standards and best practices. By building capacity through collaboration and shared learning, it empowers countries to produce high-quality environmental-economic accounts that inform sustainable development policies and contribute to achieving the SDGs. |  |
| 5234 | Request #5234 ? At the 15th session of the ESCWA Statistical Committee, on 16-17 Nov 2022, the member States requested the ESCWA Secretariat to "Support member States in developing strategies to bridge gaps in data flows for sustainable, development indicators, so as to ensure the sustainability and modernization of national reporting platforms, and to exchange statistical data and metadata nationally between components of statistical systems using modern technologies, such as SDMX, to ensure that no one is left behindâ€¦â€ , which follows similar requests made at previous sessions. / ESCWA and UNSD are addressing these through a series of joint online and in-person training events on SDMX-based dissemination and exchange of SDG data and metadata. The workshop in question is the 8th in the series and will directly contribute to the member Statesâ€™ capacity to exchange and disseminate SDG data and metadata using the global standards and advanced tools, and implementation of SDMX data exchange at the national level. / The workshop is organized jointly by UN ESCWA and UNSD and is planned to take place in Muscat, Oman, on 10-13 November 2025 (4 days). A pre-workshop meeting will be held on 9 November 2025 to check the venue and final coordination for the event. The Workshop will bring together statisticians and IT specialists from various national statistical offices in the Arab region. / This workshop is a continuation of UNSD and ESCWAâ€™s work to improve and strengthen the SDMX skills of Member States on SDG data reporting and to implement SDMX at the national level. As requested by Member States in the region, the training will cover different SDMX topics and provide hands on exercises with the aim to introduce SDMX tools to enable the automation of data and metadata exchange between entities. It will employ a variety of tools including presentations, hands-on exercises, and the sharing of good practices and challenges by countries through discussions and presentations. | Completed | Statistics Division | 10 Jun 2025 | 08 Nov 2025 | 15 Nov 2025 | Harumi Shibata Salazar ¦ shibata@un.org | At the 15th session of the ESCWA Statistical Committee, on 16-17 Nov 2022, the member States requested the ESCWA Secretariat to "Support member States in developing strategies to bridge gaps in data flows for sustainable, development indicators, so as to ensure the sustainability and modernization of national reporting platforms, and to exchange statistical data and metadata nationally between components of statistical systems using modern technologies, such as SDMX, to ensure that no one is left behindâ€¦â€ , which follows similar requests made at previous sessions. / ESCWA and UNSD are addressing these through a series of joint online and in-person training events on SDMX-based dissemination and exchange of SDG data and metadata. The workshop in question is the 8th in the series and will directly contribute to the member Statesâ€™ capacity to exchange and disseminate SDG data and metadata using the global standards and advanced tools, and implementation of SDMX data exchange at the national level. / The workshop is organized jointly by UN ESCWA and UNSD and is planned to take place in Muscat, Oman, on 10-13 November 2025 (4 days). A pre-workshop meeting will be held on 9 November 2025 to check the venue and final coordination for the event. The Workshop will bring together statisticians and IT specialists from various national statistical offices in the Arab region. / This workshop is a continuation of UNSD and ESCWAâ€™s work to improve and strengthen the SDMX skills of Member States on SDG data reporting and to implement SDMX at the national level. As requested by Member States in the region, the training will cover different SDMX topics and provide hands on exercises with the aim to introduce SDMX tools to enable the automation of data and metadata exchange between entities. It will employ a variety of tools including presentations, hands-on exercises, and the sharing of good practices and challenges by countries through discussions and presentations. |  |
| 5207 | Request #5207 ? The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Completed | Statistics Division | 09 May 2025 | 30 Sept 2025 | 03 Oct 2025 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Country standardized: 'Republic of Korea' -> 'Korea'. |
| 5131 | Request #5131 ? The Regional Workshop on Implementing the new System of National Accounts, 2025 (2025 SNA) and Compiling Digital Supply and Use Tables is jointly organized by the United Nations Statistics Division (UNSD), the Arab Monetary Fund (AMF), the Economic and Social Commission for West Asia (ESCWA) and the International Monetary Fund (IMF). The workshop aims to enhance participantsâ€™ capacity on a) the implementation of the System of National Accounts, 2025 (2025 SNA): overview and planning the implementation, globalization, digitalization, well-being and sustainability, and communicating transition to 2025 SNA); b) policy relevance of compiling the digital economy accounts under the new framework; and c) compilation of the Digital Supply and Use Tables under the new framework and data sources. / The workshop will increase technical capabilities to produce high quality economic statistics for the compilation of national accounts supporting data driven decision facilitating the implementation of the Sustainable Development Goals. Approximately 50 participants and independent experts from 22 countries and six international organizations are expected to attend this regional workshop. / The requested funds will cover the travel expenses of two resource persons from DESA and a total of four (4) participants from the National Statistics Offices of Jordan, Morocco, State of Palestine, and Tunisia. | Under consideration | Statistics Division | 18 Mar 2025 | 09 Sept 2025 | 11 Sept 2025 | Edem Kludza ¦ edem.kludza@un.org | The Regional Workshop on Implementing the new System of National Accounts, 2025 (2025 SNA) and Compiling Digital Supply and Use Tables is jointly organized by the United Nations Statistics Division (UNSD), the Arab Monetary Fund (AMF), the Economic and Social Commission for West Asia (ESCWA) and the International Monetary Fund (IMF). The workshop aims to enhance participantsâ€™ capacity on a) the implementation of the System of National Accounts, 2025 (2025 SNA): overview and planning the implementation, globalization, digitalization, well-being and sustainability, and communicating transition to 2025 SNA); b) policy relevance of compiling the digital economy accounts under the new framework; and c) compilation of the Digital Supply and Use Tables under the new framework and data sources. / The workshop will increase technical capabilities to produce high quality economic statistics for the compilation of national accounts supporting data driven decision facilitating the implementation of the Sustainable Development Goals. Approximately 50 participants and independent experts from 22 countries and six international organizations are expected to attend this regional workshop. / The requested funds will cover the travel expenses of two resource persons from DESA and a total of four (4) participants from the National Statistics Offices of Jordan, Morocco, State of Palestine, and Tunisia. |  |
| 5132 | Request #5132 ? The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Under consideration | Statistics Division | 13 Mar 2025 | 15 Mar 2025 | 15 Jul 2025 | Matthias Reister ¦ reister@un.org | The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. |  |
| 5075 | Request #5075 ? The national statistical systems in many countries are under pressure to innovate, that is increasing collaboration, making use of non-traditional data sources, methods and tools. To do this in an effective way, it is key that they also have the needed IT architecture and infrastructure available. UN Statistics Division (UNSD), as part of the Data for Now initiative and DA13 on admin data, has developed a modular, open-source IT infrastructure. A few countries have already deployed the system and are experiencing substantial differences in reduced processing time, more stable systems and easier transfer of data from other data holders. More countries want to implement this. / Overall, UNSD has developed a number of materials and tools in capacity development that member states can benefit from, but due to very limited capacities on web management, websites could not be updated, and materials also couldnâ€™t be added. To more efficiently provide member states with the resources, these updates also need to be urgently made | Ongoing | Statistics Division | 18 Sept 2024 | 01 Oct 2024 | 31 Dec 2024 | Vibeke O Nielsen ¦ vibeke.nielsen@un.org | The national statistical systems in many countries are under pressure to innovate, that is increasing collaboration, making use of non-traditional data sources, methods and tools. To do this in an effective way, it is key that they also have the needed IT architecture and infrastructure available. UN Statistics Division (UNSD), as part of the Data for Now initiative and DA13 on admin data, has developed a modular, open-source IT infrastructure. A few countries have already deployed the system and are experiencing substantial differences in reduced processing time, more stable systems and easier transfer of data from other data holders. More countries want to implement this. / Overall, UNSD has developed a number of materials and tools in capacity development that member states can benefit from, but due to very limited capacities on web management, websites could not be updated, and materials also couldnâ€™t be added. To more efficiently provide member states with the resources, these updates also need to be urgently made |  |
| 5041 | Request #5041 ? Climate change is one of the most pressing policy issues around the world, with all countries being vulnerable to its adverse effects. To better mitigate climate change, countries are more and more looking to understand how to use energy more effectively and sustainably. Such an understanding requires countries to have high-quality energy statistics, balances and accounts. Together, energy statistics, balances and accounts can provide governments with the data they need to understand how the energy sector can be made more efficient and sustainable; how the economy can be made more energy efficient; and how changes in energy use can contribute to fewer emissions. ESCWA countries have expressed interest in capacity building on energy statistics and accounts. In addition, according to the 2023 Global Assessment on Environmental-Economic Accounting, Jordan plans to restart compilation of System of Environmental-Economic Accounting (SEEA) accounts; Morocco and Tunisia have plans to expand its compilation of SEEA accounts; and Somalia has plans to begin compilation of SEEA accounts. / National statistical offices are well placed to produce energy statistics, balances and accounts. Energy statistics and balances can be compiled according to the International Recommendations for Energy Statistics (IRES), and energy accounts can be compiled according to the international statistical standard, the System of Environmental-Economic Accounting (SEEA). At the same time, there is a need to strengthen the capacity of national statistical offices and other relevant ministries to produce and disseminate energy statistics, balances and accounts to better meet user needs. / UNSD, in collaboration with ESCWA, SESRIC, IEA and AITRS held the workshop, "Energy Statistics, Balances and Accounts for Informed Energy and Climate Policies" from 10-12 December in Ankara. More than 40 participants from national statistical offices and ministries of energy came together from 10-12 December 2024 in Ankara to build capacity compilation and use of energy statistics, balances and accounts to support the dissemination of high-quality data for energy and climate change policies. The workshop also covered the institutional mechanisms needed to strengthen the institutions producing these statistics and allowed countries to share their experiences. | Completed | Statistics Division | 19 Aug 2024 | 10 Dec 2024 | 12 Dec 2024 | Jessica Ying Chan ¦ jessica.chan@un.org | Climate change is one of the most pressing policy issues around the world, with all countries being vulnerable to its adverse effects. To better mitigate climate change, countries are more and more looking to understand how to use energy more effectively and sustainably. Such an understanding requires countries to have high-quality energy statistics, balances and accounts. Together, energy statistics, balances and accounts can provide governments with the data they need to understand how the energy sector can be made more efficient and sustainable; how the economy can be made more energy efficient; and how changes in energy use can contribute to fewer emissions. ESCWA countries have expressed interest in capacity building on energy statistics and accounts. In addition, according to the 2023 Global Assessment on Environmental-Economic Accounting, Jordan plans to restart compilation of System of Environmental-Economic Accounting (SEEA) accounts; Morocco and Tunisia have plans to expand its compilation of SEEA accounts; and Somalia has plans to begin compilation of SEEA accounts. / National statistical offices are well placed to produce energy statistics, balances and accounts. Energy statistics and balances can be compiled according to the International Recommendations for Energy Statistics (IRES), and energy accounts can be compiled according to the international statistical standard, the System of Environmental-Economic Accounting (SEEA). At the same time, there is a need to strengthen the capacity of national statistical offices and other relevant ministries to produce and disseminate energy statistics, balances and accounts to better meet user needs. / UNSD, in collaboration with ESCWA, SESRIC, IEA and AITRS held the workshop, "Energy Statistics, Balances and Accounts for Informed Energy and Climate Policies" from 10-12 December in Ankara. More than 40 participants from national statistical offices and ministries of energy came together from 10-12 December 2024 in Ankara to build capacity compilation and use of energy statistics, balances and accounts to support the dissemination of high-quality data for energy and climate change policies. The workshop also covered the institutional mechanisms needed to strengthen the institutions producing these statistics and allowed countries to share their experiences. |  |
| 4996 | Request #4996 ? Following the presentation of STAT (see notes above) at the UN Statistical Commission in 2024, a number of countries have contacted UNSD and other GIST members as they want to implement STAT in their countries (all those listed in this demand proposal). Several of these do need support to implement STAT. Other GIST members are looking at supporting some of the countries, and UNSD is hoping to support a selected number of African countries that have requested the support. Attached are a few requests that have been formalized in writing. | Under consideration | Statistics Division | 07 Jun 2024 | 01 Jul 2024 | 31 Dec 2024 | Odilon Isaie Gheahnjim ¦ odilon.gheahnjim@ins-camreoun.cm | Following the presentation of STAT (see notes above) at the UN Statistical Commission in 2024, a number of countries have contacted UNSD and other GIST members as they want to implement STAT in their countries (all those listed in this demand proposal). Several of these do need support to implement STAT. Other GIST members are looking at supporting some of the countries, and UNSD is hoping to support a selected number of African countries that have requested the support. Attached are a few requests that have been formalized in writing. |  |
| 4960 | Request #4960 ? The United Nations Statistics Division (UNSD) is proposing to organize a regional workshop on statistical business registers and industrial classifications, in collaboration with the United Nations Economic and Social Commission for Western Asia (ESCWA) and the Arab Institute for Training and Research in Statistics (AITRS), in Amman, Jordan on 25 â€“ 27 June 2024. / The objectives of this regional workshop course include: 1) help participants acquire knowledge and skills on the development and use of statistical business registers (SBRs) for data production of official business statistics; and 2) introduce to the participants the relevant resources that have been produced by the United Nations Committee of Experts on Business and Trade Statistics (UNCEBTS) and other Committees with regard to SBR development, including the SBR Maturity Model, the relevant toolkit for assessment on the SBR development, and ISIC, Rev. 5 and other classifications in use in the SBR. / The total budget of this proposal is US$38,056.34, which covers the participation of two DESA/UNSD staff members, two resource persons from the UK and from the Netherlands, and 12 participants from the National Statistics Offices in the ESCWA region. | Under consideration | Statistics Division | 15 Apr 2024 | 25 Jun 2024 | 27 Jun 2024 | Julian Chow ¦ chowj@un.org | The United Nations Statistics Division (UNSD) is proposing to organize a regional workshop on statistical business registers and industrial classifications, in collaboration with the United Nations Economic and Social Commission for Western Asia (ESCWA) and the Arab Institute for Training and Research in Statistics (AITRS), in Amman, Jordan on 25 â€“ 27 June 2024. / The objectives of this regional workshop course include: 1) help participants acquire knowledge and skills on the development and use of statistical business registers (SBRs) for data production of official business statistics; and 2) introduce to the participants the relevant resources that have been produced by the United Nations Committee of Experts on Business and Trade Statistics (UNCEBTS) and other Committees with regard to SBR development, including the SBR Maturity Model, the relevant toolkit for assessment on the SBR development, and ISIC, Rev. 5 and other classifications in use in the SBR. / The total budget of this proposal is US$38,056.34, which covers the participation of two DESA/UNSD staff members, two resource persons from the UK and from the Netherlands, and 12 participants from the National Statistics Offices in the ESCWA region. |  |
| 4959 | Request #4959 ? The workshop is organized jointly by UN ESCWA, AITRS (Arab Institute for Training and Research in Statistic), LAS (League of Arab States) and UNSD and is planned to take place in Cairo, Egypt, on 3-5 June 2024 (3 days). A pre-workshop meeting will be held on 2 June 2024 to test the materials in the venue and final coordination for the event. The Workshop will bring together statisticians and IT specialists from various national statistical offices in the Arab region. / This workshop is a continuation of UNSD and ESCWAâ€™s work to improve and strengthen the SDMX skills of Member States on SDG data reporting and to implement SDMX at the national level. As requested by Member States in the region, the training will cover advanced SDMX topics and provide in-depth hands on exercises with the aim to introduce SDMX tools to enable the automation of data and metadata exchange between entities. It will employ a variety of tools including presentations, hands-on exercises, and the sharing of good practices and challenges by countries through discussions and presentations. | Under consideration | Statistics Division | 15 Apr 2024 | 02 Jun 2024 | 05 Jun 2024 | Harumi Shibata Salazar ¦ shibata@un.org | The workshop is organized jointly by UN ESCWA, AITRS (Arab Institute for Training and Research in Statistic), LAS (League of Arab States) and UNSD and is planned to take place in Cairo, Egypt, on 3-5 June 2024 (3 days). A pre-workshop meeting will be held on 2 June 2024 to test the materials in the venue and final coordination for the event. The Workshop will bring together statisticians and IT specialists from various national statistical offices in the Arab region. / This workshop is a continuation of UNSD and ESCWAâ€™s work to improve and strengthen the SDMX skills of Member States on SDG data reporting and to implement SDMX at the national level. As requested by Member States in the region, the training will cover advanced SDMX topics and provide in-depth hands on exercises with the aim to introduce SDMX tools to enable the automation of data and metadata exchange between entities. It will employ a variety of tools including presentations, hands-on exercises, and the sharing of good practices and challenges by countries through discussions and presentations. |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| 3860 | Request #3860 ? This initiative aims to strengthen UNRC/UNCT capacities for / the analyses of transboundary economic risks, economic / transformation, debt management and fiscal issues reflected / in CCAs in selected countries. It will leverage DESAâ€™s / analytical tools and products - including economic forecasting / and policy messages of the World Economic Situation / Prospects (WESP) and the World Social Report (WSR) - and / the regional outlooks and analyses produced by the UN / Regional Commissions (RECs) to strengthen macroeconomic / analyses relevant for CCAs. The analyses of the socioeconomic / impact of COVID-19 conducted by both DESA and / RECs will also be a major input to this effort. / The overall goal is to support the UNRC/UNCT to effectively / use and translate global and regional economic outlooks and / risks to develop country specific policy guidance. DESA will / work in partnership with interested RECs to deploy respective / knowledge, expertise and analytical capacities first to support / the RC/UNCT in the selected countries and then to scale up / support to other countries across regions. | Completed | Economic Analysis and Policy Division | 07 May 2020 |  |  | Monica Noagara ¦ noagara@un.org | This initiative aims to strengthen UNRC/UNCT capacities for / the analyses of transboundary economic risks, economic / transformation, debt management and fiscal issues reflected / in CCAs in selected countries. It will leverage DESAâ€™s / analytical tools and products - including economic forecasting / and policy messages of the World Economic Situation / Prospects (WESP) and the World Social Report (WSR) - and / the regional outlooks and analyses produced by the UN / Regional Commissions (RECs) to strengthen macroeconomic / analyses relevant for CCAs. The analyses of the socioeconomic / impact of COVID-19 conducted by both DESA and / RECs will also be a major input to this effort. / The overall goal is to support the UNRC/UNCT to effectively / use and translate global and regional economic outlooks and / risks to develop country specific policy guidance. DESA will / work in partnership with interested RECs to deploy respective / knowledge, expertise and analytical capacities first to support / the RC/UNCT in the selected countries and then to scale up / support to other countries across regions. |  |
| 3584 | Request #3584 ? Support the preparation of the CCA and longer-term partnership to strengthen the UNCT capacity to engage the Government counterparts and development partners on the national macroeconomic dialogue in Jordan. The RC also requested DESA collaboration together with ESCWA in the preparation of the socio-economic impact assessment of COVID-19 that took over the preparation of the CCA. | Completed | Economic Analysis and Policy Division | 02 Feb 2020 | 01 Mar 2020 | 30 Jun 2021 | Anders Pedersen ¦ anders.pedersen@un.org | Support the preparation of the CCA and longer-term partnership to strengthen the UNCT capacity to engage the Government counterparts and development partners on the national macroeconomic dialogue in Jordan. The RC also requested DESA collaboration together with ESCWA in the preparation of the socio-economic impact assessment of COVID-19 that took over the preparation of the CCA. |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001375.99.40 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | OISC | 30 Jun 2026 | 30 Jun 2026 | $114,966 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001376.99.99.31 | Securing the Future of Demographic and Health Data: Country Pathways and a Global Blueprint / | SD | 30 Sept 2026 | 31 Dec 2026 | $86,714 | Bangladesh, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Jordan, Kenya, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Papua New Guinea, Senegal, Tajikistan | Region standardized: 'global' -> 'Global'. |  |
| SB-001376.99.99.16 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | SD | 30 Jun 2026 | 30 Jun 2026 | $6,578 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001376.99.99.24 | International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity¦¦International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity | SD | 30 Sept 2026 | 30 Sept 2026 | $50,630 | Ghana, Indonesia, Jordan, Lao People's Democratic Republic, Lesotho, Madagascar, Philippines, Viet Nam | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. / Proposal past due |
| SB-001376.99.99.35 | 13th SDMx Experts Workshop | SD | 30 Jun 2026 | 30 Jun 2026 | $30,081 | Cameroon, Iraq, Jordan, Kenya, Tajikistan, Thailand | Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001375.99.50 | 2027 Global Sustainable Development Report (GSDR) the Northern Africa and Western Asia Region Consultation, Cairo, Egypt, 15–16 Dec. 2026 / | DSDG | 31 Dec 2026 | 31 Dec 2026 | $68,897 | Algeria, Egypt, Greece, Iraq, Jordan, Kuwait, Lebanon, Morocco, Oman, United Arab Emirates, Yemen |  | proposals.xlsx record 'SB-001375.99.50¦row:70': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001375.99.50¦row:70': 'f_cashOther' has non-numeric value 'N/A'. |
| SB-001375.99.44 | Implementing the Capacity Development Initiative for SDG 6 | DSDG | 30 Jun 2026 | 31 Dec 2026 | $43,788 | Costa Rica, Jordan, Nigeria, Panama, Rwanda | Region standardized: 'global' -> 'Global'. |  |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women |
| --- | --- | --- | --- | --- | --- | --- | --- |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002309088 - Jordan | 0002309088 | Past | Jordan |  | STATISTICS DIVISION | MEETING CENSUS PALESTINE |  | 26 Jun 2026 | 02 Jul 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts | 2013 | PD | Argentina, China, Egypt, El Salvador, Jordan, Korea, State of Palestine, Thailand, Türkiye | - Stimulate beneficiary countries to become active members of the NTA international network. / - Organize follow-up activities on applying NTA to analyzing currently relevant policy issues. / - Produce country briefs based on current empirical work. / - Raise extra funding to support empirical work and avoid the risk that national reports represent a one-off activity. / - Make training workshops an essential, though separate, part of international conferences organized by the NTA Working Group. / - Tailor workshops on NTA basics to separately address demographic, macroeconomic, microeconomic, and national accounts issues; offer some training in e-learning and online formats. / - Organize training on how to use results for policy recommendations, specifically through policy research workshops. / - Train staff to write short and clear reports aimed at fostering knowledge about the life-cycle economy and the economic and financial consequences of ageing. / - Translate the NTA Manual into other languages such as Spanish, Arabic, and Chinese. / - Integrate NTA more closely with SNA and increase its visibility in the workplans of international organizations; assess possible collaboration with organizations such as OECD and Eurostat. / - Consider estimating separate sectorial NTAs to account for heterogeneity in economic sectors within developing countries. / - Supplement cohort analysis with gender analysis by implementing National Time Transfer Accounts (NTTA) more widely. | - Demographic changes affect all countries, but awareness and institutional capacity to address them vary, especially in developing countries. / - NTA provides a powerful analytical tool for understanding the age and generational dimension of the economy, but its implementation requires significant investment in human capital and institutional capacity. / - Effectiveness and sustainability of NTA depend on the ability to estimate NTAs, interpret data for policy analysis, and communicate implications to policymakers and the public. / - Most participating countries have adequate statistical data for NTA, but challenges remain in mastering new concepts and improving data quality. / - Future training should focus on developing the capacity to interpret NTA data and derive policy recommendations, which is essential for raising awareness among policymakers. / - Clear communication of NTA results to policymakers is crucial, given the technical complexity of the issues. / - The international NTA network enhances project resilience and sustainability by supporting capacity development and facilitating expert identification. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/PD/ROA-167-lNational Transfer Accounts/Progress Reports/EVALUATION REPORT_ns final_24 Jul 2013.pdf | Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Turkey' -> 'Türkiye'. | evaluations.xlsx rows 100 (archived) and 46 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Terminal Evaluation of Project (Final Report) DA13 INFF Project 2124A ‘Towards Integrated National Financing Framework’ | 2025 | FSDO; EAPD | Belarus, Burkina Faso, Costa Rica, Dominican Republic, Egypt, Jordan, Kyrgyzstan, Pakistan, Samoa, Zambia | - Project conceptualisation should be preceded by a scoping session and/or planning meeting between the executing entities and the cooperating entities, to establish synergies, enhance relevance, and minimise risk, including the possibility for and perception of duplicated efforts. / - Clarified roles and responsibilities at the level of project management and activity coordination should be established to allow for efficient oversight throughout the implementation timeframe. / - Guidance documents on the INFF methodology should provide detailed, step-by-step guidelines that can be easily contextualised by the implementing country. / - The FINS project should be scaled up to provide post-project technical assistance to target and non-target countries in response to their requests for context-specific support for INFF implementation. / - A strengthening of the process for finalising and approving the project results framework should be initiated, to ensure that appropriate results targets and performance measurement indicators are established to increase the usefulness of achieved results. | - The project development phase needs to be reliably informed by a detailed assessment of risk, parallel interventions, and the contextual situation in the countries of intervention focus. / - Efficient project oversight is dependent on a clarified overview of roles and responsibilities at the level of project management. / - The effective application of the INFF methodology at the country-level requires detailed step-by-step guidelines to inform contextualisation. / - The ownership of the INFF methodology by national political leadership contributes towards a demand-driven process that is critical for effective implementation. / - A flexible design combined with strategic partnerships contributes towards stronger impact and the maximisation of efficiency and synergies. / - Digital platforms and data infrastructure support effective implementation and enhance knowledge-exchange and sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/2124A SB-016729.01 INFF/Evaluation report/REVISED Final Evaluation Report_INFF Evaluation_7OCT2025.docx |  |  |
| Enhancing Key Statistics and Indicators to Monitor Progress Towards the Millennium Development Goals and Other Internationally Agreed Development Goals | 2014 | UNSD | Brazil, Bulgaria, Jordan, Philippines, Romania, Russian Federation, Tunisia, Ukraine | - DA projects should be designed region by region and a steering committee should be setup to support management and supervision of project activities. / - DESA/SD should work with Regional Commissions and countries to increase women’s participation in future events. / - DESA/SD should ensure that potential users are aware of the Data Dissemination and Communication Knowledge Base by introducing it at meetings and workshops and featuring it prominently on the DESA/SD website. / - DESA/SD should consider establishing a City Group or similar arrangement on Data Dissemination and Communication. / - Updating the Knowledge Base should be a collaborative effort between DESA/SD, countries, and regional and international organizations. / - Statistical offices should consider syndicating content to media and news websites to reach a wider audience. / - Strategies for web-based data dissemination should consider different types of users, including those who want to access raw data to build their own interfaces. / - Countries should integrate statistical and geospatial information for dissemination and communication. / - Statistical offices should have staff trained in communication and the use of new technologies. | - Workshops served well as fora for sharing knowledge and exchange of experience, but future workshops would benefit from a more homogenous group of participants. / - Resource persons from DESA/SD, Regional Commissions, UN specialized agencies, and others contributed to the success of the workshops. / - The involvement of Regional Commissions and UN agencies contributed to the success and sustainability of the project outcomes. / - The Data Dissemination and Communication Knowledge Base was an outcome of collaborative work, which is a useful and cost-saving mechanism for similar future endeavors. / - The project was successful in strengthening the regional network of statisticians, increasing intra-regional statistical cooperation, and raising the national profile of statistics. / - The absence of a steering committee weakened implementation and monitoring; such committees are important for project duration and for institutionalizing activities after project completion. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 166 - 7th tranche - Enhancing Stats and Indic to monitor prog Agreed Dev Goals/DA Project Final Eval Rep June30, 2014.docx | Country standardized: 'Russia' -> 'Russian Federation'. |  |
| Realizing the Millennium Development Goals through socially inclusive macroeconomic policies | 2011 | DPAD | Egypt, Indonesia, Jordan, Kyrgyzstan, Morocco, Philippines, Senegal, South Africa, Tunisia, Uganda, Uzbekistan, Yemen | - Create a pool of potential national experts for future projects and consider contracting international experts to work closely with government officials. / - Strengthen the relationship between consultants, government officers, and UNDP country offices to ensure effective project implementation and appropriation of results. / - Increase the number of national and regional workshops, and emphasize the importance of national workshops for institutional arrangements and capacity building. / - Provide additional training and support to government staff to enable full use and institutionalization of the modeling framework. / - Develop a more user-friendly interface for the model to enhance usability for policy makers. / - Ensure better communication and collaboration between UNDP and partner institutions, especially at the country level. / - Schedule workshops and events well in advance to allow key participants to allocate time for participation. / - Enhance capacity building of local experts and national partners to increase the effectiveness and sustainability of the project. | - Careful selection of countries is crucial for project relevance and success. / - Selecting and forming national expert teams can be challenging due to limited local technical capacity, which may cause delays and affect project outcomes. / - High turnover among government staff can hinder institutionalization of project achievements. / - A close relationship between consultants, government agencies, and UNDP offices is essential for project success and appropriation of results. / - Both regional and national workshops are important for building institutional arrangements and capacity. / - Limited staff resources at the implementing division can slow down project progress and implementation. / - Early selection of a pool of country team members can help mitigate delays and negative effects from staff turnover. / - National trainings are crucial for generating necessary capacity at the country level and for transferring knowledge to stakeholders. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/5th tranche/ROA 87/ROA 87 - Terminal and Evaluation reports.pdf |  |  |
| Accelerating implementation of Data for Now in eight countries in Africa and Asia | 2025 | UNSD | Ethiopia, Jordan, Morocco, Sierra Leone, Tunisia, Viet Nam | - Leverage a wide range of paths to produce desired effects, such as capacity building, increased interactions, and production of better indicators, instead of targeting isolated actions; encourage positioning local resources at country-level to foster coordination and holistic change; place greater emphasis on raising awareness on IT implications of mobilising new techniques. / - Adopt a more structured, wide and long-term approach to capacity building, including clear training plans, performance monitoring, and milestones; ensure training accommodates local realities, particularly language arrangements; use tools like the Statistical Training needs Assessment Tool to streamline structured capacity building. / - During assessment and prioritisation, provide more information on prerequisites for specific innovative techniques, such as access to data, required skills, IT capacities, and potential for application to new areas, to help countries determine the most applicable tools and methods. / - Offer guidance and documentation on optimal organisational and institutional arrangements between NSOs and NSS members, such as exposure to success stories, inspiration workshops, peer reviews, and production of guidelines and methodological frameworks. / - Adopt a 'sandboxing' approach by creating an environment where participants can test new approaches and gain knowledge on innovative methods; this environment should be freely accessible, use open-source services, and complement the production-ready approach. / - Compile a deck of innovative use cases to present project actions in a standardised way, including policy issues, prerequisites, steps, tools, challenges, mitigation strategies, achievements, and testimonies; make resources available on a freely accessible repository along with notebooks, code, and training resources. / - Develop a stronger monitoring and evaluation framework to better capture, in real time, effects and impact generated by the project, including more comprehensive indicators, indicator sheets, and data collection and analysis plans; consider evaluation exercises on the D4N initiative as a whole for more holistic insights. | - Country ownership drives sustainability; countries actively involved in setting priorities and tailoring training content demonstrate higher engagement and a stronger likelihood of sustaining outcomes. / - Tailored technical support yields better results; countries benefit most when technical assistance responds directly to their needs and existing capacities. / - Flexible project design supports responsiveness; the ability to adapt plans in response to emerging needs or challenges is a major strength. / - Strategic partnerships enhance impact; collaboration with international organisations and academic experts brings high-quality, context-specific support and avoids duplication of efforts. / - Dedicated focal points improve coordination; appointing national coordinators or focal persons leads to better planning, faster response times, and improved follow-up. / - Peer learning can accelerate progress; structured opportunities for cross-country experience sharing enable participants to learn from peers’ successes and challenges. / - Monitoring and evaluation mechanisms should be embedded early; a robust M&E system from the start facilitates evidence-based learning and decision-making throughout the project lifecycle. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Active Projects/4 UNSD/D4N M1-60 SB-020332 ITALY/Evaluation/D4N - evaluation report.pdf | Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level | 2015 | UNSD | Algeria, Argentina, Bangladesh, Bolivia (Plurinational State of), Botswana, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Chile, Costa Rica, Côte d’Ivoire, Ecuador, Egypt, Ethiopia, Guyana, Jordan, Kenya, Korea, Lebanon, Madagascar, Morocco, Nigeria, South Africa, State of Palestine, Sudan, Togo, Tunisia, Uganda, Uruguay | - Create conditions to improve the technological and knowledge transfer from developed to developing countries. / - Widely promote the adoption of internationally accepted standards related to the generation, process, dissemination and use of geospatial information, created by major standards organizations such as ISO/TC211, OGC, and IHO. / - Include the integration of statistical and geospatial information as a core issue in the UN-GGIM plan work for developing countries, especially in support of the 2020 Round of Censuses and Big Data. / - Continue the work with support of the regional committees of UN-GGIM and the countries themselves to encourage the building of spatial data infrastructures. / - Raise the awareness of the importance of geospatial information at the policy and decision making levels, and strengthen human capacities in developing countries through comprehensive trainings on geodesy, cartography, remote sensing, GIS, and geostatistical mapping. | - The Steering Committee and UNSD/DESA played an important role in aligning the deliveries of the project. / - UNSD/DESA-led projects are effective in connecting experts with organizations and countries interested in geospatial knowledge. / - At a global level, only an organization such as the UN through UNSD/DESA has the capacity to convene and lead projects of this magnitude. / - Developing countries need to increase their technological capacities, which requires more financial resources. / - Improving geospatial information management requires the creation of policies, rules, and methods for information generation, management, dissemination, and use. / - Increasing awareness and support for geospatial and statistical activities among high-level politicians and decision makers is necessary. / - Specialized human resources training is essential for functional geospatial information, beyond just technical, financial, and methodological resources. / - The information exchange mechanism used in this project was effective, allowing developing countries to learn from best practices. / - Institutional coordination between geospatial and statistical offices is still a work in progress and needs to be strengthened. / - Significant gaps in geospatial data and infrastructure exist in developing countries, and this project has helped indicate the right direction. / - There is a lack of economic resources to keep information updated in some developing countries. / - Technological capacities related to geospatial information need to be upgraded. / - There is still a lack of policies, rules, and methods for geospatial information management in some developing countries. / - Specialized human resources training in geospatial disciplines and statistics is essential. / - Strong efforts are needed to create and maintain spatial data infrastructures at all levels, considering the Global Geodetic Reference Frame. / - Awareness and support for geospatial and statistical activities from high-level decision makers need improvement. / - The 2030 Sustainable Development agenda and the 2020 Round of Censuses should be leveraged to reinforce the use of geospatial and statistical data, with executional and follow-up mechanisms for expected outcomes. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 212 - 8th tranche - Geospatial/Evaluation report/Evaluation Report- DA Project-212-8.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Cote d’Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Monitoring and reporting on sustainable development objectives, goals and targets: enhancing institutional capability in selected developing countries | 2018 | DSDG; UNSD | Belize, Colombia, Ethiopia, Honduras, Jordan | - Proceed with group training workshops at the regional level, in combination with E-learning as a complementary tool, due to resource constraints and language challenges. / - Enforce a pre-training selection of national participants with at least some basic knowledge of strategic planning and management, and allocate a longer period of time to the Training of Trainers (ToT). / - Extend the Training Curriculum beyond the pilot countries, translate it into other languages, and revise future versions to be more practical and action-oriented with concrete case studies, especially for local level planning. / - Disseminate the Training Curriculum by involving universities and other institutions in as many countries as possible to broaden its reach and impact. / - Scale up the activities of the project, such as RBM learning, to involve more officials and the right drivers in each country, and consider using a website or E-learning platform for wider dissemination. / - Involve the National Statistical Office (NSO) at an early stage and strengthen or modernize the national statistical system to improve provision, access to, and use of quality data and related technologies for SDG indicators. / - Take into account the geographic dimension of data and related geospatial information and earth observations in future projects, and collaborate with UNSD to streamline UN support for strengthening countries' information infrastructures and statistical systems. / - Increase focus on domestic resource mobilization and build partnerships with the private sector and other stakeholders within the country to support project performance and outcomes. / - Encourage countries to proactively seek counter-part funding and additional support from other donors for project activities. / - Reinforce cooperation with UN agencies and UN-DESA, and continue collaborative work with UN Country Teams and UN Regional Commissions to address challenges effectively. | - Developing country-specific implementation workplans based on capacity assessments was crucial for refining project objectives and ensuring successful execution. / - The Training Curriculum on Results-Based Management (RBM), supplemented by a facilitator manual in three languages, was highly informative and provided valuable guidance for planning, implementation, and monitoring of the SDGs. / - The International ToT Workshop was effective for sharing the curriculum widely and demonstrated the value of tailoring tools and methods to local contexts. / - Learning RBM methodology requires participants to have some basic knowledge in strategic planning and management; its application to SDGs is most effective when carried out by well-trained key representatives from government departments. / - Applying RBM at the local level requires data disaggregation by location and the collection, processing, analysis, and dissemination of large amounts of data from both official and innovative sources. / - Strong support and commitment from high-level decision makers, engagement of government departments, and involvement of all stakeholders, including civil society, private sector, and academia, are crucial for successful domestic implementation of SDGs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DSDG/ROA 265-SB-001292-1415I- 9th tranche_Monitoring and reporting on SD objectives/Evaluation/Final Evaluation Report- DA 1415I.docx |  |  |
| Realizing the Millennium Development Goals through Socially-Inclusive Macroeconomic Policies | 2011 | DPAD | Egypt, Jordan, Kyrgyzstan, Morocco, Philippines, Senegal, South Africa, Tunisia, Uganda, Uzbekistan, Yemen | - Maintain close collaboration between UN agencies and the World Bank for project success and consider this approach for future projects. / - Establish a pool of potential experts to support implementation and provide flexibility for international experts to assist countries lacking national expertise. / - Identify institutions with close government relations to facilitate model appropriation by policy makers. / - Organize national workshops with participation from various government agencies to support appropriation of project results. / - Provide continuous and institutionalized technical assistance, not just one-off support, to ensure sustainability and capacity development. / - Increase the number of professionals in the DPAD/DESA team to address data availability issues and accelerate project implementation. | - Careful selection of participating countries is crucial for project success; relevance of the topic in selected countries should be ensured. / - Selection of national experts is critical; lack of local technical capabilities can delay or jeopardize country projects. / - High turnover among government staff can hinder institutionalization of project achievements; having a committed country counterpart is important. / - A strong relationship between consultants, government agencies, and UNDP offices is essential for project effectiveness and appropriation of results. / - Both regional and national workshops are important; national workshops strengthen institutional arrangements and support sustainability. / - Limited staff in DPAD/DESA can slow project progress; more professionals would help address challenges such as data availability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/5th tranche/ROA 87/External evaluation Report Final 032411.docx |  |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx rows 100 (archived) and 46 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 2 | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 3 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 4 | proposals.xlsx record 'SB-001375.99.50¦row:70': 'f_cashGov' has non-numeric value 'N/A'. |
| 5 | proposals.xlsx record 'SB-001375.99.50¦row:70': 'f_cashOther' has non-numeric value 'N/A'. |
| 6 | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. |
| 7 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 8 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 9 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 10 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 11 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 12 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 13 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 39 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 40 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 41 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 42 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 43 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 44 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 45 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 46 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 53 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |