Madagascar

Africa | LDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Madagascar is presented in this country card as part of Africa, with Madagascar also associated with an unspecified subregion and the LDC grouping. The filtered data for Madagascar highlights 4 projects for Madagascar, including 2 active or planned projects for Madagascar and 2 completed or closed projects for Madagascar.

For Madagascar, the report includes 13 requests for Madagascar, 3 RPTC proposals for Madagascar, 1 RPTC activities for Madagascar, and 0 travel records for Madagascar. Financially, Madagascar shows USD 7,053,004 in project budget, $121,117 in proposal planned budget, and $6,688 in consumed RPTC activity budget for Madagascar.

The main organizational coverage for Madagascar points to Division for Inclusive Social Development, Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, FSDO. Activity records for Madagascar list 1,299 participants, including 665 women participants, the current quality review for Madagascar includes 66 data quality notes. Current highlights for Madagascar include a request focus for Madagascar: Request #5516 ? This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses.; an RPTC proposal focus for Madagascar: United Nations Regional Workshop on the 2030 World Programme on Population and Housing Censuses for Francophone Africa: International Standards and Innovative Approaches
; an activity focus for Madagascar: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 4 |
| Project budget | USD 7,053,004 |
| Requests | 13 |
| RPTC proposals | 3 |
| Proposal planned budget | $121,117 |
| RPTC activities | 1 |
| Consumed RPTC budget | $6,688 |
| Activity participants | 1,299 |
| Women participants | 665 |
| Travel records | 0 |
| Evaluations | 7 |
| Data quality notes | 66 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment | 2017-01 | country | Division for Sustainable Development Goals | Closed | 01 May 2017 | 31 Dec 2021 | USD 2,300,000 | Central African Republic, Lao People's Democratic Republic, Madagascar, Nepal, Nigeria, Papua New Guinea | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment ¦ 2017-05-01T00:00:00 ¦ 2017-01': Country text 'Melanesia' could not be matched; no country assignment was inferred. / projects.csv record 'Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment ¦ 2017-05-01T00:00:00 ¦ 2017-01': Country/Sub region 'Melanesia' was not matched to GeoData and was ignored. |
| Promoting a socially inclusive creative economy to support the digital transformation needs of small island developing States and the least developed countries | 2629D | country | Division for Inclusive Social Development | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 640,000 | Botswana, Democratic Republic of Timor-Leste, Indonesia, Madagascar | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| Strengthening capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao Technology and analysing and disseminating best practices and lessons learned for alleviating poverty, and promoting productive employment | PDF-SDG-2020-01 | country | Division for Sustainable Development Goals | Active | 01 Jul 2021 | 30 Jun 2025 | USD 2,450,000 | Central African Republic, China, Lao People's Democratic Republic, Madagascar, Papua New Guinea, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening national capacities for enhancing MSME resilience and building forward better to accelerate the implementation of the 2030 Agenda in developing countries participating in the Belt and Road Initiative | PDF-SDG-2021-01 | country | Division for Sustainable Development Goals | Closed | 01 Jan 2021 | 31 Dec 2024 | USD 1,663,004 | Cambodia, Democratic Socialist Republic of Sri Lanka, Ethiopia, Gambia, Kenya, Lao People's Democratic Republic, Madagascar, Philippines, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5516 | Request #5516 ? This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Completed | Statistics Division | 14 May 2026 | 15 Jun 2026 | 19 Jun 2026 | Seiffe Tadesse ¦ tadesse5@un.org | This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5512 | Request #5512 ? There is an increased demand for the compilation of ecosystem accounts and indicators in support of national policies and international reporting, such as climate change and biodiversity in many countries. The statistical office of Madagascar requested assistance to enhance capacity for developing environmental accounts and statistics, following the annual assessment of how countries implement the system of environmental economic accounting (SEEA). | Under consideration | Statistics Division | 27 Oct 2025 | 01 Jun 2026 | 31 Dec 2026 | RAVOLOLONIRINA Hanta ¦ hantatia1@gmail.com | There is an increased demand for the compilation of ecosystem accounts and indicators in support of national policies and international reporting, such as climate change and biodiversity in many countries. The statistical office of Madagascar requested assistance to enhance capacity for developing environmental accounts and statistics, following the annual assessment of how countries implement the system of environmental economic accounting (SEEA). |  |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5235 | Request #5235 ? The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Under consideration | Statistics Division | 11 Jun 2025 | 11 Jun 2025 | 05 Dec 2025 | Matthias Reister ¦ reister@un.org | The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5168 | Request #5168 ? Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. | Completed | Statistics Division | 17 Jan 2025 | 1 | 1 | Deepchandsingh Jagai ¦ djagai@sadc.int | Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. |  |  |
| 4939 | Request #4939 ? 1. Policy advisory support within the realm of waste management, development of a framework for food waste to biogas production - whereby, simultaneously addressing issues of renewable energy and waste management, the digitalization and the energy autonomy of a sustainable and accountable public administration- as well as the eventual assistance with ODA requests to support construction of the necessary infrastructure. / 2. Interest in collaborating with UNOSD on the forthcoming Policy Support System (PSS) on Waste Management and for Madagascar to act as a Regional Hub Country in order to strengthen national policy, data and planning for waste and the circular economy. | Ongoing | Division for Sustainable Development Goals | 22 Feb 2024 | 01 Apr 2024 | 31 Dec 2026 | Mr. Max Fontaine Andonirina ¦ soministre@environnement.mg | 1. Policy advisory support within the realm of waste management, development of a framework for food waste to biogas production - whereby, simultaneously addressing issues of renewable energy and waste management, the digitalization and the energy autonomy of a sustainable and accountable public administration- as well as the eventual assistance with ODA requests to support construction of the necessary infrastructure. / 2. Interest in collaborating with UNOSD on the forthcoming Policy Support System (PSS) on Waste Management and for Madagascar to act as a Regional Hub Country in order to strengthen national policy, data and planning for waste and the circular economy. |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 3986 | Request #3986 ? This is to request the approval of a RPTC activity proposal for 2021 on producing training materials on Evidence-based Voluntary National Reviews (VNRs) and on data storytelling for SDGs. The activity includes two components: (a) finalizing Practical Guide for Evidence-based Voluntary National Reviews; and (b) developing guidance and training materials on data storytelling for SDGs. / The proposal has been developed to respond to the demand from many countries on the need for technical support for monitoring and capacity building for VNRs and on communicating data and data visualizations in VNRs and SDG reporting and engaging data users. RPTC funds would be used to support the production of guidance training materials, with the support of 2 consultants, who will be working closely with UNSD. / Please kindly see the following documents for your approval on using 2021 RPTC fund to produce training materials on VNRs and data storytelling for SDGs. / - Draft memo / - Annex 2 project proposal, / - Draft ToR for a consultant to finalizing Practical Guide for Evidence-based VNRs / - Draft ToR for a consultant to develop guidance and training on data storytelling / - Written statements from countries in support of the work on capacity building for VNRs and SDG monitoring | Completed | Statistics Division | 27 Sept 2021 |  | 30 Dec 2022 | Yongyi Min ¦ min3@un.org | This is to request the approval of a RPTC activity proposal for 2021 on producing training materials on Evidence-based Voluntary National Reviews (VNRs) and on data storytelling for SDGs. The activity includes two components: (a) finalizing Practical Guide for Evidence-based Voluntary National Reviews; and (b) developing guidance and training materials on data storytelling for SDGs. / The proposal has been developed to respond to the demand from many countries on the need for technical support for monitoring and capacity building for VNRs and on communicating data and data visualizations in VNRs and SDG reporting and engaging data users. RPTC funds would be used to support the production of guidance training materials, with the support of 2 consultants, who will be working closely with UNSD. / Please kindly see the following documents for your approval on using 2021 RPTC fund to produce training materials on VNRs and data storytelling for SDGs. / - Draft memo / - Annex 2 project proposal, / - Draft ToR for a consultant to finalizing Practical Guide for Evidence-based VNRs / - Draft ToR for a consultant to develop guidance and training on data storytelling / - Written statements from countries in support of the work on capacity building for VNRs and SDG monitoring |  |  |
| 3654 | Request #3654 ? The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" | Completed | Division for Public Institutions and Digital Government | 16 Feb 2021 | 11 Nov 2021 | 25 Nov 2021 | Jan Magoro ¦ JanMa@presidency.gov.za | The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" |  |  |
| 3526 | Request #3526 ? The governments of these eight countries expressed interest in participating in a potential project on MSMEs. The Government of Zimbabwe requested to be added to the list of target countries. Request number 3959 refers. | Completed | Division for Sustainable Development Goals | 01 Feb 2021 | 01 Jan 2022 | 31 Dec 2025 | various ¦ var@var.var | The governments of these eight countries expressed interest in participating in a potential project on MSMEs. The Government of Zimbabwe requested to be added to the list of target countries. Request number 3959 refers. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 2744 | Request #2744 ? Capacity Building in designing a project proposal on sustainable forest managment | Completed | United Nations Forum on Forest | 17 Nov 2018 |  |  | Jean De Dieu Benjamin ¦ ly1maniraka@yahoo.fr | Capacity Building in designing a project proposal on sustainable forest managment |  |  |
| 2648 | Request #2648 ? DPIDG/ UNPOG was requested by the National Bureau of Administration of Risks and Disasters (BNGRC) of the Government of Madagascar to provide a training on technologies for disaster risk reduction. In addition, the country also requested support on local participatory governance models, integrated financing models for the SDGs-Climate Change-DRR, as well as on monitoring and evaluation of the Sendai Framework as an outcome of the August 2018 Island States Forum in Sri Lanka. | Completed | Division for Public Institutions and Digital Government | 07 Aug 2018 | 27 Mar 2019 |  | na ¦ na@gmail.com | DPIDG/ UNPOG was requested by the National Bureau of Administration of Risks and Disasters (BNGRC) of the Government of Madagascar to provide a training on technologies for disaster risk reduction. In addition, the country also requested support on local participatory governance models, integrated financing models for the SDGs-Climate Change-DRR, as well as on monitoring and evaluation of the Sendai Framework as an outcome of the August 2018 Island States Forum in Sri Lanka. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.21 | United Nations Regional Workshop on the 2030 World Programme on Population and Housing Censuses for Francophone Africa: International Standards and Innovative Approaches / | SD | 30 Jun 2026 | 30 Jun 2026 | $45,487 | Algeria, Angola, Benin, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Equatorial Guinea, Gabon, Guinea, Guinea-Bissau, Madagascar, Mali, Mauritania, Morocco, Niger, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Togo, Tunisia | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. | Proposal past due |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001376.99.99.24 | International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity¦¦International Training Workshop on SEEA Ecosystem Accounting for Climate Change and Biodiversity | SD | 30 Sept 2026 | 30 Sept 2026 | $50,630 | Ghana, Indonesia, Jordan, Lao People's Democratic Republic, Lesotho, Madagascar, Philippines, Viet Nam | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. / Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment | 2021 | DSDG | Central African Republic, Lao People's Democratic Republic, Madagascar, Papua New Guinea, United Republic of Tanzania | - Harmonize the perceptions of different stakeholders about the project’s contribution to the SDGs and consider explicitly linking the project indicators to the relevant targets of specific SDGs. / - Formalize intra-institutional partnership between key participating parties (e.g., UNDESA, FAFU, and local partners) and incorporate detailed monitoring and reporting functions and responsibilities into the formal agreement. / - Consider developing an impact evaluation to address the effect of Juncao technology across different variables (e.g., the impact of the technology on poverty reduction and income generation, food security, and land restoration in the targeted communities). / - Strengthen the project's internal monitoring and evaluation scheme to allow better reporting on the results achieved as the project is scaled up and plays a more crucial role in increasing the visibility and promotion of Juncao technology and its contribution to achieving the SDGs. / - Elaborate gender-responsive S.M.A.R.T. performance indicators focused on both outputs and outcomes of the project. / - Elaborate S.M.A.R.T. indicators related to people in vulnerable situations to crystalize the project’s focus on the above groups, which might be useful for impact analysis as well. / - Develop a project monitoring and evaluation plan to assess the mixed results of both capacity-building interventions and technical assistance/advisory services. / - Gather data to assess the capacity-building activities across the Kirkpatrick Four-Level Training Evaluation Model. / - Continue proactive engagement of the UN Resident Coordinators and the relevant staff of other UN entities and international organizations into high-level regional and intergovernmental meetings to increase the visibility of Juncao technology and the project. / - Diversify the network of local partners and engage more non-state actors (including agriculture extension centers and educational institutions) as local partners of the project to acquire the knowledge and transfer it further. / - Continue focusing on multiple platforms for knowledge-sharing to cover face-to-face and virtual capacity building. It is advised to organize capacity-building workshops in regional centers (instead of remote areas) which offer better coverage and accessibility. / - Develop incentive schemes for the impoverished groups to enable/encourage them to travel to the Juncao demonstration sites and capacity-building workshops and improve their access to the internet. | - The design and implementation of the Juncao project were highly relevant to the needs and priorities of the targeted developing countries and direct beneficiaries, and fully aligned with the mission of UNDESA to support Member States in achieving the 2030 Agenda for Sustainable Development. / - The project lacked an exclusive focus on women, youth, and marginalized groups, which could be explained by the broader strategic mission to promote social, economic, and political inclusion through interventions at grassroots and policy levels. / - The Juncao project is distinctive as it was the first project implemented by the UN jointly with the Government of the People’s Republic of China and the intellectual property rights owner, Fujian Agriculture and Forestry University. / - Proactive involvement of the UN Resident Coordinators ensured increasing visibility and advanced promotion of the project among national stakeholders and state sector representatives. / - A mixed-method approach, combining theoretical and practical knowledge, and a mixture of top-down and bottom-up approaches, ensured alignment of the project’s implementation strategy with its objectives and expected accomplishments. / - The project indicators were not compatible with the S.M.A.R.T. framework and lacked specificity to track progress on important variables such as impact on people in vulnerable situations, gender equality, and job creation. / - The unique nature of the project partnership arrangement delayed the commencement of country-level advisory services, and the COVID-19 pandemic forced the project team to provide virtual/online solutions or postpone activities. / - The sustainability strategy demonstrated positive outcomes and overall ownership and commitment at the national level, but also showed vulnerability to external factors and dependency on the state sector. / - The project incentivized both national governments and the private sector to scale up and replicate results, but both lack the financial and human resources capacity to expand without external support or investment. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2017-01_Eval_DESA_17Jan22.docx | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx rows 216 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 249 (archived) and 2 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 55 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening national capacities for enhancing Micro-, Small and Medium -sized Enterprise (MSME) resilience and building forward better to accelerate the implementation of the 2030 agenda in developing countries participating in the Belt and Road Initiative | 2025 | DSDG | Cambodia, Democratic Socialist Republic of Sri Lanka, Ethiopia, Gambia, Kenya, Lao People's Democratic Republic, Madagascar, Philippines, Zimbabwe | - Prioritise policy engagement as the primary pathway to scale by supporting policy development and implementation, using entrepreneurs as informants and validators, and convening joint forums for policymakers and entrepreneurs. / - Support the operationalisation of draft policy products by maintaining engagement with national counterparts beyond drafting, providing targeted technical or coordination support, and tracking the status and institutionalisation of policy products. / - Align project scope with available resources and delivery capacity by ensuring ambitions are realistically matched with resources, staffing, and timeframes, and focusing on a manageable number of impactful deliverables. / - Continue leveraging UN DESA’s convening role to connect policymakers and entrepreneurs through joint forums for dialogue, training, and policy validation, ensuring inclusive multi-stakeholder workshops. / - Strengthen outcome-focused, adaptive project design and management by adopting demand-driven and flexible planning focused on meaningful outcomes and allowing adaptation to evolving partner needs. / - Strengthen indicator-based monitoring and follow-up systems by systematically tracking progress against indicators, conducting data collection at multiple points, and establishing follow-up systems for tracking engagement and uptake. | - Drafting policies is not enough—continued engagement is essential to ensure validated drafts are formally adopted and integrated into national systems. / - Convening policymakers and entrepreneurs together in joint workshops creates two-way learning, improves relevance, and increases ownership of training materials and toolkits. / - Adaptive, demand-driven capacity building tailored to country-specific needs and delivered with local partners increases satisfaction and readiness to apply lessons learned. / - Overambitious design limited delivery under constrained resources, highlighting the need to align project ambitions with available capacities and resources. / - Missed monitoring opportunities limited evidence of results, as planned monitoring tools and follow-up surveys were not consistently implemented. / - Policy work scales better than direct training of entrepreneurs, as direct capacity-building activities have limited reach compared to policy interventions that can benefit a larger number of MSMEs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2021/PDF-2021-01 DESA-DSDG/Reports/Final Report and Evaluation/MSME project DESA - evaluation report.docx | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'The Gambia' -> 'Gambia'. |  |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level | 2015 | UNSD | Algeria, Argentina, Bangladesh, Bolivia (Plurinational State of), Botswana, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Chile, Costa Rica, Côte d’Ivoire, Ecuador, Egypt, Ethiopia, Guyana, Jordan, Kenya, Korea, Lebanon, Madagascar, Morocco, Nigeria, South Africa, State of Palestine, Sudan, Togo, Tunisia, Uganda, Uruguay | - Create conditions to improve the technological and knowledge transfer from developed to developing countries. / - Widely promote the adoption of internationally accepted standards related to the generation, process, dissemination and use of geospatial information, created by major standards organizations such as ISO/TC211, OGC, and IHO. / - Include the integration of statistical and geospatial information as a core issue in the UN-GGIM plan work for developing countries, especially in support of the 2020 Round of Censuses and Big Data. / - Continue the work with support of the regional committees of UN-GGIM and the countries themselves to encourage the building of spatial data infrastructures. / - Raise the awareness of the importance of geospatial information at the policy and decision making levels, and strengthen human capacities in developing countries through comprehensive trainings on geodesy, cartography, remote sensing, GIS, and geostatistical mapping. | - The Steering Committee and UNSD/DESA played an important role in aligning the deliveries of the project. / - UNSD/DESA-led projects are effective in connecting experts with organizations and countries interested in geospatial knowledge. / - At a global level, only an organization such as the UN through UNSD/DESA has the capacity to convene and lead projects of this magnitude. / - Developing countries need to increase their technological capacities, which requires more financial resources. / - Improving geospatial information management requires the creation of policies, rules, and methods for information generation, management, dissemination, and use. / - Increasing awareness and support for geospatial and statistical activities among high-level politicians and decision makers is necessary. / - Specialized human resources training is essential for functional geospatial information, beyond just technical, financial, and methodological resources. / - The information exchange mechanism used in this project was effective, allowing developing countries to learn from best practices. / - Institutional coordination between geospatial and statistical offices is still a work in progress and needs to be strengthened. / - Significant gaps in geospatial data and infrastructure exist in developing countries, and this project has helped indicate the right direction. / - There is a lack of economic resources to keep information updated in some developing countries. / - Technological capacities related to geospatial information need to be upgraded. / - There is still a lack of policies, rules, and methods for geospatial information management in some developing countries. / - Specialized human resources training in geospatial disciplines and statistics is essential. / - Strong efforts are needed to create and maintain spatial data infrastructures at all levels, considering the Global Geodetic Reference Frame. / - Awareness and support for geospatial and statistical activities from high-level decision makers need improvement. / - The 2030 Sustainable Development agenda and the 2020 Round of Censuses should be leveraged to reinforce the use of geospatial and statistical data, with executional and follow-up mechanisms for expected outcomes. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 212 - 8th tranche - Geospatial/Evaluation report/Evaluation Report- DA Project-212-8.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Cote d’Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Mobilizing Science, Technology and Innovation in developing countries for the SDGs | 2022 | DSDG | Belgium, Brazil, Cambodia, China, Ethiopia, Ghana, India, Japan, Kenya, Korea, Madagascar, Mozambique, Myanmar, Pakistan, Philippines, Rwanda, Serbia, Thailand, Uganda, United States of America, Zambia | - DESA should ensure that projects are based on clear objectives and SMART, relevant indicators which better help measure the impact of activities. / - DESA should ensure regular and efficient monitoring throughout the project, based on thorough monitoring plans. / - DESA should ensure the continuation of the Innovation Competition and participation in the STI Forum for the winners, and develop a longer term programme of Capacity Building and support for these winners. / - DESA should build on the Capacity Building events, Study Visits, STI Roadmaps work and the Ghana Pilot Programme, which were all highly relevant to STI in developing countries. / - DESA should focus on strengthening the OLP, which currently has a low level of relevance to STI in developing countries. DESA should revisit the Independent Technical Assessment and R4D’s recent report ‘UN 2030 Connect Report’ and integrate the prototypes into the OLP. / - If the OLP and associated capacity building activities are to continue, DESA should look carefully at the human and financial resources behind the work, ensuring that there is enough capacity to deliver meaningful results. DESA should consider the financial recommendations made in the Independent Technical Assessment. Resources available must match the ambition for the work, and the level of ambition should be clarified asap. / - Any future project should include longer term support for innovators on the ground, over a period of at least a year. This could focus on the winners of Innovation Competitions. / - Any future project should build on the successes and the lessons learned of the Ghana Pilot Project, which could be scaled to other countries in partnership with R4D. / - DESA should improve the ongoing monitoring around such projects, strengthening the indicators (ensure SMART and relevant indicators) and ensuring that questionnaires are provided to participants following relevant activities (Capacity Building sessions, Study Visits etc). / - DESA should spend more time persuading and convincing partners of the value of integrating their databases with that of the OLP, in order to address the perceived incoherence with OLP partners. / - DESA and partners should consider the viability of one overarching STI project / work stream which incorporates the various streams of work being undertaken - the STI Forum, STI Roadmaps for SDGs, 2030 Connect, Capacity Building etc. The possibility of a joint funding mechanism – an STI Trust Fund – should be explored in order to reduce inefficiencies. / - DESA should allocate meaningful human resources (at least 60% of a full time role) to ensure the success of the OLP and associated Capacity Building activities. / - DESA should ensure that resources allocated to the OLP match the ambition for the OLP. / - DESA should consider allocating more funds for longer term Capacity Building support to innovators across target countries. / - DESA should consider replicating / adapting the relationship with R4D, recognising the importance of having local partners to work with local innovators. This could either be done with R4D, other relevant CSOs or UNCTs (UN Country Teams). / - DESA should ensure there is enough time available for meaningful work to be completed, avoiding last minute rushes. / - DESA should systematically work through tools like Exit strategies, succession planning and cases for financial support before the end of a project, in order to ensure sustainability, whether a project is designed to continue or not. / - DESA, with the IATT, should revisit the Independent Technical Assessment, as well as the recent recommendations by R4D for the OLP, in order to be very clear about the ambition and strategic direction of the OLP before developing the case for support. / - Given the clear mandate provided by MS for the OLP, DESA should attempt to secure a mixture of UN regular budget and voluntary/extra-budgetary funds to finance the OLP. / - DESA should ensure that capacity building activities take place over a longer period, and provide more sustained support for innovators. This should be built into the case for support. / - The UN should integrate the principle of Leave No-One Behind into all its STI related work, ensuring that it does not inadvertently enhance the digital divide. This could be done in the context of this project by offering capacity building activities in different languages, offering interpretation, and ensuring translation of the OLP. / - DESA should consider scaling up the Ghana Pilot Project into other countries, specifically the Technical Support offered to local innovators. / - DESA should build on the momentum around the STI Roadmaps for SDGs and investigate whether a coherent package of work can be built around the Roadmaps, the OLP and the capacity building activities. / - DESA and OICT should consider structuring the OLP (specifically the Search Engine) around the SDGs in order to facilitate closer linkages between STI and HR & GE. / - DESA, and the UN more widely, should strengthen the focus on HR & GE in the project design and monitoring, including concrete details of how HR & GE issues will be addressed. UNEG’s guidance on this should be considered. / - DESA, and the UN more widely, should respect the SDG principle of LNOB by ensuring Capacity Building activities include interpretation, and official sites are available in at least the 6 official languages of the UN. / - DESA should consider contributing to tackling the existing gender inequality in STI by insisting on having at least 50% of women as speakers, moderators and participants in events. / - DESA should incorporate HR & GE specific indicators in its project design. Again, UNEG’s guidance on this should be considered. / - DESA should commit to gathering disaggregated data throughout its projects, starting with clear participant lists for every activity. / - The UN PDF should ensure that the recently developed form which collects HR & GE data is consistently used across all projects which it supports. / - DESA should build on the good practise of the Study Visits, Capacity Building Sessions and Ghana Project, linking STI to specific SDGs and gender issues in order to ensure a meaningful focus on HR & GE. / - DESA should use its position as implementer of this project and Co-Convenor of the IATT to work closely with the IATT to consider the ambition and funding for the OLP, ensuring coherence with the mandate given by MS in Agenda 2030, the AAAA and the Independent Assessment. / - DESA should continue the practise of piggybacking on other meetings and cost-sharing when organising activities. | - The project design could have been improved by developing stronger and more relevant indicators which better help measure the impact of the activities, and by ensuring regular and efficient monitoring throughout the project. / - Insufficient human and financial resources can significantly limit the effectiveness and efficiency of project implementation. / - A lack of clear exit planning, succession planning, and fundraising strategy can undermine the sustainability of project outcomes. / - Longer-term engagement and support for innovators, rather than one-off events or competitions, are valued and more likely to lead to sustained impact. / - Capacity building activities are more inclusive and effective when offered in multiple languages and with interpretation, supporting the Leave No-One Behind principle. / - Partnerships with local organizations, such as R4D in Ghana, enhance the relevance and effectiveness of capacity building for local innovators. / - Integrating gender and human rights considerations from the project design stage, with specific indicators and disaggregated data, leads to better outcomes and more inclusive participation. / - Administrative and technical barriers to integrating partner databases can undermine the effectiveness and coherence of online platforms. / - Piggybacking on existing meetings and cost-sharing with partners increases efficiency and reach. / - Clear political mandates and alignment with broader UN strategies facilitate project relevance and coherence, but must be matched by adequate resources and stakeholder engagement. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2016/PDF-2016-03 DSD internal STI/Reports/Final report & Eva/fisrt ver. 18 Mar 22/STI Evaluation LW final.pdf | Country standardized: 'USA' -> 'United States of America'. | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening statistical capacity-building in support of progress towards the Internationally Agreed Development Goals in the Southern African Development Community (SADC) region | 2011 | UNSD | Angola, Botswana, Democratic Republic of the Congo, Eswatini, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, United Republic of Tanzania, Zambia, Zimbabwe |  | - Focus on a single objective to make project planning and evaluation more manageable and effective. / - Put more effort into developing indicators that encompass quantity, quality, and time, and that can be reliably calculated with minimal resources. / - Build production of monitoring and evaluation indicators into the project by providing appropriate budget, staffing, data sources, and procedures in project planning. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 86 - Support to MDGs in SADC/Eval Report Feeney/UNSD-SADC Final Evaluation Report.pdf | Country standardized: 'DR Congo' -> 'Democratic Republic of the Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 3 | evaluations.xlsx rows 216 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 249 (archived) and 2 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 8 | evaluations.xlsx rows 55 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 10 | proposals.xlsx record 'SB-001376.99.99.24¦row:53': 'costTravelConsultants' has non-numeric value '-'. |
| 11 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 12 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 13 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 14 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 15 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 16 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 17 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 18 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 19 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 52 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 62 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 65 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 66 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |