Nepal

Asia | LDC | LLDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Nepal is presented in this country card as part of Asia, with Nepal also associated with an unspecified subregion and the LDC, LLDC grouping. The filtered data for Nepal highlights 12 projects for Nepal, including 2 active or planned projects for Nepal and 8 completed or closed projects for Nepal.

For Nepal, the report includes 25 requests for Nepal, 3 RPTC proposals for Nepal, 0 RPTC activities for Nepal, and 3 travel records for Nepal. Financially, Nepal shows USD 22,381,749 in project budget, $149,638 in proposal planned budget, and $0 in consumed RPTC activity budget for Nepal.

The main organizational coverage for Nepal points to Division for Sustainable Development Goals, EAPD, Economic Analysis and Policy Division, Financing for Sustainable Development Office. Activity records for Nepal list 0 participants, including 0 women participants, the current quality review for Nepal includes 60 data quality notes. Current highlights for Nepal include a request focus for Nepal: Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data.

      

      

      
This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing.

      

      

      
The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint.; an RPTC proposal focus for Nepal: Trade Promotion Using Digital Tools for Export Product Requirement Information (ePing) in Nepal in the context of smooth transition from the LDC category.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 12 |
| Project budget | USD 22,381,749 |
| Requests | 25 |
| RPTC proposals | 3 |
| Proposal planned budget | $149,638 |
| RPTC activities | 0 |
| Consumed RPTC budget | $0 |
| Activity participants | 0 |
| Women participants | 0 |
| Travel records | 3 |
| Evaluations | 11 |
| Data quality notes | 60 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment | 2017-01 | country | Division for Sustainable Development Goals | Closed | 01 May 2017 | 31 Dec 2021 | USD 2,300,000 | Central African Republic, Lao People's Democratic Republic, Madagascar, Nepal, Nigeria, Papua New Guinea | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment ¦ 2017-05-01T00:00:00 ¦ 2017-01': Country text 'Melanesia' could not be matched; no country assignment was inferred. / projects.csv record 'Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment ¦ 2017-05-01T00:00:00 ¦ 2017-01': Country/Sub region 'Melanesia' was not matched to GeoData and was ignored. |
| Enhancing the resilience, accessibility, and sustainability of infrastructure assets in developing countries along the Belt and Road initiative in support of the 2030 Agenda |  | country | Financing for Sustainable Development Office | Closed | 01 Feb 2022 | 31 Jan 2025 | USD 0 | Costa Rica, Gambia, Kenya, Lao People's Democratic Republic, Nepal, Peru | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Enhancing the resilience, accessibility, and sustainability of infrastructure assets in developing countries along the Belt and Road initiative in support of the 2030 Agenda ¦ 2022-02-01T00:00:00 ¦ [no project code]': Budget Budget is blank. |
| Monitoring the Sustainable Development Goals |  | country | Statistics Division | Closed | 01 Aug 2016 | 31 Jul 2022 | USD 9,334,229 | Bangladesh, Burundi, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Kyrgyzstan, Lao People's Democratic Republic, Liberia, Mozambique, Myanmar, Nepal, Rwanda, Tajikistan, Uganda, United Republic of Tanzania, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Municipal asset management for sustainable development in selected Least Developed Countries in Africa and Asia | 1819AU | country | Financing for Sustainable Development Office | Closed | 01 Jul 2018 | 31 Dec 2021 | USD 682,500 | Bangladesh, Nepal, Uganda, United Republic of Tanzania | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| New assistance measures for graduating Belt and Road Least DevelopedCountries toward the achievement of Agenda 2030 | PDF-SDG-2018-03 | country | Economic Analysis and Policy Division | Closed | 18 Nov 2020 | 31 Oct 2022 | USD 1,054,420 | Bangladesh, Cambodia, Democratic Republic of Timor-Leste, Lao People's Democratic Republic, Nepal | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| Accelerating SDGs in Developing Countries: Promoting Juncao Technology for Resilient Food Systems, Poverty Eradication and Climate Adaptation |  | country | Division for Sustainable Development Goals | Ongoing | 01 Jul 2025 | 30 Jun 2028 | USD 2,721,400 | Democratic Socialist Republic of Sri Lanka, Fiji, Kenya, Nepal, Nigeria, Papua New Guinea, Rwanda, United Republic of Tanzania | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Harnessing Synergies Between Climate Action, Energy, and Sustainable Development for Delivering the Paris Agreement and the SDGs |  | country | Division for Sustainable Development Goals | Under development | 01 Jan 2027 | 31 Dec 2030 | USD 696,000 | Democratic Socialist Republic of Sri Lanka, Fiji, Nepal | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Integrating Macroeconomy and Resource Systems for Country Planning in Asia-Pacific |  | country | Economic Analysis and Policy Division | Under development | 01 Jan 2027 | 31 Dec 2030 | USD 622,800 | Cambodia, Fiji, Nepal, Philippines |  |  |
| Promoting Environmentally Sustainable Transport (EST) in Asia - Formulation of National EST Strategies vis-à-vis Capacity Building for Socio-economic Concerns |  | country | Division for Sustainable Development Goals | Closed | 05 Jan 2015 | 19 Mar 2020 | USD 3,010,400 | Bangladesh, Cambodia, Democratic Socialist Republic of Sri Lanka, India, Indonesia, Lao People's Democratic Republic, Maldives, Nepal, Philippines, Viet Nam | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| Strategies for mitigating the impact of graduation from the least developed countries category | 1617C | country | Economic Analysis and Policy Division | Closed | 16 Apr 2020 | 19 Dec 2020 | USD 560,000 | Bhutan, Nepal, Uganda |  |  |
| Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises | 2427I | country | Economic Analysis and Policy Division | Active | 01 Feb 2024 | 01 Dec 2027 | USD 650,000 | Colombia, Malawi, Nepal |  |  |
| Strengthening geospatial information management in developing countries towards implementing the 2030 Agenda | 1819D | country | Statistics Division | Closed | 01 Mar 2018 | 31 Dec 2022 | USD 750,000 | Burkina Faso, Ethiopia, Fiji, Mongolia, Nepal, Tonga |  |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |  |
| 5422 | Request #5422 ? During the December 2025 mission, the Government of Nepal requested UN DESA support to address critical capacity-development and technical-cooperation needs related to its upcoming LDC graduation. In particular, Nepal seeks: / An in-person DESA/EAPD mission in early 2026 to engage a broad range of private-sector stakeholders and government counterparts, clarify misconceptions about the LDC graduation process, explain graduation criteria and monitoring, and provide guidance on available international support measures, including extensive Q&A. / Targeted capacity-building support for the private sector, notably through in-person ePing training workshops, to strengthen access to market-requirement information (SPS and TBT measures) and enhance preparedness for post-graduation trade conditions. / These requests aim to support effective implementation of Nepalâ€™s Smooth Transition Strategy (STS), strengthen institutional coordination, and ensure that both government and private-sector stakeholders are better prepared for a smooth and sustainable transition from LDC status. | Under consideration | Economic Analysis and Policy Division | 15 Dec 2025 | 01 Jan 2026 | 31 Dec 2026 | Mr. Senya Tuni ¦ senya.tuni@planning.go.tz | During the December 2025 mission, the Government of Nepal requested UN DESA support to address critical capacity-development and technical-cooperation needs related to its upcoming LDC graduation. In particular, Nepal seeks: / An in-person DESA/EAPD mission in early 2026 to engage a broad range of private-sector stakeholders and government counterparts, clarify misconceptions about the LDC graduation process, explain graduation criteria and monitoring, and provide guidance on available international support measures, including extensive Q&A. / Targeted capacity-building support for the private sector, notably through in-person ePing training workshops, to strengthen access to market-requirement information (SPS and TBT measures) and enhance preparedness for post-graduation trade conditions. / These requests aim to support effective implementation of Nepalâ€™s Smooth Transition Strategy (STS), strengthen institutional coordination, and ensure that both government and private-sector stakeholders are better prepared for a smooth and sustainable transition from LDC status. |  |  |
| 5377 | Request #5377 ? A total RPTC budget of US$20,000 is proposed to cover the consultancy fee for the development of these training materials, which will serve as a practical resource for statisticians, policymakers, and capacity-building initiatives across countries. / Background: Existing international standards and tools, developed under the UNSD migration statistics programme and endorsed by the Statistical Commission, provide a strong foundation for this work. These include the revised Recommendations on Statistics of International Migration and Temporary Mobility, and the accompanying technical reports on core and additional indicators, data integration, operationalization of the conceptual framework and data sources, and communication in the context of migration statistics, which together ensure comparable, high-quality data across countries. The consultancy will develop user-friendly training materials to support national statistical offices in applying these standards, operationalizing the conceptual framework as contained in the revised Recommendations, and producing reliable and comparable international migration statistics. | Completed | Statistics Division | 12 Nov 2025 | 01 Dec 2025 | 31 Mar 2026 | Maria Isabel Cobos ¦ cobos@un.org | A total RPTC budget of US$20,000 is proposed to cover the consultancy fee for the development of these training materials, which will serve as a practical resource for statisticians, policymakers, and capacity-building initiatives across countries. / Background: Existing international standards and tools, developed under the UNSD migration statistics programme and endorsed by the Statistical Commission, provide a strong foundation for this work. These include the revised Recommendations on Statistics of International Migration and Temporary Mobility, and the accompanying technical reports on core and additional indicators, data integration, operationalization of the conceptual framework and data sources, and communication in the context of migration statistics, which together ensure comparable, high-quality data across countries. The consultancy will develop user-friendly training materials to support national statistical offices in applying these standards, operationalizing the conceptual framework as contained in the revised Recommendations, and producing reliable and comparable international migration statistics. |  |  |
| 5321 | Request #5321 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Under consideration | Statistics Division | 19 Aug 2025 | 27 Oct 2025 | 31 Oct 2025 | Julian Chow ¦ chowj@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5134 | Request #5134 ? The System of Environmental Economic Accounting (SEEA) provides the internationally agreed statistical framework for measuring the relationship between the environment and the economy. It is comprised of two complimentary international statistical standards: the SEEA Central Framework (SEEA CF) and the SEEA Ecosystem Accounting (SEEA EA). The SEEA can be flexibly implemented by countries prioritizing accounts based on availability of information and policy priorities. The accounts are designed to respond to data needs for multiple policy initiatives including global initiatives on sustainable development goals (SDGs), on mitigating and adapting to climate change, disaster related statistics and on measuring the contribution of the environment to well-being. The accounts are also a necessary input to the compilation of headline indicators such as net domestic product as part of the recently adopted 2025 System of National Accounts (SNA). / In Asia, good progress has been made in the compilation of SEEA accounts with many countries regularly compiling SEEA CF accounts. National statistical offices (NSOs) of countries in the region continue to express strong interest in compiling SEEA accounts, including taking steps towards compiling asset accounts which are relevant for informing the relationship between the economy and the environment. With the recent adoption of the 2025 SNA which has expanded its asset boundary to include several natural resources assets of the SEEA CF, demands for environmental asset accounts will increase as the SEEA CF can provide input data for the compilation of the 2025 SNA. More broadly, there is a need to strengthen the capacities of NSOs to produce and disseminate SEEA accounts to better meet the needs of users for high quality integrated data on the contribution of the environment to the economy and the impact of the economy on the environment. | Under consideration | Statistics Division | 05 Mar 2025 | 16 Jun 2025 | 19 Jun 2025 | Marko Javorsek ¦ marko.javorsek@un.org | The System of Environmental Economic Accounting (SEEA) provides the internationally agreed statistical framework for measuring the relationship between the environment and the economy. It is comprised of two complimentary international statistical standards: the SEEA Central Framework (SEEA CF) and the SEEA Ecosystem Accounting (SEEA EA). The SEEA can be flexibly implemented by countries prioritizing accounts based on availability of information and policy priorities. The accounts are designed to respond to data needs for multiple policy initiatives including global initiatives on sustainable development goals (SDGs), on mitigating and adapting to climate change, disaster related statistics and on measuring the contribution of the environment to well-being. The accounts are also a necessary input to the compilation of headline indicators such as net domestic product as part of the recently adopted 2025 System of National Accounts (SNA). / In Asia, good progress has been made in the compilation of SEEA accounts with many countries regularly compiling SEEA CF accounts. National statistical offices (NSOs) of countries in the region continue to express strong interest in compiling SEEA accounts, including taking steps towards compiling asset accounts which are relevant for informing the relationship between the economy and the environment. With the recent adoption of the 2025 SNA which has expanded its asset boundary to include several natural resources assets of the SEEA CF, demands for environmental asset accounts will increase as the SEEA CF can provide input data for the compilation of the 2025 SNA. More broadly, there is a need to strengthen the capacities of NSOs to produce and disseminate SEEA accounts to better meet the needs of users for high quality integrated data on the contribution of the environment to the economy and the impact of the economy on the environment. | Country standardized: 'Republic of Korea' -> 'Korea'. |  |
| 5082 | Request #5082 ? In response to countries' requests for enhanced training in evidence-based Voluntary National Review (VNR) development, UNSD has initiated capacity-building efforts, including workshops and the creation of the "Practical Guide for Evidence-based Voluntary National Reviews." To further support these efforts and meet the demand for accessible, self-paced learning, e-learning materials will be developed based on the Guide, allowing Member States to access the training at any time. These materials will not only reinforce the guidance in the workshops but also offer more in-depth information, country examples, case studies, and practical tools to assist in the development of evidence-based VNRs. | Under consideration | Statistics Division | 20 Sept 2024 | 01 Oct 2024 | 31 Dec 2024 | Yongyi Min ¦ min3@un.org | In response to countries' requests for enhanced training in evidence-based Voluntary National Review (VNR) development, UNSD has initiated capacity-building efforts, including workshops and the creation of the "Practical Guide for Evidence-based Voluntary National Reviews." To further support these efforts and meet the demand for accessible, self-paced learning, e-learning materials will be developed based on the Guide, allowing Member States to access the training at any time. These materials will not only reinforce the guidance in the workshops but also offer more in-depth information, country examples, case studies, and practical tools to assist in the development of evidence-based VNRs. | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5080 | Request #5080 ? This workshop builds on last year's event, which focused on supporting evidence-based Voluntary National Reviews (VNRs) and Sustainable Development Goals (SDG) reporting for National Statistics Office (NSO) SDG focal persons presenting their VNR in 2024, with an emphasis on data. More information can be found here. This time, we are integrating it with the First Global Workshop for the 2025 Voluntary National Reviews, bringing together national VNR focal persons and NSO focal persons. The goal is to connect policy and data experts to enhance evidence-based VNR implementation for the 2025 cohort of countries. / The integrated workshop has been approved with our respective management and the agenda and concept note is being developed. The plan is to support the participation of member states from the approved RPTC budget from SD and OISC. | Under consideration | Office for Intergovernmental Support and Coordination for Sustainable Development, Statistics Division | 19 Sept 2024 | 03 Dec 2024 | 11 Apr 2025 | Yongyi Min, ¦ min3@un.org | This workshop builds on last year's event, which focused on supporting evidence-based Voluntary National Reviews (VNRs) and Sustainable Development Goals (SDG) reporting for National Statistics Office (NSO) SDG focal persons presenting their VNR in 2024, with an emphasis on data. More information can be found here. This time, we are integrating it with the First Global Workshop for the 2025 Voluntary National Reviews, bringing together national VNR focal persons and NSO focal persons. The goal is to connect policy and data experts to enhance evidence-based VNR implementation for the 2025 cohort of countries. / The integrated workshop has been approved with our respective management and the agenda and concept note is being developed. The plan is to support the participation of member states from the approved RPTC budget from SD and OISC. | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5038 | Request #5038 ? Guidance and expertise in developing and implementing effective training programs and capacity-building initiatives aligned with Nepal's SDG implementation strategies. / Opportunities for NASC faculty and staff to participate in training programs, seminars, conferences, and exposure visits in Asian countries to gain exposure to best practices and emerging trends in public administration and governance. / Opportunities to collaborate with DPIDG/UN DESA and other relevant institutions to share knowledge, exchange expertise, and build networks to enhance NASC's capacity and contribute to global knowledge exchange. | Completed | Division for Public Institutions and Digital Government | 29 Nov 2023 | 01 Jul 2024 | 01 Dec 2024 | Dr. Rajan Khanal ¦ prabin.maharjan@un.org | Guidance and expertise in developing and implementing effective training programs and capacity-building initiatives aligned with Nepal's SDG implementation strategies. / Opportunities for NASC faculty and staff to participate in training programs, seminars, conferences, and exposure visits in Asian countries to gain exposure to best practices and emerging trends in public administration and governance. / Opportunities to collaborate with DPIDG/UN DESA and other relevant institutions to share knowledge, exchange expertise, and build networks to enhance NASC's capacity and contribute to global knowledge exchange. |  |  |
| 4847 | Request #4847 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for one resource expert and for two UNSD staff to co-organize and co-lead a Regional Course on Statistical Business Registers that will be hosted by the Statistical Institute for Asia and the Pacific in Chiba, Japan, on 11-14 March 2024. / This regional course aims to help participants acquire knowledge and skills to deepens their understanding on the principles and methodology on statistical business registers. The course will review international recommendations and standards on Statistical Business Registers and provide guidance on the implementation of the Maturity Model for Statistical Business Registers. / The proposal concerns a total budget of US$15,783.00 covering the participation of a resource expert from Statistics Netherlands. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the course. | Completed | Statistics Division | 22 Jan 2024 |  | 14 Mar 2024 | Pedro Farinas ¦ farinas@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for one resource expert and for two UNSD staff to co-organize and co-lead a Regional Course on Statistical Business Registers that will be hosted by the Statistical Institute for Asia and the Pacific in Chiba, Japan, on 11-14 March 2024. / This regional course aims to help participants acquire knowledge and skills to deepens their understanding on the principles and methodology on statistical business registers. The course will review international recommendations and standards on Statistical Business Registers and provide guidance on the implementation of the Maturity Model for Statistical Business Registers. / The proposal concerns a total budget of US$15,783.00 covering the participation of a resource expert from Statistics Netherlands. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the course. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 4817 | Request #4817 ? Support to conduct a research on special challenges and opportunities for landlocked LDCs and to organize a dialogue on this topic during the LLDC3 conference in Kigali, June 2024. | Completed | Economic Analysis and Policy Division | 01 Dec 2023 | 01 Dec 2023 | 31 Dec 2024 | Mahesh Bhattarai ¦ mbhattarai@npc.gov.np | Support to conduct a research on special challenges and opportunities for landlocked LDCs and to organize a dialogue on this topic during the LLDC3 conference in Kigali, June 2024. |  |  |
| 3763 | Request #3763 ? support the national/local governments by applying the asset management tools to enhance transparency, accountability and good governance in future. | Completed | Financing for Sustainable Development Office | 07 May 2021 | 01 Jan 2023 | 31 Dec 2023 | Bamdev Sharma Adhikary ¦ bsadhikary@gmail.com | support the national/local governments by applying the asset management tools to enhance transparency, accountability and good governance in future. |  |  |
| 4760 | Request #4760 ? Request from that Asia-Pacific regional office of UNFPA for a joint DESA-UNFPA-US Census Bureau regional workshop on population projections to take place in Thailand, 16-20 October 2023. | Completed | Population Division | 25 Aug 2023 | 12 Oct 2023 | 20 Oct 2023 | Christophe Lefranc ¦ lefranc@unfpa.org | Request from that Asia-Pacific regional office of UNFPA for a joint DESA-UNFPA-US Census Bureau regional workshop on population projections to take place in Thailand, 16-20 October 2023. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4674 | Request #4674 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Completed | Statistics Division | 02 Aug 2023 | 02 Oct 2023 | 06 Oct 2023 | Ilaria di Matteo ¦ dimatteo@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 4731 | Request #4731 ? FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. | Completed | Financing for Sustainable Development Office | 31 Jan 2022 | 01 Jun 2022 | 12 Jan 2022 | Daniel Platz ¦ platz@un.org | FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. |  | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. / requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4020 | Request #4020 ? The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. | Completed | Economic Analysis and Policy Division | 18 Nov 2021 | 01 Jan 2022 | 31 Jan 2022 | Namsuk Kim ¦ kimnamsuk@un.org | The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. |  |  |
| 3915 | Request #3915 ? The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. | Completed | Economic Analysis and Policy Division | 10 May 2021 | 26 Jun 2021 | 15 Dec 2021 | Namsuk Kim ¦ kimnamsuk@un.org | The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. |  |  |
| 3754 | Request #3754 ? "Public financial management, Fiduciary risk management & Public / Assets management." | Outdated | Financing for Sustainable Development Office | 07 May 2021 |  |  | Sanjeeb Basnet ¦ sanjeebmails@gmail.com | "Public financial management, Fiduciary risk management & Public / Assets management." |  |  |
| 3757 | Request #3757 ? Request for technical assistance in infrastructure asset management. | Outdated | Financing for Sustainable Development Office | 07 May 2021 |  |  | Krishna Prasad Sapkota ¦ tdf@tdf.org.np | Request for technical assistance in infrastructure asset management. |  |  |
| 3462 | Request #3462 ? Direct demand from Member States submitted through the UNDP Country Offices and the UNDP Bangkok Regional Hub / In 2020 EAPD transitioned to remote delivery of its introductory Climate, Land, Energy and Water systems training programs. RPTC project SB-001377.58 funded the development of virtual training materials and in collaboration with UNDP this was delivered to participants from the Asia-Pacific region. 49 trainees from 8 countries completed the first part of the training program and teams for each of these countries are expected to finalize preliminary CLEWs analysis and present it at a policy dialogue event scheduled for February 24-25 2021. This project would support the finalization of the Asia-Pacific training course as well as follow up activities such as model improvements, reporting and finalization of policy papers. | Completed | Economic Analysis and Policy Division | 12 Feb 2021 |  | 31 Dec 2021 | Thomas Alfstad ¦ thomas.alfstad@un.org | Direct demand from Member States submitted through the UNDP Country Offices and the UNDP Bangkok Regional Hub / In 2020 EAPD transitioned to remote delivery of its introductory Climate, Land, Energy and Water systems training programs. RPTC project SB-001377.58 funded the development of virtual training materials and in collaboration with UNDP this was delivered to participants from the Asia-Pacific region. 49 trainees from 8 countries completed the first part of the training program and teams for each of these countries are expected to finalize preliminary CLEWs analysis and present it at a policy dialogue event scheduled for February 24-25 2021. This project would support the finalization of the Asia-Pacific training course as well as follow up activities such as model improvements, reporting and finalization of policy papers. |  |  |
| 2702 | Request #2702 ? To support the Government of Nepal with the implementation of SDG 6 | Not fulfilled by DESA | Division for Sustainable Development Goals | 18 Mar 2020 | 01 Feb 2021 | 31 Aug 2021 | Valerie Julliand ¦ valerie.julliand@un.org | To support the Government of Nepal with the implementation of SDG 6 |  |  |
| 2663 | Request #2663 ? DPIDG/ UNPOG was requested by the Ministry of Home Affairs/Municipalities Association of Nepal to support mayors and deputy mayors on SDG implementation as essential to localizing the Goals and to provide support on how to strengthen youth inclusion; to design policies and procedures that can enable youth to take part in setting local government development strategies, and on building capacity to strengthen national to local government coordination as an outcome of the December 2017 Regional Symposium by organizing a Learning Conference and a Regional Symposium. | Completed | Division for Public Institutions and Digital Government | 12 Oct 2017 | 23 Jan 2019 | 24 Jan 2019 | na ¦ na@gmail.com | DPIDG/ UNPOG was requested by the Ministry of Home Affairs/Municipalities Association of Nepal to support mayors and deputy mayors on SDG implementation as essential to localizing the Goals and to provide support on how to strengthen youth inclusion; to design policies and procedures that can enable youth to take part in setting local government development strategies, and on building capacity to strengthen national to local government coordination as an outcome of the December 2017 Regional Symposium by organizing a Learning Conference and a Regional Symposium. |  |  |
| 2662 | Request #2662 ? The Government of Nepal requested DESA to provide support in integrating the 2030 Agenda into their National e-Government Plan | Completed | Division for Public Institutions and Digital Government | 08 Jan 2016 | 19 Mar 2016 | 26 Mar 2016 | na ¦ na@gmail.com | The Government of Nepal requested DESA to provide support in integrating the 2030 Agenda into their National e-Government Plan |  |  |
| 2586 | Request #2586 ? Description not provided | Completed | Economic Analysis and Policy Division |  |  |  |  |  |  |  |
| 2575 | Request #2575 ? Building capacities for infrastructure asset mangement | Outdated | Financing for Sustainable Development Office | 19 Dec 2020 |  |  |  | Building capacities for infrastructure asset mangement |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001377.99.09 | Trade Promotion Using Digital Tools for Export Product Requirement Information (ePing) in Nepal in the context of smooth transition from the LDC category | EAPD | 31 Mar 2026 | 30 Jun 2026 | $15,000 | Nepal |  | Proposal past due |
| SB-001376.99.99.30 | Regional Training Workshop on the Implementation of the International Recommendations for the 2030 Round of Population and Housing Censuses in Asia | SD | 30 Sept 2026 | 30 Sept 2026 | $47,924 | Bangladesh, Bhutan, Cambodia, Democratic Republic of Timor-Leste, Democratic Socialist Republic of Sri Lanka, India, Indonesia, Lao People's Democratic Republic, Malaysia, Maldives, Mongolia, Nepal, Pakistan, Philippines, Thailand, Viet Nam | Country standardized: 'Lao People’s Democratic Republic' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor Leste' -> 'Democratic Republic of Timor-Leste'. | Proposal past due |
| SB-001376.99.99.31 | Securing the Future of Demographic and Health Data: Country Pathways and a Global Blueprint / | SD | 30 Sept 2026 | 31 Dec 2026 | $86,714 | Bangladesh, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Jordan, Kenya, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Papua New Guinea, Senegal, Tajikistan | Region standardized: 'global' -> 'Global'. |  |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women |
| --- | --- | --- | --- | --- | --- | --- | --- |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002065314 - Nepal | 0002065314 | Past | Nepal |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | ORGANIZING AND COORDINATING THE TOT WORKSHOP IN NEPAL |  | 11 May 2025 | 16 May 2025 |
| 0002257465 - Nepal | 0002257465 | Past | Nepal |  | DEVELOPMENT POLICY AND ANALYSIS DIVISION | NATIONAL WORKSHOP ON LDC GRADUATION AND EPING TRAINING |  | 06 Apr 2026 | 12 Apr 2026 |
| 0002258965 - Nepal | 0002258965 | Past | Nepal |  | DEVELOPMENT POLICY AND ANALYSIS DIVISION | NATIONAL WORKSHOPS ON LDC GRADUATION AND EPING, AND DATA |  | 06 Apr 2026 | 15 Apr 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| New Assistance Measures for Graduating Least Developed Countries Toward the Achievement of Agenda 2030 | 2023 | EAPD; CDPMO; DSDG | Bangladesh, Cambodia, Democratic Republic of Timor-Leste, Lao People's Democratic Republic, Myanmar, Nepal | - Future Projects should build a relationship management approach into design that includes consistency of staff for strategic partnership management. Minimizing staff turnover will assist with consistency with country stakeholders as well as increased efficiency through reduction of effort to establish relationships of new staff members. / - Consider a more programmatic approach within UNDESA to LDC graduation support rather than distinct Projects. This would include a more proactive and integrated communication approach to build understanding across each country. UNDESA needs to have clearly stated objectives and distinct components to help countries to understand UNDESA’s role and scope of support. This includes clarity about UNDESA’s added value to other graduation support initiatives during implementation so that it is clearer to the countries that there is a coordinated approach and that there is broader strategic work. This may be achieved through a brief project newsletter or other mechanism to update countries on wider UNDESA work and how the project contributes to and is aligned to that work. / - A continued and coordinated approach to ISMs and graduation support for the LDCs is required to build coherence and effective support and progress from the project gains towards the project objective. This requires increased use of available coordination mechanisms such as the RCO network, the IATF and the WTO sub-committee. The approach should allocate roles and responsibilities based on the strengths and mandates of each partner. Increased coordination could also assist with identifying common areas of demand where global tools such as guidance notes and studies could be developed. An external relations approach could be adopted that focuses on one main ministry who then delegates to avoid multiple, overlapping approaches to several ministries and to encourage intra-government engagement. Intra-government engagement can help to clarify priorities across sectors more effectively than engagement with one sector at a time. There is potential for improved coherence across the graduation process through a system-wide financing strategy. / - The impacts of COVID-19 reduced the potential of project activities to overcome delays in graduation preparation making a case for continued support based on lessons learned regarding: strengthened SSTC opportunities; balancing common requirements with responsiveness to country demand; iterative approaches and enabling environments and addressing gaps in assistance to progress beyond STS preparation – specific areas for ongoing support vary between countries. UNDESA has a role to play in sharing these lessons with other development partners. / - UNDESA needs to encourage sustainable development initiatives (particularly LNOB and environmental considerations) as part of the STS. UNDESA is in a unique position, given previous connections and guidance given for preparing the STS, to advocate for a more comprehensive approach to graduation at the country level. Given the priorities of UNDESA member states related to the principles of the 2030 Agenda and inclusion, UNDESA should take a much stronger position on these issues. Additional considerations in developing new guidance could include, enhancing country ownership through the preparation process and more practical rather than theoretical guidance. / - The graduation process should be made more robust and clearer through reduction of monitoring burden on graduating countries and improved feedback loops between countries graduating and international actors. The LDC5 conference as well as potential regular feedback events at the RCs annual meeting provide opportunities to expand the successes of the final project workshop and integrate an SSTC approach to ensure ongoing graduation support is based on the experiences of graduating countries. | - Coordinated engagement with country transition processes is essential to respond to country demand and provide coherent support. The design of the project addressed an identified need to provide tailored support to countries in their transition processes. This support needed to be identified in direct liaison with country stakeholders rather than through only studies or digital tools. The mainstreaming of the STS process into national planning is critical. Engagement of senior national stakeholders was important to ensure national relevance and enable follow-up actions. Building relationships at the country level is imperative for buy in on topics as complex and sensitive as graduation and in-country staff within the RCO and other development partners were essential to facilitate the process, build trust and communicate country needs to wider development partners. South-south cooperation, peer exchange and multistakeholder engagement were effective means for building capacity, understanding and knowledge related to graduation and establishing peer networks. / - Effective harnessing of ISMs relies on in-country clarity for priorities by sector and capacity to prepare the required documentation to secure necessary resources. The country’s readiness to articulate priorities for transition was not as well developed as expected at project commencement. Initial efforts to identify priorities were not sufficiently comprehensive or interactive. Once a more active, multi-sector dialogue occurred, priorities for transition emerged. This facilitated focus on required ISMs but countries still see major barriers to accessing required support. / - Some aspects of graduation and support tools can be standardised across countries but specific measures that respond directly to country priorities are required. Some stages of graduation preparation such as the STS are useful across all graduating LDCs. However, the specifics to be included in the STS and guidance for implementation arrangements is specific to each country and requires additional, tailored support beyond a standardized graduation approach. This reflects the specifics of each country in terms of attitudes towards graduation, capacity, legislative and planning context and priorities for graduation. An additional area that requires a tailored approach relates to specific aspects of mainstreaming human rights and gender into graduation discussions and how to integrate LNOB in the most appropriate way. / - Iterative approaches are appropriate for graduation support but must be aligned with country requirements and maintain a degree of flexibility to be successful. A focus as complex as graduation support may require a staged approach that builds knowledge, understanding and momentum for change before securing national ownership of follow-on initiatives related to specific support mechanisms. There is a high degree of risk associated with definite iterative approaches that rely on successful completion of early activities before implementing follow-on activities without adaptability and flexibility written into design to respond to arising challenges or lack of progress. Additionally, adaptability is important for responding to changes in context such as those brought about by the COVID-19 pandemic. / - There are multiple initiatives across several agencies to support graduation, synergies must be purposefully pursued to avoid duplication and increase relevance. Synergies should be pursued based on comparative advantages of each partner. In the case of UNDESA, this advantage relates to strong relationships at the country level, technical experience and engagement with recently graduated countries and strategic and analytical perspectives. This synergy should be pursued both within UNDESA programs and between agencies. The establishment of the RCO network structure has been a positive step for coherence and could be further utilised. / - Transition processes have largely focused on economic indicators and there is still less attention to social and environmental concerns. The project activities provided an important avenue for raising the profile of social and environmental considerations in transition. Stakeholders noted an increase in awareness of the broader aspects of graduation but there is still little tangible progress in how such concerns can be embedded in the STS. Linking the STS to wider national development processes can help to widen the understanding of the likely impacts and benefits of transition. Greater engagement of specialized UN agencies related to gender equity and human rights in STS process can stimulate consideration of equity concerns in transition policies and plans. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/Sharing with donor/4th batch (to be shared)/2023_PDF-SDG-2018-03_Eval_EAPD_12July23.pdf | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| Strategies for mitigating the impact of graduation from the LDC category | 2020 | EAPD | Bhutan, Gambia, Nepal | - Make the Gradjet platform available in other languages, starting with French and Portuguese, to increase its impact in non-English-speaking countries. / - Future activities should include the creation of a participant file and follow up on participants to assess short- and long-term benefits and knowledge transfer. / - Subsequent project stages should take into account French-speaking countries. / - Ensure the sustainability of knowledge acquired by participants in seminars and training courses organized within the project. / - Replicate the project in countries that have not yet benefited, and systematize this type of project for countries entering a graduation process. / - Follow up the project to ensure that smooth transition strategies are defined. | - Listening to participants and adapting project activities to their needs, such as prioritizing the development of the Gradjet platform, increases project ownership and relevance. / - Administrative and political changes in beneficiary countries can affect project ownership and institutional memory, requiring flexible and adaptive project management. / - Ambitious targets, such as developing formal smooth transition strategies, may need to be adjusted based on external factors and the readiness of pilot countries. / - Workshops and interregional exchanges facilitate the sharing of experiences and lessons learned among LDCs, enhancing the value and scalability of project outcomes. / - Collaboration with multiple UN entities and international organizations leverages comparative advantages and improves the quality and recognition of project outputs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/10th tranche/DPIDG/Evaluation Report ROA 1617C_Final.pdf |  |  |
| Municipal Asset Management for Sustainable Development in Selected Least Developed Countries in Africa and Asia | 2022 | FSDO; CDPMO | Bangladesh, Nepal, Uganda, United Republic of Tanzania | - Expand the target audience to include more central level government officials to facilitate buy-in. / - Explicitly request a larger proportion of female workshop participants to advance gender equality, without compromising the calibre of qualified stakeholders. / - Continue experimenting with variations of the hybrid workshop model, combining online and in-person facilitation, and maintain the use of workshop questionnaires. / - Offer remuneration or support to cover connectivity fees for stakeholders facing internet access challenges. / - Provide relevant, context-specific examples in workshops, including examples clarifying the links between gender, asset management, and human rights. / - Spread workshops over the year, such as three or four sessions annually, if funding allows. / - Provide more support to address information gaps and climate proofing of assets, including producing short instructional videos on information gathering and climate-related asset management. / - Continue supporting the institutionalization of training in all four countries, including initiating and expanding ToT (Training of Trainers) development programs. / - Explore ToT training opportunities in Nepal with the Local Development Training Academy. / - Provide additional substantive support to the Government of Uganda to ensure effective policy implementation for municipal financing and asset management. / - Continue collaboration with the Town Development Fund in Nepal, as its mandate complements the project’s objectives. / - Make future results frameworks more realistic by including external factors such as pandemics, funding limitations, coordination challenges, and varying AMAP complexity as underlying assumptions. | - For stakeholders in Africa, internet access is unreliable and expensive; future evaluations should include monetary support to ensure equitable participation and that all voices are heard. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/1819AU SB-010719 Municipal Asset Management/Final evaluation/Final Evaluation Report 8 March 2022.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data | 2018 | DPIDG | Bangladesh, Nepal, Panama, Uruguay | - Increase the number of participants in regional and international workshops and pursue new avenues of funding for additional participants from the target country, including contributions from local governments, private sector, and host countries. / - Translate the Guide on Lessons for OGD Action Planning for Sustainable Development into Spanish and regularly publicize its location on the UNDESA website. / - DPADM should recommend to the three Governments that have adopted the OGD National Action Plan to publicize this milestone to increase awareness among government and non-government stakeholders of its achievement and potential benefits. | - The selection of target countries should be based on in-depth feasibility study and assessment of demand, including analysis of needs, motivation, presence of a 'champion', political conditions, risks of political transitions, and early consultation with relevant regional organizations or networks. / - Future project design and planning should prioritize distributing benefits more widely within a region by leveraging the knowledge and capacity of key networks and more advanced countries. / - Greater planning and local consultation are needed to ensure participants have sufficient preparation and technical skills, relevant topics receive adequate time, and more country-specific case studies and local experts are included in workshops. / - More time should be allocated for group discussions and exercises, and documents and materials should be shared before the workshop. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/02 PROJECTS - CURRENT/UNSD/OGD FINAL_Eval Report_ Klein21March_submitted to CDO on 21 March 2018.docx |  | evaluations.xlsx rows 171 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 199 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 252 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries | 2016 | DPIDG | Gambia, Lesotho, Nepal, Uganda | - A clear and ambitious development strategy to organize regular training in all LDCs should be defined, particularly to favor implementation in LDCs where needs in capacity building seem to be stronger. / - To ensure joint capacity development activities with the WTO and ITC, DESA staff should quickly establish a strategy to lobby for the project to ensure its sustainable funding. DESA staff should thus incorporate regular monitoring reports into the project. / - Where possible, public officers should be helped to better understand the SPS and TBT issues and to translate this information in a user friendly way to producers and traders. / - All comments and feedback from users should be quickly taken into account to improve the toolkit. / - In future steps, DESA will have to redesign the project to adapt it to each LDC, for instance by better considering cultural differences to make sure that stakeholders from non-English-speaking countries are also able to benefit from the project and its positive externalities. | - e-Ping fills a void by providing a publicly available online service that enables countries lacking institutional infrastructure to access key information from trading partners regarding new product requirements. / - Regular training is essential for optimal use of e-Ping, especially in LDCs where institutional constraints are higher. / - A Training of Trainers course can help develop country-based expertise and training capacity for the continued and broader use of the e-Ping system. / - The involvement of stakeholders in project implementation and output definition increases the usefulness and relevance of the project. / - Some producers may have difficulty understanding the technical information provided by e-Ping, highlighting the need for user-friendly communication and support. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/ROA 205 - DPAD - Trade-related International Support/Evaluation report/161209 - Evaluation report ROA 205.docx |  | evaluations.xlsx rows 185 (archived) and 53 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| UN Capacity Development Initiative on Enhancing the Resilience, Accessibility, and Sustainability of Infrastructure Assets in Developing Countries in Support of the 2030 Agenda | 2025 | FSDO; CDPMO | Costa Rica, Gambia, Kenya, Lao People's Democratic Republic, Nepal, United Republic of Tanzania | - Engage major project stakeholders, including International Experts, to reflect on what avenues would be best to dive deeper into Data for IAM, Climate-Resilience, and IAM finance. / - Continue to engage females in selecting workshop participants in the future, especially if they are in senior management positions within the central government. Advocacy for female workshop participants and female focal points could be used. / - Strengthen the Training of Trainers (ToT) component and have a specific budget allocation for it. / - Consider other recruitment processes to address delays due to a large number of qualified applicants. / - When engaging central government officials, increase the amount of time allotted to the process. / - If continuing to use the UNOPS CAT-I Tool, reduce the number of questions or increase the amount of time allotted to the exercise, and streamline the tool to be consistent with the Diagnostic Tool. | - Female representation in workshops is enhanced when women are responsible for the selection of participants, especially in senior management positions. / - The process of engaging a broad base of stakeholders for infrastructure asset management is new in many countries and takes more time than anticipated. / - Customized Training of Trainers (ToT) and partnerships with National Training Institutes are critical for sustainability in capacity development projects. / - Switching project countries in response to political or commitment challenges can be managed efficiently without significant delays to project outcomes. / - Lengthy assessment tools (such as the CAT-I) may fatigue stakeholders and should be streamlined for future use. / - Savings from efficient project management can be reinvested to strengthen key project components, such as additional ToT workshops. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2021/PDF-2021-03 DESA-FSDO/Reports/Fin Rep_Evaluation/FINAL Evaluation Report 12 May.pdf | Country standardized: 'The Gambia' -> 'Gambia'. |  |
| Evaluation of the United Nations Centre for Regional Development (UNCRD) | 2023 | DSDG; CDPMO | Afghanistan, Australia, Bangladesh, Bhutan, Brunei Darussalam, Cambodia, China, Democratic Republic of Timor-Leste, Democratic Socialist Republic of Sri Lanka, Fiji, India, Indonesia, Iran (Islamic Republic of), Japan, Kiribati, Korea, Lao People's Democratic Republic, Malaysia, Maldives, Marshall Islands, Micronesia (Federated States of), Mongolia, Myanmar, Nepal, New Zealand, Palau, Papua New Guinea, Philippines, Russian Federation, Samoa, Singapore, Solomon Islands, Thailand, Tonga, Tuvalu, Viet Nam | - Develop a strategic vision for UNCRD that is closely aligned with UN DESA’s mandate and the priorities of the donor and that articulates its added value, comparative advantages, and strengths. / - Secure additional core funding to ensure UNCRD’s sustainability. / - Take actionable concrete steps to support more holistic office management. / - Strengthen collaboration between UN DESA and UNCRD. / - Develop a technical assistance programme to support member state capacity development throughout the year. | - Visibility and effective communication with donors along with intentional alignment with donor priorities are essential components to ensuring programme sustainability. / - When more than one donor funds programming, staff cohesion and teamwork can be promoted by ensuring that each donor funds a portion of each staff position. / - Generating partner buy-in and leveraging that buy-in through in-kind and financial contributions can significantly increase an office’s capacity to achieve greater results. / - UN DESA’s project offices require investment from UN DESA to support their strategic work and not only their administrative work. / - Focusing on specific thematic areas can provide excellent added value to overall efforts to achieve the SDGs. However, programming must be centered within the wider SDG context and be aligned with DESA and donor priorities in order to demonstrate its relevance. / - Supporting intra-governmental collaboration across government ministries is a highly valued contribution towards achieving the complexity of the SDGs. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Active Projects/6 DSDG (DSD)/UNCRD/All UNCRD projects/Audit & Evaluation/Evaluation 2023/Final Evaluation Report June 26 2023/UNCRD Evaluation Final Report June 26 2023.docx | Country standardized: 'Federated States of Micronesia' -> 'Micronesia (Federated States of)'. / Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | evaluations.xlsx rows 282 (archived) and 127 (retained): Review conflicts: Countries differs: archived row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Korea; Lao People’s Democratic Republic; Malaysia; Maldives; Marshall Islands; Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'; retained row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Republic of Korea; Lao People's Democratic Republic; Lao PDR; Malaysia; Maldives; Marshall Islands; Federated States of Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'. Country lists were not merged. |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Developing a Public‐Private Partnerships (PPP) and Infrastructure Financing Network in Asia and the Pacific | 2022 |  | Afghanistan, Bangladesh, Cambodia, Democratic Republic of Timor-Leste, Fiji, India, Indonesia, Kazakhstan, Kyrgyzstan, Lao People's Democratic Republic, Malaysia, Mongolia, Nepal, Pakistan, Papua New Guinea, Philippines, Russian Federation, Tajikistan, Thailand, Türkiye, Viet Nam | - The project team should further clarify the end-purpose of the Network to its key internal and external stakeholders, establish a clear theory of change and results matrix, and set measurable targets to assess its performance. / - Increase attention to collecting data on key outcomes and impacts to document and learn about changes occurring at different levels, and develop a clear M&E plan involving national partners. / - Further incorporate human rights, gender equality, and related issues in key priority areas by systematically collecting disaggregated data and arranging training on mainstreaming gender and human rights issues in project design and implementation. / - Seek additional resources for building on the results achieved so far and diversify the donor base for sustainability and expansion. / - Enhance collaboration with other ESCAP divisions and sections to offer deeper expertise and build on collaboration with related units and networks such as the ESCAP Sustainable Business Network (ESBN). | - Involving private sector entities and carefully selecting local and international partnerships contributed to the successful establishment and operationalization of the network and should be replicated in other projects where relevant. / - Remote collaboration, while necessary during the pandemic, limited deeper engagement critical for higher-order outcomes such as building trust and making investments; future phases should emphasize site visits and in-person networking to facilitate more meaningful connections. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2018/PDF-2018-06 ESCAP/Reports/Final Report & Evaluation/PPP Project Evaluation Report _formatted 17Nov.pdf | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | evaluations.xlsx row 214: Divisions not provided. |
| Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies | 2015 | DPAD | Afghanistan, Bangladesh, Bhutan, Botswana, Cambodia, Chile, China, Democratic Socialist Republic of Sri Lanka, Eswatini, India, Indonesia, Kazakhstan, Korea, Lao People's Democratic Republic, Lesotho, Mozambique, Myanmar, Namibia, Nepal, Philippines, Singapore, South Africa, Tajikistan, Thailand, Uzbekistan, Viet Nam, Zambia | - Future capacity development projects of UNDESA should be sufficiently ambitious in their objectives but designed with adequate flexibility to deliver capacity development objectives in a demand-driven and nationally-owned manner. / - Future projects should ensure sufficient flexibility in the activities listed in project documents, making the list of activities indicative and not a binding constraint. / - Future training workshops should allocate additional time for discussion among participants and distribute research and background papers in advance. / - Future capacity development projects should include a post-project phase engagement framework to ensure sustainability of project interventions, especially since UNDESA is a non-resident entity. / - Future projects should earmark resources to facilitate the deployment of experts from other UN agencies to reduce dependence on external consultants. / - Future capacity development projects should make fostering South-South Cooperation a stated objective, with a clear focus on enabling developing countries to learn from each other. / - Future projects may devote technical and financial resources to develop an online forum to ensure the sustainability of interventions beyond completion. / - Future projects would benefit from having a clear and well-defined monitoring and evaluation strategy, including early recruitment of an external evaluator and allocation of resources for field visits and online evaluation tools. / - UNDESA should continue to provide policy-advisory and capacity development support to beneficiary countries and add a few additional countries to ensure sustainability of the impacts. | - An integrated approach, building on previous successful projects and deepening engagement in a few countries, leads to significant multiplier effects, cost-savings, and greater policy impact. / - Flexibility and improvisation in project implementation allow for responsiveness to evolving needs and ensure country ownership, rather than following a rigid, pre-determined set of activities. / - There is greater demand for country-specific, evidence-based policy advice than for generic handbooks or textbooks. / - Partnerships with other UN agencies, especially UNDP and regional commissions, are key to sustaining project impact and should be further strengthened. / - South-South cooperation, though not a stated objective, emerged as a valuable outcome and should be explicitly included in future project objectives. / - Establishing online communities or networks for trained officials and trainers can help sustain knowledge exchange and learning beyond project completion. / - A clear and well-defined monitoring and evaluation strategy, including early involvement of external evaluators and use of online tools, improves the quality and comprehensiveness of project evaluation. / - The project generated new requests for support from additional countries, indicating the importance of maintaining and expanding capacity development support to ensure sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/6th tranche/ROA 182 (DPAD)/Final Evaluation Report of MAC - Complete.pdf | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Vietnam' -> 'Viet Nam'. | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict | 2013 | DSDG | Lebanon, Liberia, Nepal, Zimbabwe | - Establish an institutionalized structure for national ownership and sustainability by building on existing institutions to create a nationally owned unit responsible for project management and implementation, tailored to each country's political context and leadership structure. / - Strengthen the capacity and engagement of civil society to raise awareness of sustainable development issues and the importance of integrating sustainable development principles into national planning and policies. / - Improve stakeholder engagement and participation by increasing consultations and preparation time to ensure high-level commitment, local ownership, and relevance of project activities and outputs. / - Expand project activities to include more opportunities for practical application and training on the integration of sustainable development tools in national planning. / - Strengthen monitoring and evaluation mechanisms throughout the project to better assess results, inform stakeholders of progress and impact, and develop systems for monitoring longer-term outcomes. / - Expand the project to other countries emerging from conflict, incorporating lessons learned from the pilot countries to maximize success and impact. | - Project design and objectives are highly relevant to countries emerging from conflict, but successful implementation requires in-depth understanding of each country's unique context, stakeholder dynamics, and political structures. / - Flexibility in project design and implementation is essential to adapt to changes in leadership, stakeholder commitment, and political environments. / - Strong research, substance, and knowledge in training and activities increase project relevance and effectiveness. / - Terminology and concepts used in the project, such as 'post-conflict' and 'sustainable development,' affect stakeholder perceptions of relevance and effectiveness. / - Securing strong political will, high-level commitment, and national ownership is critical, especially in countries with shifting powers and multiple party agendas; more time and resources may be needed to achieve this. / - Timing of negotiation and implementation is crucial in post-conflict countries where leadership and priorities are constantly shifting. / - In-depth stakeholder mapping and engagement, as well as coordination with existing national development efforts, are vital for successful implementation; clear roles among partner agencies should be established before implementation. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/6th tranche/ROA-105-Final External Evaluation.docx |  | evaluations.xlsx rows 298 (archived) and 220 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Lebanon; Liberia; Nepal; Zimbabwe'; Divisions differs: archived row has ''; retained row has 'DSDG'; Evaluation Year differs: archived row has ''; retained row has '2013'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 2 | evaluations.xlsx row 214: Divisions not provided. |
| 3 | evaluations.xlsx rows 171 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 185 (archived) and 53 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 199 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 252 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | evaluations.xlsx rows 282 (archived) and 127 (retained): Review conflicts: Countries differs: archived row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Korea; Lao People’s Democratic Republic; Malaysia; Maldives; Marshall Islands; Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'; retained row has 'Afghanistan; Australia; Bangladesh; Bhutan; Brunei Darussalam; Cambodia; China; Fiji; India; Indonesia; Iran; Japan; Kiribati; Republic of Korea; Lao People's Democratic Republic; Lao PDR; Malaysia; Maldives; Marshall Islands; Federated States of Micronesia; Mongolia; Myanmar; Nepal; New Zealand; Palau; Papua New Guinea; Philippines; Russian Federation; Samoa; Singapore; Solomon Islands; Sri Lanka; Thailand; Timor-Leste; Tonga; Tuvalu; Viet Nam'. Country lists were not merged. |
| 8 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 10 | evaluations.xlsx rows 298 (archived) and 220 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Lebanon; Liberia; Nepal; Zimbabwe'; Divisions differs: archived row has ''; retained row has 'DSDG'; Evaluation Year differs: archived row has ''; retained row has '2013'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 11 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 12 | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. |
| 13 | requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 46 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 60 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |