Pakistan

Asia

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Pakistan is presented in this country card as part of Asia, with Pakistan also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Pakistan highlights 1 projects for Pakistan, including 0 active or planned projects for Pakistan and 1 completed or closed projects for Pakistan.

For Pakistan, the report includes 15 requests for Pakistan, 3 RPTC proposals for Pakistan, 1 RPTC activities for Pakistan, and 0 travel records for Pakistan. Financially, Pakistan shows USD 2,321,000 in project budget, $222,405 in proposal planned budget, and $6,688 in consumed RPTC activity budget for Pakistan.

The main organizational coverage for Pakistan points to Division for Public Institutions and Digital Government, DPIDG, DSDG, Financing for Sustainable Development Office. Activity records for Pakistan list 1,299 participants, including 665 women participants, the current quality review for Pakistan includes 56 data quality notes. Current highlights for Pakistan include a request focus for Pakistan: Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data.

      

      

      
This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing.

      

      

      
The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint.; an RPTC proposal focus for Pakistan: Regional Training Workshop on the Implementation of the International Recommendations for the 2030 Round of Population and Housing Censuses in Asia; an activity focus for Pakistan: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 1 |
| Project budget | USD 2,321,000 |
| Requests | 15 |
| RPTC proposals | 3 |
| Proposal planned budget | $222,405 |
| RPTC activities | 1 |
| Consumed RPTC budget | $6,688 |
| Activity participants | 1,299 |
| Women participants | 665 |
| Travel records | 0 |
| Evaluations | 8 |
| Data quality notes | 56 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Towards integrated national financing framework | 2124A | country | Financing for Sustainable Development Office | Closed | 01 Mar 2021 | 28 Jun 2024 | USD 2,321,000 | Belarus, Burkina Faso, Colombia, Costa Rica, Egypt, Indonesia, Jordan, Kyrgyzstan, Pakistan, Zambia |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5572 | Request #5572 ? In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. | Under consideration | Statistics Division | 06 Mar 2026 | 06 Mar 2026 | 31 Mar 2027 | Omar Seidu ¦ omar.seidu@statsghana.gov.gh | In early 2025, the Demographic and Health Survey (DHS) programme was terminated, disrupting ongoing surveys and threatening continuity of access to a data platform with more than 20 million data points and 4,000 indicators. For four decades, DHS supported health, nutrition, demographic and gender data production in more than 90 countries, and 39 SDG indicators rely to some degree on DHS data. / This project will support implementation of the Inter-Secretariat Working Group on Household Surveys (ISWGHS) work programme for a sustainable health and demographic data through two mutually reinforcing components. Component 1 will build capacity of 15 countries to identify priority health and population indicators, map data gaps and sources, assess technical, institutional and financial capacity, and develop sequenced national roadmaps. Component 2 will develop a Blueprint for Sustainable, Country-Led Demographic and Health Data Systems through Surveys, covering standards and indicators, innovation and harmonization, and capacity building strategies and financing. / The project will include a consultancy service to support the coordination of activities undertaken under Component 1 and 2; while the technical meeting in Nairobi, Kenya, on 2-3 November 2026, will bring countries together to finalise the Blueprint. |  |  |
| 5352 | Request #5352 ? The Financing for Sustainable Development Office (FSDO) of the United Nations Department of Economic and Social Affairs (DESA) organized a Regional Workshop on Transfer Pricing in Asia-Pacific, held from 25 to 29 August 2025 in Incheon, Republic of Korea. / The workshop responded directly to countries' demand for practical tools and training on transfer pricing, aimed at strengthening domestic resource mobilization to support sustainable development. Transfer pricing â€” the pricing of cross-border transactions involving goods, services, or intangibles between related entitiesâ€” has gained increasing global attention due to its significant implications for equitable taxation and sustainable development. / Developing countries face considerable challenges in this area, including a high risk of profit shifting and limited access to specialized training and resources available to policy makers and tax administrations. The workshop brought together 23 participants (39% female) from 23 countries across the Asia-Pacific region, including least developed countries (LDCs), landlocked developing countries (LLDCs), and small island developing states (SIDS). Participants engaged in hands-on training on transfer pricing principles, using practical case studies to illustrate challenges frequently encountered by tax officials during audits of real-life transfer pricing cases. / Delivered in English, the workshop contributed to ongoing capacity-building efforts, enhancing the ability of tax officials to effectively address complex international tax issues. | Under consideration | Financing for Sustainable Development Office | 27 May 2025 | 25 Aug 2025 | 29 Aug 2025 | FSDO following request from Member States ¦ fsdcapdev@un.org | The Financing for Sustainable Development Office (FSDO) of the United Nations Department of Economic and Social Affairs (DESA) organized a Regional Workshop on Transfer Pricing in Asia-Pacific, held from 25 to 29 August 2025 in Incheon, Republic of Korea. / The workshop responded directly to countries' demand for practical tools and training on transfer pricing, aimed at strengthening domestic resource mobilization to support sustainable development. Transfer pricing â€” the pricing of cross-border transactions involving goods, services, or intangibles between related entitiesâ€” has gained increasing global attention due to its significant implications for equitable taxation and sustainable development. / Developing countries face considerable challenges in this area, including a high risk of profit shifting and limited access to specialized training and resources available to policy makers and tax administrations. The workshop brought together 23 participants (39% female) from 23 countries across the Asia-Pacific region, including least developed countries (LDCs), landlocked developing countries (LLDCs), and small island developing states (SIDS). Participants engaged in hands-on training on transfer pricing principles, using practical case studies to illustrate challenges frequently encountered by tax officials during audits of real-life transfer pricing cases. / Delivered in English, the workshop contributed to ongoing capacity-building efforts, enhancing the ability of tax officials to effectively address complex international tax issues. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 5129 | Request #5129 ? The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Completed | Population Division, Statistics Division | 28 Mar 2025 | 16 Jun 2025 | 20 Jun 2025 | Maria Isabel Cobos ¦ cobos@un.org | The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5134 | Request #5134 ? The System of Environmental Economic Accounting (SEEA) provides the internationally agreed statistical framework for measuring the relationship between the environment and the economy. It is comprised of two complimentary international statistical standards: the SEEA Central Framework (SEEA CF) and the SEEA Ecosystem Accounting (SEEA EA). The SEEA can be flexibly implemented by countries prioritizing accounts based on availability of information and policy priorities. The accounts are designed to respond to data needs for multiple policy initiatives including global initiatives on sustainable development goals (SDGs), on mitigating and adapting to climate change, disaster related statistics and on measuring the contribution of the environment to well-being. The accounts are also a necessary input to the compilation of headline indicators such as net domestic product as part of the recently adopted 2025 System of National Accounts (SNA). / In Asia, good progress has been made in the compilation of SEEA accounts with many countries regularly compiling SEEA CF accounts. National statistical offices (NSOs) of countries in the region continue to express strong interest in compiling SEEA accounts, including taking steps towards compiling asset accounts which are relevant for informing the relationship between the economy and the environment. With the recent adoption of the 2025 SNA which has expanded its asset boundary to include several natural resources assets of the SEEA CF, demands for environmental asset accounts will increase as the SEEA CF can provide input data for the compilation of the 2025 SNA. More broadly, there is a need to strengthen the capacities of NSOs to produce and disseminate SEEA accounts to better meet the needs of users for high quality integrated data on the contribution of the environment to the economy and the impact of the economy on the environment. | Under consideration | Statistics Division | 05 Mar 2025 | 16 Jun 2025 | 19 Jun 2025 | Marko Javorsek ¦ marko.javorsek@un.org | The System of Environmental Economic Accounting (SEEA) provides the internationally agreed statistical framework for measuring the relationship between the environment and the economy. It is comprised of two complimentary international statistical standards: the SEEA Central Framework (SEEA CF) and the SEEA Ecosystem Accounting (SEEA EA). The SEEA can be flexibly implemented by countries prioritizing accounts based on availability of information and policy priorities. The accounts are designed to respond to data needs for multiple policy initiatives including global initiatives on sustainable development goals (SDGs), on mitigating and adapting to climate change, disaster related statistics and on measuring the contribution of the environment to well-being. The accounts are also a necessary input to the compilation of headline indicators such as net domestic product as part of the recently adopted 2025 System of National Accounts (SNA). / In Asia, good progress has been made in the compilation of SEEA accounts with many countries regularly compiling SEEA CF accounts. National statistical offices (NSOs) of countries in the region continue to express strong interest in compiling SEEA accounts, including taking steps towards compiling asset accounts which are relevant for informing the relationship between the economy and the environment. With the recent adoption of the 2025 SNA which has expanded its asset boundary to include several natural resources assets of the SEEA CF, demands for environmental asset accounts will increase as the SEEA CF can provide input data for the compilation of the 2025 SNA. More broadly, there is a need to strengthen the capacities of NSOs to produce and disseminate SEEA accounts to better meet the needs of users for high quality integrated data on the contribution of the environment to the economy and the impact of the economy on the environment. | Country standardized: 'Republic of Korea' -> 'Korea'. |  |
| 4850 | Request #4850 ? Request is a follow-up to the DESA-UNFPA Asia-Pacific workshop on population projections (2023). / Request is for 2 workshops to train Pakistan statisticians: (1) in the use of Pop Division's stochastic population forecast method; (2) training in the statistical language "R" for demographic analysis. | Under consideration | Population Division | 26 Jan 2024 | 03 Jun 2024 | 14 Jun 2024 | Muqaddar Shah ¦ sshah@unfpa.org | Request is a follow-up to the DESA-UNFPA Asia-Pacific workshop on population projections (2023). / Request is for 2 workshops to train Pakistan statisticians: (1) in the use of Pop Division's stochastic population forecast method; (2) training in the statistical language "R" for demographic analysis. |  |  |
| 4812 | Request #4812 ? Capacity development support to the Government of Pakistan through amplification of technical advice by UNDP Pakistan through a Climate and SDG Financing Facility. Technical support focuses on enhancing the bankability of green investment projects prioritized by various stakeholders, principally departments that develop Public-Private Partnerships for tendering and financing. The technical assistance includes reviewing feasibility studies on various climate investments, convening workshops and government-investor dialogues to build local capacities in private SDG investment, and policy engagement with federal and provincial planning and economic development chiefs on building systematic approaches to SDG investment pipelining and integration of SDGs into planning and financing processes. Additionally, support is being provided to the Government of Pakistan to mobilize private financing for SDG-aligned projects and to leverage its participation in the 10th SDG Investment Fair. | Completed | Financing for Sustainable Development Office | 31 Oct 2023 | 31 Oct 2023 | 31 Jul 2025 | Ammara Durrani ¦ ammara.durrani@undp.org | Capacity development support to the Government of Pakistan through amplification of technical advice by UNDP Pakistan through a Climate and SDG Financing Facility. Technical support focuses on enhancing the bankability of green investment projects prioritized by various stakeholders, principally departments that develop Public-Private Partnerships for tendering and financing. The technical assistance includes reviewing feasibility studies on various climate investments, convening workshops and government-investor dialogues to build local capacities in private SDG investment, and policy engagement with federal and provincial planning and economic development chiefs on building systematic approaches to SDG investment pipelining and integration of SDGs into planning and financing processes. Additionally, support is being provided to the Government of Pakistan to mobilize private financing for SDG-aligned projects and to leverage its participation in the 10th SDG Investment Fair. |  |  |
| 4760 | Request #4760 ? Request from that Asia-Pacific regional office of UNFPA for a joint DESA-UNFPA-US Census Bureau regional workshop on population projections to take place in Thailand, 16-20 October 2023. | Completed | Population Division | 25 Aug 2023 | 12 Oct 2023 | 20 Oct 2023 | Christophe Lefranc ¦ lefranc@unfpa.org | Request from that Asia-Pacific regional office of UNFPA for a joint DESA-UNFPA-US Census Bureau regional workshop on population projections to take place in Thailand, 16-20 October 2023. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4726 | Request #4726 ? DPIDG was requested by Mr. Shah Nasir Khan, Head, UNRCO in Pakistan - Changing mindset courses gaining grounds now, we have been requested by Civil Services Academy to deliver the workshop (4 days) for Middle Career Management Course . | Completed | Division for Public Institutions and Digital Government | 01 Nov 2022 | 26 Jan 2023 | 27 Jan 2023 | Shah Nasir Khan, UNRCO ¦ shah.nasir@un.org | DPIDG was requested by Mr. Shah Nasir Khan, Head, UNRCO in Pakistan - Changing mindset courses gaining grounds now, we have been requested by Civil Services Academy to deliver the workshop (4 days) for Middle Career Management Course . |  |  |
| 4731 | Request #4731 ? FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. | Completed | Financing for Sustainable Development Office | 31 Jan 2022 | 01 Jun 2022 | 12 Jan 2022 | Daniel Platz ¦ platz@un.org | FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. |  | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. / requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 4750 | Request #4750 ? DPIDG was requested by the RCO to collaborate in the development of a toolkit on strategic foresight to support the Government of Pakistan to address climate change and flooding. / https://publicadministration.desa.un.org/events/workshop-strategic-foresight-pakistan-developing-vision-chitral | Completed | Division for Public Institutions and Digital Government | 13 Oct 2022 | 15 Nov 2022 | 28 Apr 2023 | Shah Nasir ¦ shah.nasir@un.org | DPIDG was requested by the RCO to collaborate in the development of a toolkit on strategic foresight to support the Government of Pakistan to address climate change and flooding. / https://publicadministration.desa.un.org/events/workshop-strategic-foresight-pakistan-developing-vision-chitral |  |  |
| 4170 | Request #4170 ? The National Management College of the Government of Pakistan requested DPIDG's support in strengthening capacities of public servants to promote new mindsets for SDG implementation through the organization of a training of trainers on the same topic and expert participation in a training workshop on Changing Mindset in Public Institutions to realize the 2030 Agenda in Pakistan to be held in August 2022. The training is a follow up to the workshop held by DPIDG for the highest level of public officials in Pakistan held in January 2022 and targeted to middle management and young public servants. / DPIDG will train the RCO to deliver the workshop with the National Management College. | Completed | Division for Public Institutions and Digital Government | 19 May 2022 | 21 Aug 2022 | 22 Aug 2022 | Afaqi Muhammad Jamil ¦ j.afaqi@gmail.com | The National Management College of the Government of Pakistan requested DPIDG's support in strengthening capacities of public servants to promote new mindsets for SDG implementation through the organization of a training of trainers on the same topic and expert participation in a training workshop on Changing Mindset in Public Institutions to realize the 2030 Agenda in Pakistan to be held in August 2022. The training is a follow up to the workshop held by DPIDG for the highest level of public officials in Pakistan held in January 2022 and targeted to middle management and young public servants. / DPIDG will train the RCO to deliver the workshop with the National Management College. |  |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4073 | Request #4073 ? DPIDG was requested by the D-8 (also known as Developing-8, which is an organization for development cooperation among Bangladesh, Egypt, Indonesia, Iran, Malaysia, Nigeria, Pakistan and Turkey) to provide support in strengthening their capacities to promote digital government. / Event page: https://publicadministration.desa.un.org/en/news-and-events/calendar/ModuleID/1146/ItemID/3123/mctl/EventDetails | Completed | Division for Public Institutions and Digital Government | 30 Dec 2021 | 15 Mar 2022 | 16 Mar 2022 | Mr. Ali Taha KoÃ§, c/oMuhammed Enes Uslu ¦ enes.uslu@mfa.gov.tr | DPIDG was requested by the D-8 (also known as Developing-8, which is an organization for development cooperation among Bangladesh, Egypt, Indonesia, Iran, Malaysia, Nigeria, Pakistan and Turkey) to provide support in strengthening their capacities to promote digital government. / Event page: https://publicadministration.desa.un.org/en/news-and-events/calendar/ModuleID/1146/ItemID/3123/mctl/EventDetails | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 3651 | Request #3651 ? DPIDG was requested by the National School of Public Policy (NSPP) of the Government of Pakistan to conduct a training on "Changing Mindsets in Public Institutions to Realize the 2030 Agenda in Pakistan". The training was held in close collaboration with the UN Resident Coordinator Office in Pakistan. | Completed | Division for Public Institutions and Digital Government | 16 Apr 2021 | 15 Oct 2021 | 31 Dec 2021 | Dr. Jamil Afaqi ¦ j.afaqi@gmail.com | DPIDG was requested by the National School of Public Policy (NSPP) of the Government of Pakistan to conduct a training on "Changing Mindsets in Public Institutions to Realize the 2030 Agenda in Pakistan". The training was held in close collaboration with the UN Resident Coordinator Office in Pakistan. |  |  |
| 3462 | Request #3462 ? Direct demand from Member States submitted through the UNDP Country Offices and the UNDP Bangkok Regional Hub / In 2020 EAPD transitioned to remote delivery of its introductory Climate, Land, Energy and Water systems training programs. RPTC project SB-001377.58 funded the development of virtual training materials and in collaboration with UNDP this was delivered to participants from the Asia-Pacific region. 49 trainees from 8 countries completed the first part of the training program and teams for each of these countries are expected to finalize preliminary CLEWs analysis and present it at a policy dialogue event scheduled for February 24-25 2021. This project would support the finalization of the Asia-Pacific training course as well as follow up activities such as model improvements, reporting and finalization of policy papers. | Completed | Economic Analysis and Policy Division | 12 Feb 2021 |  | 31 Dec 2021 | Thomas Alfstad ¦ thomas.alfstad@un.org | Direct demand from Member States submitted through the UNDP Country Offices and the UNDP Bangkok Regional Hub / In 2020 EAPD transitioned to remote delivery of its introductory Climate, Land, Energy and Water systems training programs. RPTC project SB-001377.58 funded the development of virtual training materials and in collaboration with UNDP this was delivered to participants from the Asia-Pacific region. 49 trainees from 8 countries completed the first part of the training program and teams for each of these countries are expected to finalize preliminary CLEWs analysis and present it at a policy dialogue event scheduled for February 24-25 2021. This project would support the finalization of the Asia-Pacific training course as well as follow up activities such as model improvements, reporting and finalization of policy papers. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.30 | Regional Training Workshop on the Implementation of the International Recommendations for the 2030 Round of Population and Housing Censuses in Asia | SD | 30 Sept 2026 | 30 Sept 2026 | $47,924 | Bangladesh, Bhutan, Cambodia, Democratic Republic of Timor-Leste, Democratic Socialist Republic of Sri Lanka, India, Indonesia, Lao People's Democratic Republic, Malaysia, Maldives, Mongolia, Nepal, Pakistan, Philippines, Thailand, Viet Nam | Country standardized: 'Lao People’s Democratic Republic' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Timor Leste' -> 'Democratic Republic of Timor-Leste'. | Proposal past due |
| SB-001376.99.99.31 | Securing the Future of Demographic and Health Data: Country Pathways and a Global Blueprint / | SD | 30 Sept 2026 | 31 Dec 2026 | $86,714 | Bangladesh, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Jordan, Kenya, Malawi, Mozambique, Nepal, Nigeria, Pakistan, Papua New Guinea, Senegal, Tajikistan | Region standardized: 'global' -> 'Global'. |  |
| SB-001374.99.40 | Strengthening Artificial Intelligence (AI) Capabilities and Governance for Sustainable Digital Transformation in Africa and Asia-Pacific | DPIDG , DSDG | 30 Sept 2026 | 30 Sept 2026 | $87,767 | Algeria, Burkina Faso, Burundi, Cambodia, Democratic Socialist Republic of Sri Lanka, Gambia, Guinea-Bissau, Kenya, Lao People's Democratic Republic, Pakistan, Rwanda, Sierra Leone, Togo, Uganda, United Republic of Tanzania, Uzbekistan, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Terminal Evaluation of Project (Final Report) DA13 INFF Project 2124A ‘Towards Integrated National Financing Framework’ | 2025 | FSDO; EAPD | Belarus, Burkina Faso, Costa Rica, Dominican Republic, Egypt, Jordan, Kyrgyzstan, Pakistan, Samoa, Zambia | - Project conceptualisation should be preceded by a scoping session and/or planning meeting between the executing entities and the cooperating entities, to establish synergies, enhance relevance, and minimise risk, including the possibility for and perception of duplicated efforts. / - Clarified roles and responsibilities at the level of project management and activity coordination should be established to allow for efficient oversight throughout the implementation timeframe. / - Guidance documents on the INFF methodology should provide detailed, step-by-step guidelines that can be easily contextualised by the implementing country. / - The FINS project should be scaled up to provide post-project technical assistance to target and non-target countries in response to their requests for context-specific support for INFF implementation. / - A strengthening of the process for finalising and approving the project results framework should be initiated, to ensure that appropriate results targets and performance measurement indicators are established to increase the usefulness of achieved results. | - The project development phase needs to be reliably informed by a detailed assessment of risk, parallel interventions, and the contextual situation in the countries of intervention focus. / - Efficient project oversight is dependent on a clarified overview of roles and responsibilities at the level of project management. / - The effective application of the INFF methodology at the country-level requires detailed step-by-step guidelines to inform contextualisation. / - The ownership of the INFF methodology by national political leadership contributes towards a demand-driven process that is critical for effective implementation. / - A flexible design combined with strategic partnerships contributes towards stronger impact and the maximisation of efficiency and synergies. / - Digital platforms and data infrastructure support effective implementation and enhance knowledge-exchange and sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/2124A SB-016729.01 INFF/Evaluation report/REVISED Final Evaluation Report_INFF Evaluation_7OCT2025.docx |  |  |
| Mobilizing Science, Technology and Innovation in developing countries for the SDGs | 2022 | DSDG | Belgium, Brazil, Cambodia, China, Ethiopia, Ghana, India, Japan, Kenya, Korea, Madagascar, Mozambique, Myanmar, Pakistan, Philippines, Rwanda, Serbia, Thailand, Uganda, United States of America, Zambia | - DESA should ensure that projects are based on clear objectives and SMART, relevant indicators which better help measure the impact of activities. / - DESA should ensure regular and efficient monitoring throughout the project, based on thorough monitoring plans. / - DESA should ensure the continuation of the Innovation Competition and participation in the STI Forum for the winners, and develop a longer term programme of Capacity Building and support for these winners. / - DESA should build on the Capacity Building events, Study Visits, STI Roadmaps work and the Ghana Pilot Programme, which were all highly relevant to STI in developing countries. / - DESA should focus on strengthening the OLP, which currently has a low level of relevance to STI in developing countries. DESA should revisit the Independent Technical Assessment and R4D’s recent report ‘UN 2030 Connect Report’ and integrate the prototypes into the OLP. / - If the OLP and associated capacity building activities are to continue, DESA should look carefully at the human and financial resources behind the work, ensuring that there is enough capacity to deliver meaningful results. DESA should consider the financial recommendations made in the Independent Technical Assessment. Resources available must match the ambition for the work, and the level of ambition should be clarified asap. / - Any future project should include longer term support for innovators on the ground, over a period of at least a year. This could focus on the winners of Innovation Competitions. / - Any future project should build on the successes and the lessons learned of the Ghana Pilot Project, which could be scaled to other countries in partnership with R4D. / - DESA should improve the ongoing monitoring around such projects, strengthening the indicators (ensure SMART and relevant indicators) and ensuring that questionnaires are provided to participants following relevant activities (Capacity Building sessions, Study Visits etc). / - DESA should spend more time persuading and convincing partners of the value of integrating their databases with that of the OLP, in order to address the perceived incoherence with OLP partners. / - DESA and partners should consider the viability of one overarching STI project / work stream which incorporates the various streams of work being undertaken - the STI Forum, STI Roadmaps for SDGs, 2030 Connect, Capacity Building etc. The possibility of a joint funding mechanism – an STI Trust Fund – should be explored in order to reduce inefficiencies. / - DESA should allocate meaningful human resources (at least 60% of a full time role) to ensure the success of the OLP and associated Capacity Building activities. / - DESA should ensure that resources allocated to the OLP match the ambition for the OLP. / - DESA should consider allocating more funds for longer term Capacity Building support to innovators across target countries. / - DESA should consider replicating / adapting the relationship with R4D, recognising the importance of having local partners to work with local innovators. This could either be done with R4D, other relevant CSOs or UNCTs (UN Country Teams). / - DESA should ensure there is enough time available for meaningful work to be completed, avoiding last minute rushes. / - DESA should systematically work through tools like Exit strategies, succession planning and cases for financial support before the end of a project, in order to ensure sustainability, whether a project is designed to continue or not. / - DESA, with the IATT, should revisit the Independent Technical Assessment, as well as the recent recommendations by R4D for the OLP, in order to be very clear about the ambition and strategic direction of the OLP before developing the case for support. / - Given the clear mandate provided by MS for the OLP, DESA should attempt to secure a mixture of UN regular budget and voluntary/extra-budgetary funds to finance the OLP. / - DESA should ensure that capacity building activities take place over a longer period, and provide more sustained support for innovators. This should be built into the case for support. / - The UN should integrate the principle of Leave No-One Behind into all its STI related work, ensuring that it does not inadvertently enhance the digital divide. This could be done in the context of this project by offering capacity building activities in different languages, offering interpretation, and ensuring translation of the OLP. / - DESA should consider scaling up the Ghana Pilot Project into other countries, specifically the Technical Support offered to local innovators. / - DESA should build on the momentum around the STI Roadmaps for SDGs and investigate whether a coherent package of work can be built around the Roadmaps, the OLP and the capacity building activities. / - DESA and OICT should consider structuring the OLP (specifically the Search Engine) around the SDGs in order to facilitate closer linkages between STI and HR & GE. / - DESA, and the UN more widely, should strengthen the focus on HR & GE in the project design and monitoring, including concrete details of how HR & GE issues will be addressed. UNEG’s guidance on this should be considered. / - DESA, and the UN more widely, should respect the SDG principle of LNOB by ensuring Capacity Building activities include interpretation, and official sites are available in at least the 6 official languages of the UN. / - DESA should consider contributing to tackling the existing gender inequality in STI by insisting on having at least 50% of women as speakers, moderators and participants in events. / - DESA should incorporate HR & GE specific indicators in its project design. Again, UNEG’s guidance on this should be considered. / - DESA should commit to gathering disaggregated data throughout its projects, starting with clear participant lists for every activity. / - The UN PDF should ensure that the recently developed form which collects HR & GE data is consistently used across all projects which it supports. / - DESA should build on the good practise of the Study Visits, Capacity Building Sessions and Ghana Project, linking STI to specific SDGs and gender issues in order to ensure a meaningful focus on HR & GE. / - DESA should use its position as implementer of this project and Co-Convenor of the IATT to work closely with the IATT to consider the ambition and funding for the OLP, ensuring coherence with the mandate given by MS in Agenda 2030, the AAAA and the Independent Assessment. / - DESA should continue the practise of piggybacking on other meetings and cost-sharing when organising activities. | - The project design could have been improved by developing stronger and more relevant indicators which better help measure the impact of the activities, and by ensuring regular and efficient monitoring throughout the project. / - Insufficient human and financial resources can significantly limit the effectiveness and efficiency of project implementation. / - A lack of clear exit planning, succession planning, and fundraising strategy can undermine the sustainability of project outcomes. / - Longer-term engagement and support for innovators, rather than one-off events or competitions, are valued and more likely to lead to sustained impact. / - Capacity building activities are more inclusive and effective when offered in multiple languages and with interpretation, supporting the Leave No-One Behind principle. / - Partnerships with local organizations, such as R4D in Ghana, enhance the relevance and effectiveness of capacity building for local innovators. / - Integrating gender and human rights considerations from the project design stage, with specific indicators and disaggregated data, leads to better outcomes and more inclusive participation. / - Administrative and technical barriers to integrating partner databases can undermine the effectiveness and coherence of online platforms. / - Piggybacking on existing meetings and cost-sharing with partners increases efficiency and reach. / - Clear political mandates and alignment with broader UN strategies facilitate project relevance and coherence, but must be matched by adequate resources and stakeholder engagement. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2016/PDF-2016-03 DSD internal STI/Reports/Final report & Eva/fisrt ver. 18 Mar 22/STI Evaluation LW final.pdf | Country standardized: 'USA' -> 'United States of America'. | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation | 2021 | DSDG | Algeria, Argentina, Austria, Bolivia (Plurinational State of), Bosnia and Herzegovina, Bulgaria, Colombia, Ecuador, Ethiopia, Georgia, Ghana, Guyana, Honduras, India, Italy, Kenya, Lebanon, Malawi, Morocco, Nauru, Niger, North Macedonia, Pakistan, Papua New Guinea, Poland, Portugal, Samoa, Seychelles, United Arab Emirates, United Kingdom of Great Britain and Northern Ireland, Zambia | - Future similar projects should apply a Results-Based Management approach, developing an M&E framework, plan, and data collection tools that articulate instrumental and transformational changes rather than processes. / - Additional resources should be mobilized to ensure follow-up and implementation of the commitments secured in the global roadmap and in the Energy Compacts, starting with pilot projects to determine their viability and scalability. / - Future similar projects should include studies on Cost-Benefit Analysis to determine the viability and scalability of policy changes, ranking options in the Energy Compacts according to their costs and benefits to society. / - More staff wholly dedicated to the project should be planned for at the conceptualization stage, including roles for communications and project management assistance, and a project steering committee to ensure recommendations for course corrections are followed. / - Future projects should develop a clear partnership strategy to guide implementers on where to invest in collaboration for the greatest value to the organization. / - The composition of the global Technical Advisory Group (TAG) should be replicated and cascaded to regional and national levels to ensure continuity and nuanced specificities beyond the project’s shelf life. / - Future projects should leverage United Nations Information Centers (UNICs) to develop and implement coordinated communications strategies for Member States, amplifying project achievements at the local level. | - The joint production and dissemination of knowledge products laid a strong foundation for sustainability, scaling up, replication, and future programming, increasing knowledge and capacities for accountability. / - Synergistic partnerships and multi-stakeholder participation facilitated ownership, sustainability, and coherence between national planning processes, enhancing coordination among line ministries for timely VNR production. / - Upstream activities allowed the project to adapt to challenges such as Covid-19, and partnering with the public sector leveraged government influence for mainstreaming SDG7 implementation. / - Engagement with the private sector was strategic, as private sector input and financial commitments in the Energy Compacts are essential for accelerating SDG7 implementation. / - The project was initially thinly staffed, but hiring a dedicated Project Officer after commencement improved implementation; future projects should plan for adequate dedicated staffing from the outset. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2017/2017-02 DSD SDG7/Reports/Evaluation/Final_Dec 18th_UNDESA_Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Achieving SDGs and Ending Poverty through Universal Social Protection | 2021 | DISD | Cambodia, Pakistan | - Careful thought be given to renewing the ILO/UNDESA partnership, possibly through a Phase 2, to consolidate and build on the progress made, making full use of the learning tools developed and ensuring the full engagement of the People’s Republic of China. / - Link future partnership to the Plan of Action on universal social protection called for by the International Labour Conference. / - Edit and purpose the research papers for teaching. / - Make progress in the streamlining of bureaucratic procedures between agencies. / - Ensure good use of the knowledge products – the research papers and the modules – to support the ILO’s Plan of Action on universal social protection systems. | - The different institutional procedures of the two agencies created bottlenecks, particularly in reporting and budget adjustments, but these were overcome and relations between the agencies remain excellent. / - Learning from this partnership constitutes the basis for even more effective cooperation between UN agencies. / - The UNDESA/ILO partnership worked well, playing to the strengths of each agency, and could be a model for collaboration between UN agencies in the future. / - The modifications required by Covid-19, such as moving training online and developing national training manuals, brought cost benefits and a beneficial focus on national experience. / - Sustainability depends on the political commitment of governments and the continued technical support to national institutions. / - The full impact of the project will only become evident in years to come as processes set in train come to fruition and as political leaders make decisions about resourcing social protection. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2019/PDF-2019-02 Strategic/Inst.s/CDPMO/A1.1/Proj.s/PDF-SDG-2018-04 DESA-ILO/Final Evaluation_internal rev..pdf |  |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Developing a Public‐Private Partnerships (PPP) and Infrastructure Financing Network in Asia and the Pacific | 2022 |  | Afghanistan, Bangladesh, Cambodia, Democratic Republic of Timor-Leste, Fiji, India, Indonesia, Kazakhstan, Kyrgyzstan, Lao People's Democratic Republic, Malaysia, Mongolia, Nepal, Pakistan, Papua New Guinea, Philippines, Russian Federation, Tajikistan, Thailand, Türkiye, Viet Nam | - The project team should further clarify the end-purpose of the Network to its key internal and external stakeholders, establish a clear theory of change and results matrix, and set measurable targets to assess its performance. / - Increase attention to collecting data on key outcomes and impacts to document and learn about changes occurring at different levels, and develop a clear M&E plan involving national partners. / - Further incorporate human rights, gender equality, and related issues in key priority areas by systematically collecting disaggregated data and arranging training on mainstreaming gender and human rights issues in project design and implementation. / - Seek additional resources for building on the results achieved so far and diversify the donor base for sustainability and expansion. / - Enhance collaboration with other ESCAP divisions and sections to offer deeper expertise and build on collaboration with related units and networks such as the ESCAP Sustainable Business Network (ESBN). | - Involving private sector entities and carefully selecting local and international partnerships contributed to the successful establishment and operationalization of the network and should be replicated in other projects where relevant. / - Remote collaboration, while necessary during the pandemic, limited deeper engagement critical for higher-order outcomes such as building trust and making investments; future phases should emphasize site visits and in-person networking to facilitate more meaningful connections. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2018/PDF-2018-06 ESCAP/Reports/Final Report & Evaluation/PPP Project Evaluation Report _formatted 17Nov.pdf | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | evaluations.xlsx row 214: Divisions not provided. |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 3 | evaluations.xlsx row 214: Divisions not provided. |
| 4 | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 8 | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. |
| 9 | requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 10 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 11 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 12 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 13 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 42 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 43 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 44 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 45 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 46 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 56 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |