Peru

Americas

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Peru is presented in this country card as part of Americas, with Peru also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Peru highlights 8 projects for Peru, including 2 active or planned projects for Peru and 5 completed or closed projects for Peru.

For Peru, the report includes 14 requests for Peru, 4 RPTC proposals for Peru, 2 RPTC activities for Peru, and 1 travel records for Peru. Financially, Peru shows USD 7,063,296 in project budget, $93,897 in proposal planned budget, and $201,588 in consumed RPTC activity budget for Peru.

The main organizational coverage for Peru points to Division for Inclusive Social Development, Division for Sustainable Development Goals, Financing for Sustainable Development Office, FSDO. Activity records for Peru list 1,381 participants, including 709 women participants, the current quality review for Peru includes 67 data quality notes. Current highlights for Peru include a request focus for Peru: Request #5567 ? The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics.

      

      

      
Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives.

      

      

      
The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions.

      

      

      
ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. 

      

      

      
The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026.

      

      

      
Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness.; an RPTC proposal focus for Peru: Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development; an activity focus for Peru: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 8 |
| Project budget | USD 7,063,296 |
| Requests | 14 |
| RPTC proposals | 4 |
| Proposal planned budget | $93,897 |
| RPTC activities | 2 |
| Consumed RPTC budget | $201,588 |
| Activity participants | 1,381 |
| Women participants | 709 |
| Travel records | 1 |
| Evaluations | 7 |
| Data quality notes | 67 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making |  | country | Statistics Division | Active | 01 Jul 2025 | 30 Jun 2027 | USD 2,000,000 | Costa Rica, Morocco, Peru, Senegal |  |  |
| Enhancing national capacities for unleashing full potentials of micro-, small- and medium-enterprises (MSMEs) in achieving sustainable development goals in developing countries | 2016-04 | country | Division for Sustainable Development Goals | Closed | 31 May 2017 | 31 Dec 2021 | USD 1,652,296 | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Enhancing the resilience, accessibility, and sustainability of infrastructure assets in developing countries along the Belt and Road initiative in support of the 2030 Agenda |  | country | Financing for Sustainable Development Office | Closed | 01 Feb 2022 | 31 Jan 2025 | USD 0 | Costa Rica, Gambia, Kenya, Lao People's Democratic Republic, Nepal, Peru | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Enhancing the resilience, accessibility, and sustainability of infrastructure assets in developing countries along the Belt and Road initiative in support of the 2030 Agenda ¦ 2022-02-01T00:00:00 ¦ [no project code]': Budget Budget is blank. |
| Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people | 2629C | country | United Nations Forum on Forest | Active | 02 Feb 2026 | 31 Dec 2029 | USD 634,400 | Bolivia (Plurinational State of), Colombia, Guyana, Peru |  |  |
| Monitoring progress towards sustainable forest management | 1617F | country | United Nations Forum on Forest | Closed | 16 Jun 2020 | 19 Dec 2020 | USD 709,000 | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines |  |  |
| Enhancing migration data to support evidence-based policymaking and the achievement of the 2030 Agenda for Sustainable Development in Africa and Latin America and the Caribbean |  | country | Population Division | Under development | 01 Jan 2027 | 31 Dec 2030 | USD 911,000 | Jamaica, Kenya, Malawi, Mexico, Mozambique, Peru |  |  |
| Policies and programmes for youth with disabilities in Latin America | 1819A | country | Division for Inclusive Social Development | Closed | 01 Jan 2018 | 31 Dec 2021 | USD 524,600 | Argentina, Ecuador, Peru |  |  |
| Strengthening capacity of National Tax Administrations in developing countries to effectively negotiate and apply double tax treaties for financing of sustainable development | 1415A | country | Financing for Sustainable Development Office | Closed | 15 Jan 2020 | 18 Sept 2020 | USD 632,000 | Barbados, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Jamaica, Mexico, Nicaragua, Panama, Paraguay, Peru, Trinidad and Tobago, Uruguay, Venezuela (Bolivarian Republic of) |  |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5567 | Request #5567 ? The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 Dec 2026 | Kimberly Bordon ¦ kbordon@aladi.org | The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. |  |
| 5373 | Request #5373 ? There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 May 2026 | Kimberly Bordon ¦ kbordon@aladi.org | There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. |  |
| 5129 | Request #5129 ? The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Completed | Population Division, Statistics Division | 28 Mar 2025 | 16 Jun 2025 | 20 Jun 2025 | Maria Isabel Cobos ¦ cobos@un.org | The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Country standardized: 'Turkey' -> 'Türkiye'. |
| 5136 | Request #5136 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. | Under consideration | Statistics Division | 03 Mar 2025 | 17 Mar 2025 | 27 May 2025 | Pedro Farinas ¦ farinas@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. |  |
| 5106 | Request #5106 ? During this project, UNSD plans to update both apps, Android and iOS, with the 2024 data that are already available and whose content will fully resemble the printed version of the World Statistics Pocketbook 2024. For those SDG indicators included, a link to SDG data and metadata from the app will be added. In order to achieve this, UNSD plans to fix some shortcomings that external and internal users have identified in the SDG user interface including the API and other relevant parts of the system such as those related to the SDG metadata. These fixes will facilitate the integration and use of the SDG data and metadata links in the UNdata apps. / The budget will cover the contractual services needed to update the UNdata apps and fix some components in the SDG infrastructure, including SDG metadata. / UNSD will utilize this use case of the integration of SDG data and metadata into statistical outputs via SDMX in its forthcoming SDMX Regional Training Workshop organized and hosted by OECD in collaboration with other international agencies, including UNSD, SESRIC, ESCAP and UNESCO that will take place in Istanbul, TÃ¼rkiye, on 4-6 December 2024. Participants will be trained in the extraction of SDG data and metadata and its integration into digital products such as the UNdata apps. | Completed | Statistics Division | 25 Oct 2024 | 01 Nov 2024 | 31 Dec 2024 | Harumi Shibata Salazar ¦ shibata@un.org | During this project, UNSD plans to update both apps, Android and iOS, with the 2024 data that are already available and whose content will fully resemble the printed version of the World Statistics Pocketbook 2024. For those SDG indicators included, a link to SDG data and metadata from the app will be added. In order to achieve this, UNSD plans to fix some shortcomings that external and internal users have identified in the SDG user interface including the API and other relevant parts of the system such as those related to the SDG metadata. These fixes will facilitate the integration and use of the SDG data and metadata links in the UNdata apps. / The budget will cover the contractual services needed to update the UNdata apps and fix some components in the SDG infrastructure, including SDG metadata. / UNSD will utilize this use case of the integration of SDG data and metadata into statistical outputs via SDMX in its forthcoming SDMX Regional Training Workshop organized and hosted by OECD in collaboration with other international agencies, including UNSD, SESRIC, ESCAP and UNESCO that will take place in Istanbul, TÃ¼rkiye, on 4-6 December 2024. Participants will be trained in the extraction of SDG data and metadata and its integration into digital products such as the UNdata apps. |  |
| 5092 | Request #5092 ? The Workshop is being organized and hosted by OECD in collaboration with other international agencies, such as UNSD, SESRIC, ESCAP and UNESCO. It is planned to take place in Istanbul, TÃ¼rkiye, on 4-6 December 2024 (3 days). The Workshop will bring together statisticians and IT specialists from various national statistical offices already familiar in the use of SDMX and data modelling as part of their work. Participants will learn to optimise a data model for effective dissemination, enrich it with relevant reference metadata, and establish automated processes for future data updates. The workshop will facilitate the dissemination and reporting of statistical data including the SDGs. | Completed | Statistics Division | 04 Oct 2024 | 04 Dec 2024 | 06 Dec 2024 | Harumi Shibata Salazar ¦ shibata@un.org | The Workshop is being organized and hosted by OECD in collaboration with other international agencies, such as UNSD, SESRIC, ESCAP and UNESCO. It is planned to take place in Istanbul, TÃ¼rkiye, on 4-6 December 2024 (3 days). The Workshop will bring together statisticians and IT specialists from various national statistical offices already familiar in the use of SDMX and data modelling as part of their work. Participants will learn to optimise a data model for effective dissemination, enrich it with relevant reference metadata, and establish automated processes for future data updates. The workshop will facilitate the dissemination and reporting of statistical data including the SDGs. |  |
| 5083 | Request #5083 ? Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. | Completed | Statistics Division | 20 Sept 2024 | 21 Sept 2024 | 31 Jan 2025 | Camilo Andres Mendez Coronado ¦ camendezc@dane.gov.co | Camilo AndrÃ©s MÃ©ndez C, Head of International Affairs at Colombia's National Statistical Office (DANE), requests support from the United Nations Statistics Division to help upgrade the data science skills and capabilities in DANE and other National Statistical Offices in Latin America. The request is made in light of rapidly advancing trends in data science and emerging technologies. |  |
| 5070 | Request #5070 ? The tenth meeting of the EGES encouraged countries to invest through their national statistical systems in the development of climate change statistics, by designing special surveys or other data collection tools, and to include climate and environment-related questions in the PHC, agriculture censuses, household surveys (household income), censuses/surveys of economic activities, etc. UNSD is offering support in this area, by reviewing the experiences from countries who have advanced on collected climate change statistics via censuses and surveys (UK, Netherlands, Nepal, Tanzania); preparing a draft core set of suitable questions and assisting/advising countries which are currently preparing their own climate change surveys. The interest and demand for such support is growing, e.g. Uganda, Peru, Cameroon, Suriname and others are planning or already developing climate change surveys and will benefit from capacity development support along with Uganda. | Under consideration | Statistics Division | 17 Sept 2024 |  |  | Keith Ahumuza ¦ keith.ahumuza@ubos.org | The tenth meeting of the EGES encouraged countries to invest through their national statistical systems in the development of climate change statistics, by designing special surveys or other data collection tools, and to include climate and environment-related questions in the PHC, agriculture censuses, household surveys (household income), censuses/surveys of economic activities, etc. UNSD is offering support in this area, by reviewing the experiences from countries who have advanced on collected climate change statistics via censuses and surveys (UK, Netherlands, Nepal, Tanzania); preparing a draft core set of suitable questions and assisting/advising countries which are currently preparing their own climate change surveys. The interest and demand for such support is growing, e.g. Uganda, Peru, Cameroon, Suriname and others are planning or already developing climate change surveys and will benefit from capacity development support along with Uganda. |  |
| 4779 | Request #4779 ? UNSD is responding to the request put forward during the Statistical Commission held in New York from 28 February â€“ 3 March 2023 by Member States in written comments and oral intervention during the session on Global indicator framework for the Sustainable Development Goals and targets of the 2030 Agenda for Sustainable Development. | Completed | Statistics Division | 28 Feb 2023 | 28 Feb 2023 | 26 Feb 2024 | Yongyi Min ¦ min3@un.org | UNSD is responding to the request put forward during the Statistical Commission held in New York from 28 February â€“ 3 March 2023 by Member States in written comments and oral intervention during the session on Global indicator framework for the Sustainable Development Goals and targets of the 2030 Agenda for Sustainable Development. |  |
| 4231 | Request #4231 ? The Global Set of Climate Change Statistics and Indicators was adopted at the 53rd session of the United Nations Statistical Commission in March 2022 as the framework for climate change statistics and indicators to be used by countries when preparing their own sets according to their individual concerns, priorities and resources. To put the Global Set to work, UNSD proposed a number of activities which are included in section V of the Report of the Secretary General to the 53rd Session of the Statistical Commission. Many countries expressed their support to the proposed activities via written and oral statements. More than 40 countries submitted such statements of which about half underlined that they need capacity development support from UNSD. This includes the need for training on applying the Global Set; the need for national missions; interest in receiving on-line support; and guidance for developing national surveys on climate change statistics. In addition, as specified in the Report of the Statistical Commission, the international statistical community is urged to expand its capacity development efforts with regard to climate change statistics by fostering closer collaboration and coordination among the multiple agencies involved in the process, and the donor community is urged to mobilize resources to enable capacity building in environment and climate change statistics in developing countries. | Completed | Statistics Division | 01 Jul 2022 | 01 Aug 2022 | 31 Dec 2022 | Peter Abad ¦ peter.abad@inei.gob.pe | The Global Set of Climate Change Statistics and Indicators was adopted at the 53rd session of the United Nations Statistical Commission in March 2022 as the framework for climate change statistics and indicators to be used by countries when preparing their own sets according to their individual concerns, priorities and resources. To put the Global Set to work, UNSD proposed a number of activities which are included in section V of the Report of the Secretary General to the 53rd Session of the Statistical Commission. Many countries expressed their support to the proposed activities via written and oral statements. More than 40 countries submitted such statements of which about half underlined that they need capacity development support from UNSD. This includes the need for training on applying the Global Set; the need for national missions; interest in receiving on-line support; and guidance for developing national surveys on climate change statistics. In addition, as specified in the Report of the Statistical Commission, the international statistical community is urged to expand its capacity development efforts with regard to climate change statistics by fostering closer collaboration and coordination among the multiple agencies involved in the process, and the donor community is urged to mobilize resources to enable capacity building in environment and climate change statistics in developing countries. |  |
| 3520 | Request #3520 ? The City of Lima wants to organize a voluntary local review and requested support from DESA. | Completed | Division for Sustainable Development Goals | 11 Feb 2021 | 11 Feb 2021 | 31 Mar 2021 | Gabriela Elgegren Vasquez ¦ gabriela.elgegren@undp.org | The City of Lima wants to organize a voluntary local review and requested support from DESA. |  |
| 3441 | Request #3441 ? Joint DESA-ECLAC initiative. Responding to a request from UN ECLAC on behalf of member states for training in forecasting the economic and fiscal impacts of population ageing. | Completed | Population Division | 19 Oct 2019 | 25 Nov 2019 | 27 Nov 2019 | Mr. Paulo Saad ¦ paulo.saad@un.org | Joint DESA-ECLAC initiative. Responding to a request from UN ECLAC on behalf of member states for training in forecasting the economic and fiscal impacts of population ageing. |  |
| 3435 | Request #3435 ? Joint DESA-ECLAC initiative in support of the Madrid International Plan of Action on Ageing (MIPAA). Held training workshop on forecasting the national economic and fiscal impacts of population ageing. | Completed | Population Division | 23 May 2019 | 09 Sept 2019 | 11 Sept 2019 | Mr. Paulo Saad ¦ paulo.saad@un.org | Joint DESA-ECLAC initiative in support of the Madrid International Plan of Action on Ageing (MIPAA). Held training workshop on forecasting the national economic and fiscal impacts of population ageing. |  |
| 2747 | Request #2747 ? Financial support from the GFFFN such as access existing and new financing mechanisms such as the Green Climate Fund | Completed | United Nations Forum on Forest | 09 May 2018 |  | 12 Dec 2024 | Gustavo Eduardo Mostajo Ocola ¦ cynga@serfor.gob.pe | Financial support from the GFFFN such as access existing and new financing mechanisms such as the Green Climate Fund |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001380.92 | Practical Workshops on the Negotiation of Tax Treaties – Seoul (2-6 November 2026) and Madrid (23-27 November 2026) | FSDO | 30 Sept 2026 | 31 Dec 2026 | $0 | Algeria, Bahamas, Belize, Côte d’Ivoire, Democratic Socialist Republic of Sri Lanka, Ghana, Guinea-Bissau, Guyana, Lao People's Democratic Republic, Lesotho, Mozambique, North Macedonia, Peru, Trinidad and Tobago, Tunisia, Zimbabwe | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashDESA' has non-numeric value 'USD XX,XXX to cover travel of FSDO staff and experts, and contractor services (for translation of training materials into Spanish for the Madrid workshop)'. / proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashOther' has non-numeric value 'Organzing partners will fund the travel of participants to the workshops.'. / proposals.xlsx record 'SB-001380.92¦row:48': 'Total Budget' is blank. |
| SB-001376.99.99.32 | Regional Workshop on the Implementation of the Revised MSITS 2026 | SD | 31 Dec 2026 | 31 Dec 2026 | $62,098 | Argentina, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Guyana, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay, Venezuela (Bolivarian Republic of) | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Venezuela' -> 'Venezuela (Bolivarian Republic of)'. | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| SB-001376.99.99.39 | International workshop on the measurement of SDG Indicator 5.4.1 and XXVII International Meeting on Gender Statistics | SD | 31 Dec 2026 | 31 Dec 2026 | $6,799 | Brazil, Chile, Colombia, Costa Rica, Democratic Republic of Timor-Leste, Dominican Republic, Ecuador, Grenada, Guatemala, Honduras, Lao People's Democratic Republic, Mexico, Morocco, Paraguay, Peru, Tunisia | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. / Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costConferenceServices' has non-numeric value '0¦¦0¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelConsultants' has non-numeric value '4,098¦¦4,098¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelParticipants' has non-numeric value '0¦¦0¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelStaff' has non-numeric value '2,701¦¦2,701¦¦$'. / proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'f_cashDESA' has non-numeric value 'US$ 6,799'. |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002088809 - Peru | 0002088809 | Past | Peru |  | DIVISION FOR INCLUSIVE SOCIAL DEVELOPMENT | DISD/XB_TO ATTEND COMMEMORATIVE EVENT 25TH ANNIVERSARY FIMI |  | 19 Jun 2025 | 23 Jun 2025 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries | 2021 | DSDG; CDPMO | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | - Build on the momentum and lessons from this Project in the design of a follow-on project. / - Ensure engagement at the senior policy level at project commencement and maintain or renew engagement as required to avoid loss of momentum. / - Include assistance for network mapping, activation, and strengthening in each country, with a project contacts database to support ongoing engagement. / - Invest in establishing and expanding the knowledge management aspects of the Project, including improved logical frameworks, performance indicators, and strengthened monitoring systems. / - Support critical pilot sub-projects with potential for both policy and inclusive MSME sector impact, ensuring sufficient resources and targeted technical support for implementation and scaling up. | - The Project entry point at a senior policy level activates national coordination and prioritization. / - A targeted, meso-level approach towards programming contributes towards a stronger MSME enabling environment. / - Active engagement and networking opportunities contribute to immediate and longer-term results, but contacts must be retained to maintain momentum. / - A flexible approach helps to optimize results, allowing activities to be adjusted to local context and requirements. / - National consultants and credible focal points in key ministries are important drivers of success. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2016-04_Eval_DSDG_17Mar22.docx | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'The Gambia' -> 'Gambia'. | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Monitoring Progress towards Sustainable Forest Management (2016-2019) | 2019 | UNFFS | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines | - The project document should be used as the reference as much as possible for the implementation and monitoring of the project. A provision for mid-term review is also worthwhile in future projects. / - The Project should maintain better coordination between the country national focal points and UNFF Secretariat, and among the pilot countries for inter-pilot country cross-fertilization of ideas and sharing of experiences in designing and operationalizing monitoring frameworks. / - The UNFF Secretariat should explore more effective cooperation and coordination with CPF members that are key forest-related data generators and users (e.g., FAO, Rio Convention Secretariats, and the International Tropical Timber Organization). / - Pilot countries should make every effort to continue moving forward in designing, improving and utilizing their national forest monitoring frameworks, based on the building blocks generated through the project. | - Developing monitoring frameworks would require a longer term commitment from both the project and pilot countries. / - The project intervention in a pilot country should not have ended after the national consultant’s study on ‘data sources and gaps’ and two national workshops; not having any follow-up process after the national workshops broke the momentum the project had built. / - Perhaps, limiting the number of pilot countries to a lower number in the project and increasing the duration of the project would have provided more resources and attention in going beyond the national studies and consultation workshops, leading to a successful monitoring framework development processes and models that can be scaled up to a larger number of countries. / - The project should be flexible for course correction based on the ground realities. Not being able to initiate project activities in all pilot countries simultaneously impacts not only the efficiency but the effectiveness of the project. / - The project should have an item in its key activities to synthesize the experiences from its pilot countries and present a toolkit of recommendations for developing, maintaining and utilizing a national monitoring framework to monitor progress on SFM in the country, and report to forest-related and relevant international and regional processes such as FAO/FRA, CBD, UNCCD, UNFCCC and UNFF. / - Maintaining record of participants of national workshops is crucial for project management and for gathering post-workshop feedback as an indicator of capacity building. / - If an evaluation-related activity (such as interviews, focus group or panel discussions) is to be attached to a future meeting or workshop, then it should be appropriately included in the programme of the meeting/workshop, and the participants should be notified in advance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/10th tranche/UNFF/UNFF Project Evaluation Report_24Dec2019.docx |  |  |
| Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues | 2014 | FSDO | Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay | - Ensure pilot countries have all necessary data available, including up-to-date and filtered taxpayer databases and appropriate sample weighting, before selection. / - Select countries that have not recently undergone major tax reforms to avoid distortion of TTCs due to adaptation processes. / - Include qualitative aspects such as psychological costs as part of non-economic costs in future TTCs studies to better understand results. / - Adapt survey implementation methods to the context (e.g., face-to-face vs. online) and include control questions to improve data quality. / - Encourage NTAs to seek synergies with other public institutions for information gathering and fieldwork support. | - Institutional support and commitment from NTAs are decisive factors for successful project implementation and sustainability. / - A thorough methodology that includes both administrative and compliance costs, considers the taxpayer cycle, and covers all relevant taxes is effective for TTC measurement. / - Allowing each country to choose its own survey method, considering size and cultural context, can improve implementation but may affect comparability. / - CIAT's coordination and reputation are critical for engaging countries and ensuring project sustainability. / - The methodology is generally easy to apply in interested countries, but successful implementation depends on institutional support and well-designed databases. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/ROA181-6B/Evaluation/Evaluation Report- FINAL.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Supporting Developing Countries Measure Progress towards Achieving a Green Economy | 2016 | UNSD | Bhutan, Chile, Colombia, Ecuador, Malaysia, Mongolia, Peru, Viet Nam | - Replicate the high rate of women's participation in workshops in other DESA projects. / - Avoid reducing project budgets after implementation has started; DESA Development Account Project Management Team in CDO should establish systems to prevent this. / - Highlight project results at the annual meetings of the High-Level Political Forum on Sustainable Development to publicize DESA/SD's work and engage policy makers. / - For future projects, consider engaging more consultants to match the number of project countries, to encourage wider sharing of ideas and innovative thinking. / - Promote stronger links between green economy indicators and indicators useful for follow-up of the SDGs and the 2030 Agenda for Sustainable Development. | - Workshops in all phases of the project were effective for knowledge sharing and experience exchange; future workshops should continue to emphasize this. / - Resource persons from DESA/SD, regional commissions, UN agencies, and other organizations contributed significantly to workshop quality. / - Involvement of regional commissions and other UN agencies contributed to both project success and sustainability of outcomes. / - The project strengthened regional networks of statisticians, increased intra-institutional and intra-regional cooperation, and raised the national profile of statistics. / - Using only one consultant for all technical assistance missions may have limited inter-regional experience sharing; involving more consultants could enrich interventions. / - Pairing resource countries with pilot countries facilitated knowledge sharing and is a best practice to replicate. / - Involving regional specialized agencies added value by providing technical assistance and supporting sustainability. / - Designating focal points in pilot countries to coordinate inputs and participation was productive and should be emulated in similar projects. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 211 - 8th tranche - Green Economy/Evaluation/Evaluation report/DA_GreenEcon_proj_eval_10Oct2016 R1.pdf |  |  |
| Monitoring Progress towards Sustainable Forest Management | 2019 | UNFFS | Ghana, Jamaica, Kenya, Mongolia, Peru, Philippines | - The project document should be used as the reference as much as possible for the implementation and monitoring of the project. A provision for mid-term review is also worthwhile in future projects. / - The Project should maintain better coordination between the country national focal points and UNFF Secretariat, and among the pilot countries for inter-pilot country cross-fertilization of ideas and sharing of experiences in designing and operationalizing monitoring frameworks. / - The UNFF Secretariat should explore more effective cooperation and coordination with CPF members that are key forest-related data generators and users (e.g., FAO, Rio Convention Secretariats, and the International Tropical Timber Organization). / - Pilot countries should make every effort to continue moving forward in designing, improving and utilizing their national forest monitoring frameworks, based on the building blocks generated through the project. | - Developing monitoring frameworks would require a longer term commitment from both the project and pilot countries. / - The project intervention in a pilot country should not have ended after the national consultant’s study on ‘data sources and gaps’ and two national workshops; not having any follow-up process after the national workshops broke the momentum the project had built. This should be a lesson to apply in designing future projects with similar themes. / - Perhaps, limiting the number of pilot countries to a lower number in the project and increasing the duration of the project would have provided more resources and attention in going beyond the national studies and consultation workshops, leading to a successful monitoring framework development processes and models that can be scaled up to a larger number of countries. / - The project should be flexible for course correction based on the ground realities. Not being able to initiate project activities in all pilot countries simultaneously, as was evident in this project, impacts not only the efficiency but the effectiveness of the project. / - The project should have an item in its key activities to synthesize the experiences from its pilot countries and present a toolkit of recommendations for developing, maintaining and utilizing a national monitoring framework to monitor progress on SFM in the country, and report to forest-related and relevant international and regional processes such as FAO/FRA, CBD, UNCCD, UNFCCC and UNFF. / - Maintaining record of participants of national workshops is crucial for project management and for gathering post-workshop feedback as an indicator of capacity building. / - If an evaluation-related activity (such as interviews, focus group or panel discussions) is to be attached to a future meeting or workshop, then it should be appropriately included in the programme of the meeting/workshop, and the participants should be notified in advance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FF/1617F SB-006014 10th tranche - Monitoring of Sus For Mgmt/Final evaluation/Report/UNFF Project Evaluation Report_24Dec2019.docx.pdf |  |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 3 | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 4 | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 8 | evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 10 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. |
| 11 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| 12 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costConferenceServices' has non-numeric value '0¦¦0¦¦$'. |
| 13 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelConsultants' has non-numeric value '4,098¦¦4,098¦¦$'. |
| 14 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelParticipants' has non-numeric value '0¦¦0¦¦$'. |
| 15 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'costTravelStaff' has non-numeric value '2,701¦¦2,701¦¦$'. |
| 16 | proposals.xlsx record 'SB-001376.99.99.39¦row:74': 'f_cashDESA' has non-numeric value 'US$ 6,799'. |
| 17 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashDESA' has non-numeric value 'USD XX,XXX to cover travel of FSDO staff and experts, and contractor services (for translation of training materials into Spanish for the Madrid workshop)'. |
| 18 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashGov' has non-numeric value 'N/A'. |
| 19 | proposals.xlsx record 'SB-001380.92¦row:48': 'f_cashOther' has non-numeric value 'Organzing partners will fund the travel of participants to the workshops.'. |
| 20 | proposals.xlsx record 'SB-001380.92¦row:48': 'Total Budget' is blank. |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 53 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 62 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 65 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 66 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 67 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |