Sao Tome and Principe

Africa | SIDS

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Sao Tome and Principe is presented in this country card as part of Africa, with Sao Tome and Principe also associated with an unspecified subregion and the SIDS grouping. The filtered data for Sao Tome and Principe highlights 2 projects for Sao Tome and Principe, including 2 active or planned projects for Sao Tome and Principe and 0 completed or closed projects for Sao Tome and Principe.

For Sao Tome and Principe, the report includes 12 requests for Sao Tome and Principe, 4 RPTC proposals for Sao Tome and Principe, 1 RPTC activities for Sao Tome and Principe, and 0 travel records for Sao Tome and Principe. Financially, Sao Tome and Principe shows USD 1,349,500 in project budget, $201,699 in proposal planned budget, and $0 in consumed RPTC activity budget for Sao Tome and Principe.

The main organizational coverage for Sao Tome and Principe points to Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, DPIDG, Economic Analysis and Policy Division. Activity records for Sao Tome and Principe list 7 participants, including 3 women participants, the current quality review for Sao Tome and Principe includes 59 data quality notes. Current highlights for Sao Tome and Principe include a request focus for Sao Tome and Principe: Request #5526 ? The Antigua and Barbuda Agenda for Small Island Developing States (ABAS) was adopted at the Fourth International Conference on Small Island Developing States (SIDS) held in May 2024. ABAS called for the development of a monitoring and evaluation framework that builds on the Samoa Pathway monitoring framework, aligns with the Sustainable Development Goals (SDGs), and utilizes data from existing reporting mechanisms. The framework is designed to comprehensively reflect the priorities of ABAS while remaining focused and practical, minimizing additional reporting burdens for SIDS. To ensure coherence with existing global commitments, approximately two-thirds of its indicators are drawn from the SDG indicator framework. Under paragraph 39 of ABAS, the United Nations Department of Economic and Social Affairs (DESA) is mandated to support implementation by conducting workshops to familiarize SIDS with the framework and strengthen national capacities for data collection, reporting, and submission, thereby enabling effective monitoring of progress and informed policymaking.

      
This proposal plans the organization of a workshop for SIDS in Africa. The workshop will be organized in collaboration with regional partners and UK Office for National Statistics (ONS). The objective of the workshop is to introduce tools for reporting and dissemination of data related to the framework based on the SDMx standard. ONS will introduce the use of Open SDGs as a platform for data dissemination.; an RPTC proposal focus for Sao Tome and Principe: Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.||Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.; an activity focus for Sao Tome and Principe: Strengthening the capacity of Supreme Audit Institutions (SAIs) from Small Island Developing States (SIDS) to audit the implementation of the Sustainable Development Goals (SDGs).

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 2 |
| Project budget | USD 1,349,500 |
| Requests | 12 |
| RPTC proposals | 4 |
| Proposal planned budget | $201,699 |
| RPTC activities | 1 |
| Consumed RPTC budget | $0 |
| Activity participants | 7 |
| Women participants | 3 |
| Travel records | 0 |
| Evaluations | 2 |
| Data quality notes | 59 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Support the digital transformation needs of small island developing States and the least developed countries. | 2528B | country | Division for Sustainable Development Goals | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 740,100 | Cabo Verde, Guinea-Bissau, Sao Tome and Principe | projects - the one.xlsx record 'Support the digital transformation needs of small island developing States and the least developed countries. ¦ [2528B]': Possible duplicate project code '2528B'. Both records retained pending review: projects.csv: Science, Technology and Innovation (STI) for Integrated Climate Action for Small Island Developing States (SIDS); projects - the one.xlsx: Support the digital transformation needs of small island developing States and the least developed countries. |
| Science, Technology and Innovation (STI) for Integrated Climate Action for Small Island Developing States (SIDS) | 2528B | country | Division for Sustainable Development Goals | Active | 15 Apr 2025 | 31 Dec 2028 | USD 609,400 | Cabo Verde, Guinea-Bissau, Sao Tome and Principe | projects.csv record 'Science, Technology and Innovation (STI) for Integrated Climate Action for Small Island Developing States (SIDS) ¦ 2025-04-15T09:19:24 ¦ 2528B': Possible duplicate project code '2528B'. Both records retained pending review: projects.csv: Science, Technology and Innovation (STI) for Integrated Climate Action for Small Island Developing States (SIDS); projects - the one.xlsx: Support the digital transformation needs of small island developing States and the least developed countries. |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5526 | Request #5526 ? The Antigua and Barbuda Agenda for Small Island Developing States (ABAS) was adopted at the Fourth International Conference on Small Island Developing States (SIDS) held in May 2024. ABAS called for the development of a monitoring and evaluation framework that builds on the Samoa Pathway monitoring framework, aligns with the Sustainable Development Goals (SDGs), and utilizes data from existing reporting mechanisms. The framework is designed to comprehensively reflect the priorities of ABAS while remaining focused and practical, minimizing additional reporting burdens for SIDS. To ensure coherence with existing global commitments, approximately two-thirds of its indicators are drawn from the SDG indicator framework. Under paragraph 39 of ABAS, the United Nations Department of Economic and Social Affairs (DESA) is mandated to support implementation by conducting workshops to familiarize SIDS with the framework and strengthen national capacities for data collection, reporting, and submission, thereby enabling effective monitoring of progress and informed policymaking. / This proposal plans the organization of a workshop for SIDS in Africa. The workshop will be organized in collaboration with regional partners and UK Office for National Statistics (ONS). The objective of the workshop is to introduce tools for reporting and dissemination of data related to the framework based on the SDMx standard. ONS will introduce the use of Open SDGs as a platform for data dissemination. | Under consideration | Statistics Division | 15 Jun 2026 | 07 Dec 2026 | 10 Dec 2026 | Harumi ¦ shibata@un.org | The Antigua and Barbuda Agenda for Small Island Developing States (ABAS) was adopted at the Fourth International Conference on Small Island Developing States (SIDS) held in May 2024. ABAS called for the development of a monitoring and evaluation framework that builds on the Samoa Pathway monitoring framework, aligns with the Sustainable Development Goals (SDGs), and utilizes data from existing reporting mechanisms. The framework is designed to comprehensively reflect the priorities of ABAS while remaining focused and practical, minimizing additional reporting burdens for SIDS. To ensure coherence with existing global commitments, approximately two-thirds of its indicators are drawn from the SDG indicator framework. Under paragraph 39 of ABAS, the United Nations Department of Economic and Social Affairs (DESA) is mandated to support implementation by conducting workshops to familiarize SIDS with the framework and strengthen national capacities for data collection, reporting, and submission, thereby enabling effective monitoring of progress and informed policymaking. / This proposal plans the organization of a workshop for SIDS in Africa. The workshop will be organized in collaboration with regional partners and UK Office for National Statistics (ONS). The objective of the workshop is to introduce tools for reporting and dissemination of data related to the framework based on the SDMx standard. ONS will introduce the use of Open SDGs as a platform for data dissemination. |  |  |
| 5516 | Request #5516 ? This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Completed | Statistics Division | 14 May 2026 | 15 Jun 2026 | 19 Jun 2026 | Seiffe Tadesse ¦ tadesse5@un.org | This activity has been developed in response to the resolution adopted by the 56th session of the United Nations Statistical Commission (later adopted as resolution E/RES/2025/13 by the Economic and Social Council on 10 June 2025) on the 2030 World Population and Housing Census Programme as well as decision 56/102(e) of the Statistical Commission. Both the resolution and the decision recognize censuses as key for formulating, implementing, and monitoring inclusive socioeconomic development and environmental sustainability policies, and as a vital source of disaggregated data for tracking the 2030 Sustainable Development Goals, including assessments by income, sex, age, race, ethnicity, migratory status, disability, geographic location, and other characteristics. As part of the 2030 World Population and Housing Census Programme, which includes several inter-related objectives and activities, UNSD is mandated to develop international statistical standards, methods, and guidelines to facilitate the conduct of population and housing censuses, and to provide technical assistance for building national capacity in planning and conducting censuses. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5453 | Request #5453 ? During the CDP Consultation, the Government of SÃ£o TomÃ© and PrÃ­ncipe provided an update on its post-graduation development trajectory, highlighting progress in macroeconomic stabilization, institutional continuity, sectoral development, and digitalization, alongside vulnerabilities related to energy security, climate shocks, and limited human and institutional capacity. The Government emphasized its commitment to long-term planning through the 15-year National Sustainability and Development Strategy (awaiting parliamentary adoption) and outlined priority areas for continued support: / â€¢ Enhanced Monitoring and Post-Graduation Support: Continued engagement under the EMM through 2027, with triennial monitoring until 2033, to support reporting, policy implementation, and management of potential risks in the post-graduation context. / â€¢ Macroeconomic Stability and Fiscal Governance: Technical assistance to strengthen tax administration, modernize customs processes, broaden the domestic revenue base, and implement fiscal reforms, including support under IMF Extended Credit Facility and Development Policy Operations. / â€¢ Agriculture and Food Security: Capacity development and advisory support to expand irrigation systems, promote household-level food production, and enhance high-quality cocoa and coffee exports to reduce import dependency and improve resilience to droughts. / â€¢ Energy Transition and Infrastructure: Advisory support and technical assistance to accelerate the shift toward renewable energy, improve electricity reliability, and mobilize private-sector participation in energy and coastal resilience projects. | Under consideration | Economic Analysis and Policy Division | 18 Nov 2025 | 15 Jan 2026 | 31 Dec 2026 | Sen Helmute Barreto ¦ helmutenv@hotmail.com | During the CDP Consultation, the Government of SÃ£o TomÃ© and PrÃ­ncipe provided an update on its post-graduation development trajectory, highlighting progress in macroeconomic stabilization, institutional continuity, sectoral development, and digitalization, alongside vulnerabilities related to energy security, climate shocks, and limited human and institutional capacity. The Government emphasized its commitment to long-term planning through the 15-year National Sustainability and Development Strategy (awaiting parliamentary adoption) and outlined priority areas for continued support: / â€¢ Enhanced Monitoring and Post-Graduation Support: Continued engagement under the EMM through 2027, with triennial monitoring until 2033, to support reporting, policy implementation, and management of potential risks in the post-graduation context. / â€¢ Macroeconomic Stability and Fiscal Governance: Technical assistance to strengthen tax administration, modernize customs processes, broaden the domestic revenue base, and implement fiscal reforms, including support under IMF Extended Credit Facility and Development Policy Operations. / â€¢ Agriculture and Food Security: Capacity development and advisory support to expand irrigation systems, promote household-level food production, and enhance high-quality cocoa and coffee exports to reduce import dependency and improve resilience to droughts. / â€¢ Energy Transition and Infrastructure: Advisory support and technical assistance to accelerate the shift toward renewable energy, improve electricity reliability, and mobilize private-sector participation in energy and coastal resilience projects. |  |  |
| 5319 | Request #5319 ? This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Completed | Statistics Division | 18 Aug 2025 | 15 Dec 2025 | 17 Dec 2025 | Sokunpanha You ¦ sokunpanha.you@un.org | This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 5014 | Request #5014 ? Strengthening institutional capacity for effective investment facilitation in Sao Tome and Principe. Sao Tome and Principe identified the need to enhance the capacity of APCI in their iGRAD request and the Director of APCI has communicated through email the request for such support. | Completed | Economic Analysis and Policy Division | 15 Jun 2024 | 15 Jun 2024 | 31 Dec 2024 | Alfredo da Trindade ¦ alfredodatrindade@gmail.com | Strengthening institutional capacity for effective investment facilitation in Sao Tome and Principe. Sao Tome and Principe identified the need to enhance the capacity of APCI in their iGRAD request and the Director of APCI has communicated through email the request for such support. |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4232 | Request #4232 ? DESA has received several requests for assistance for pandemic recovery from SIDS and are in conversations with RCOs and national counterparts in several African SIDS about strengthened DESA support. Furthermore, DESA is part of the UNCT in the Comoros and on path to join the UNCTs in Guinea Bissau, SÃ£o TomÃ© and PrÃ­ncipe, Mauritius and the Seychelles. DESA is also supporting SÃ£o TomÃ© and PrÃ­ncipe with its LDC graduation strategy. It is envisaged that 3 or 4 countries could be supported. | Completed | Economic Analysis and Policy Division | 05 Jul 2022 | 01 Jan 2022 | 31 Dec 2022 | Governments of Guinea Bissau, SÃ£o TomÃ© and PrÃ­ncipe, Mauritius and the Seychelles ¦ thomas.alfstad@un.org | DESA has received several requests for assistance for pandemic recovery from SIDS and are in conversations with RCOs and national counterparts in several African SIDS about strengthened DESA support. Furthermore, DESA is part of the UNCT in the Comoros and on path to join the UNCTs in Guinea Bissau, SÃ£o TomÃ© and PrÃ­ncipe, Mauritius and the Seychelles. DESA is also supporting SÃ£o TomÃ© and PrÃ­ncipe with its LDC graduation strategy. It is envisaged that 3 or 4 countries could be supported. |  |  |
| 4097 | Request #4097 ? DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Completed | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals | 15 Feb 2022 | 28 Mar 2022 | 29 Mar 2022 | Eddy Maloka ¦ eddy.maloka@aprm-au.org | DPIDG together with DSDG were requested to provide support in strengthening the capacities of African countries to operationalize the 11 principles of effective governance by organizing a three-day workshop for 22 African countries who are presenting their Voluntary National Reviews at the High-Level Political Forum in July 2022. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 4020 | Request #4020 ? The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. | Completed | Economic Analysis and Policy Division | 18 Nov 2021 | 01 Jan 2022 | 31 Jan 2022 | Namsuk Kim ¦ kimnamsuk@un.org | The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. |  |  |
| 3915 | Request #3915 ? The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. | Completed | Economic Analysis and Policy Division | 10 May 2021 | 26 Jun 2021 | 15 Dec 2021 | Namsuk Kim ¦ kimnamsuk@un.org | The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. |  |  |
| 3560 | Request #3560 ? This project will support the Government of SÃ£o TomÃ© e / PrÃ­ncipe in its efforts to prepare for LDC Graduation. As followup / to the government's request for assistance in late 2019, the / goal is to assist the country via policy advisory in designing a / Smooth Transition Strategy (STS), which will encompass 1) / identifying and addressing the loss of international support / through facilitating access to different programmes and / preparation for trade negotiations; 2) facilitate the / preparation and support the government in the preparation of / the STS roadmap, potentially including private sector / representatives and key development partners, who will / design/implement/monitor the STS in line with the NDP; 3) In / line with STS/NDP assess and assist the government in / identifying new forms of resource mobilization, focusing on / enhancing access to finance. The project will include i) design a / concept/plan for the STS roadmap; ii) identify/build capacity in / accessing resource mobilization opportunities iii) meet with / government officials and other representatives to support the / implementation of the STS. | Completed | Economic Analysis and Policy Division | 01 Mar 2021 | 01 Jan 2021 | 31 Dec 2021 | Edite dos Ramos da Costa Ten Jua ¦ mneccstp@gmail.com | This project will support the Government of SÃ£o TomÃ© e / PrÃ­ncipe in its efforts to prepare for LDC Graduation. As followup / to the government's request for assistance in late 2019, the / goal is to assist the country via policy advisory in designing a / Smooth Transition Strategy (STS), which will encompass 1) / identifying and addressing the loss of international support / through facilitating access to different programmes and / preparation for trade negotiations; 2) facilitate the / preparation and support the government in the preparation of / the STS roadmap, potentially including private sector / representatives and key development partners, who will / design/implement/monitor the STS in line with the NDP; 3) In / line with STS/NDP assess and assist the government in / identifying new forms of resource mobilization, focusing on / enhancing access to finance. The project will include i) design a / concept/plan for the STS roadmap; ii) identify/build capacity in / accessing resource mobilization opportunities iii) meet with / government officials and other representatives to support the / implementation of the STS. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.14 | Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026.¦¦Regional Workshop on International Statistical Classifications, Addis Ababa, Ethiopia, 5-7 May 2026. | SD | 30 Jun 2026 | 31 Dec 2026 | $67,832 | Burkina Faso, Cameroon, Chad, Eritrea, Ghana, Liberia, Malawi, Mali, Mauritius, Niger, Sao Tome and Principe, Senegal |  |  |
| SB-001376.99.99.21 | United Nations Regional Workshop on the 2030 World Programme on Population and Housing Censuses for Francophone Africa: International Standards and Innovative Approaches / | SD | 30 Jun 2026 | 30 Jun 2026 | $45,487 | Algeria, Angola, Benin, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Equatorial Guinea, Gabon, Guinea, Guinea-Bissau, Madagascar, Mali, Mauritania, Morocco, Niger, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Togo, Tunisia | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. | Proposal past due |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001376.99.99.36 | Supporting the development of ABAS and SDG national data platforms in African SIDS / | SD | 31 Dec 2026 | 31 Dec 2026 | $63,380 | Cabo Verde, Comoros, Guinea-Bissau, Maldives, Mauritius, Sao Tome and Principe, Seychelles |  |  |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001374.99.35 | Strengthening the capacity of Supreme Audit Institutions (SAIs) from Small Island Developing States (SIDS) to audit the implementation of the Sustainable Development Goals (SDGs) | DPIDG | 03 Aug 2026 | 05 Aug 2026 | $0 | 7 | 3 | Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. / activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Strengthening the capacity of Small Island Developing States to assess progress in the implementation of the Mauritius Strategy to mitigate risks and reduce vulnerability | 2018 | DSDG | Barbados, Cabo Verde, Guinea-Bissau, Jamaica, Saint Lucia, Sao Tome and Principe, Seychelles | - Continue to support the 7 countries in a Phase 2 project and invest directly in strengthening national data systems, particularly for social and environmental data. / - Conduct baseline assessments and readiness assessments in new target countries before project roll-out to tailor activities to country needs. / - Modify the VRCP tool to make it less subjective, including changes such as conducting country situational analyses, adjusting ranking scales, and improving the clarity of outputs. / - Create a communication strategy on the use of the VRCP tool to prepare stakeholders and emphasize the objective of the exercise. / - Allocate a larger share of resources to direct country support and less on sub-regional workshops. / - Incorporate initiatives for South-South cooperation. / - Analyze all vulnerability indices and M&E tools operating at the national level to determine areas of synergy and recommend approaches to leverage their advantages. / - Encourage all UN agencies to promote integration of the SAMOA Pathway with SDGs in collaboration with other development partners at the national level. | - Collaboration among national stakeholders reinforced commitments to international agreements. / - Stakeholder engagement is critical for successful project implementation. / - The project highlighted the value of data and the need for robust data systems, revealing previously unrecognized data gaps. / - Environmental statistics are a new and fragmented area, requiring network building among data sources. / - Understanding data sets is essential for proper data interpretation. / - Exchange of experiences with other SIDS provided valuable insights. / - Advocacy on the need to build resilience was strengthened. / - Similarities among the SAMOA Pathway, SDGs, and national development strategies can allow for unified reporting frameworks. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 259 - DSD Final Evaluation Report.PDF | Country standardized: 'Guinea Bissau' -> 'Guinea-Bissau'. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. |
| 2 | activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |
| 3 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 4 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 5 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 6 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 7 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 8 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 9 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 10 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 11 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 12 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 13 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 45 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 46 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 49 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 50 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 51 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 59 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |