United Republic of Tanzania

Africa | LDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

United Republic of Tanzania is presented in this country card as part of Africa, with United Republic of Tanzania also associated with an unspecified subregion and the LDC grouping. The filtered data for United Republic of Tanzania highlights 11 projects for United Republic of Tanzania, including 4 active or planned projects for United Republic of Tanzania and 7 completed or closed projects for United Republic of Tanzania.

For United Republic of Tanzania, the report includes 21 requests for United Republic of Tanzania, 5 RPTC proposals for United Republic of Tanzania, 3 RPTC activities for United Republic of Tanzania, and 3 travel records for United Republic of Tanzania. Financially, United Republic of Tanzania shows USD 21,274,894 in project budget, $335,200 in proposal planned budget, and $316,554 in consumed RPTC activity budget for United Republic of Tanzania.

The main organizational coverage for United Republic of Tanzania points to DISD, Division for Sustainable Development Goals, DPIDG, DSDG. Activity records for United Republic of Tanzania list 3,407 participants, including 761 women participants, the current quality review for United Republic of Tanzania includes 81 data quality notes. Current highlights for United Republic of Tanzania include a request focus for United Republic of Tanzania: Request #5483 ? SDG Localization and Voluntary Local Reviews; an RPTC proposal focus for United Republic of Tanzania: Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF ; an activity focus for United Republic of Tanzania: Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 11 |
| Project budget | USD 21,274,894 |
| Requests | 21 |
| RPTC proposals | 5 |
| Proposal planned budget | $335,200 |
| RPTC activities | 3 |
| Consumed RPTC budget | $316,554 |
| Activity participants | 3,407 |
| Women participants | 761 |
| Travel records | 3 |
| Evaluations | 12 |
| Data quality notes | 81 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Administrative data for disaggregated Sustainable Development Goals indicators in Africa, Asia and the Pacific and Latin America | 2124C | country | Statistics Division | Closed | 01 Jan 2020 | 28 Jun 2024 | USD 624,000 | Bhutan, Cameroon, Chile, Democratic Socialist Republic of Sri Lanka, Dominican Republic, Ecuador, Namibia, United Republic of Tanzania | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Developing institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals |  | country | Division for Public Institutions and Digital Government | Closed | 01 Oct 2021 | 31 Oct 2024 | USD 824,649 | Bangladesh, Bhutan, Cambodia, Democratic Socialist Republic of Sri Lanka, Egypt, Ethiopia, Fiji, Gambia, Ghana, Lao People's Democratic Republic, Morocco, Namibia, Rwanda, Samoa, Sierra Leone, United Republic of Tanzania, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Enhancing national capacities for unleashing full potentials of micro-, small- and medium-enterprises (MSMEs) in achieving sustainable development goals in developing countries | 2016-04 | country | Division for Sustainable Development Goals | Closed | 31 May 2017 | 31 Dec 2021 | USD 1,652,296 | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Monitoring the Sustainable Development Goals |  | country | Statistics Division | Closed | 01 Aug 2016 | 31 Jul 2022 | USD 9,334,229 | Bangladesh, Burundi, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Kyrgyzstan, Lao People's Democratic Republic, Liberia, Mozambique, Myanmar, Nepal, Rwanda, Tajikistan, Uganda, United Republic of Tanzania, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Municipal asset management for sustainable development in selected Least Developed Countries in Africa and Asia | 1819AU | country | Financing for Sustainable Development Office | Closed | 01 Jul 2018 | 31 Dec 2021 | USD 682,500 | Bangladesh, Nepal, Uganda, United Republic of Tanzania | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Accelerating SDGs in Developing Countries: Promoting Juncao Technology for Resilient Food Systems, Poverty Eradication and Climate Adaptation |  | country | Division for Sustainable Development Goals | Ongoing | 01 Jul 2025 | 30 Jun 2028 | USD 2,721,400 | Democratic Socialist Republic of Sri Lanka, Fiji, Kenya, Nepal, Nigeria, Papua New Guinea, Rwanda, United Republic of Tanzania | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |
| Promoting agricultural cooperatives in sub-Saharan Africa to enhance resilience and adaptation of small-holder farmers to climate change | 2528C | country | Division for Inclusive Social Development | Ongoing | 01 Jan 2025 | 31 Dec 2028 | USD 647,400 | Botswana, Cameroon, Ghana, United Republic of Tanzania | Duplicate review: selected this entry and excluded projects.csv row 71. |
| Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance | 2427A | country | Division for Sustainable Development Goals | Active | 01 Feb 2024 | 31 Dec 2027 | USD 1,000,000 | Cambodia, Maldives, Namibia, Senegal, United Republic of Tanzania, Zambia | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Strengthening capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao Technology and analysing and disseminating best practices and lessons learned for alleviating poverty, and promoting productive employment | PDF-SDG-2020-01 | country | Division for Sustainable Development Goals | Active | 01 Jul 2021 | 30 Jun 2025 | USD 2,450,000 | Central African Republic, China, Lao People's Democratic Republic, Madagascar, Papua New Guinea, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Strengthening capacity of National Tax Administrations And Ministries of Finance in developing countries to protect and broaden their tax base for financing of sustainable development | 1415AV | country | Financing for Sustainable Development Office | Closed | 14 May 2020 | 17 Dec 2020 | USD 360,000 | Angola, Dominican Republic, Panama, Paraguay, Trinidad and Tobago, United Republic of Tanzania | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Strengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda | PDF‐SDG‐2018-02 | country | Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, Economic Analysis and Policy Division, Financing for Sustainable Development Office, Statistics Division | Closed | 01 Nov 2018 | 30 Jun 2021 | USD 978,420 | Bangladesh, Ethiopia, Lao People's Democratic Republic, United Republic of Tanzania | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5483 | Request #5483 ? SDG Localization and Voluntary Local Reviews | Under consideration | Division for Sustainable Development Goals | 14 Nov 2025 | 11 Mar 2026 | 31 Dec 2026 | Gertrude Rose Gamwera Buyinga ¦ eaclgasecretarygeneral@eaclga.org | SDG Localization and Voluntary Local Reviews |  |  |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5431 | Request #5431 ? The Government of Tanzania, through the National Planning Commission, formally requests UN support to assist the countryâ€™s preparation for graduation from the LDC category. The request covers analytical and capacity-building support, including: (i) a study on the impacts of LDC graduation, particularly the loss of LDC-specific differential treatment and related trade policy options; (ii) analysis of ongoing changes in international development cooperation and their implications for Tanzania; and (iii) support for the Doha Programme of Action Mid-Term Review, including stakeholder workshops, with a view to ensuring a smooth and well-managed transition. | Under consideration | Economic Analysis and Policy Division | 12 Jan 2026 | 13 Jan 2026 | 31 Dec 2026 | Dr. Fred Msemwa ¦ es@planning.go.tz | The Government of Tanzania, through the National Planning Commission, formally requests UN support to assist the countryâ€™s preparation for graduation from the LDC category. The request covers analytical and capacity-building support, including: (i) a study on the impacts of LDC graduation, particularly the loss of LDC-specific differential treatment and related trade policy options; (ii) analysis of ongoing changes in international development cooperation and their implications for Tanzania; and (iii) support for the Doha Programme of Action Mid-Term Review, including stakeholder workshops, with a view to ensuring a smooth and well-managed transition. |  |  |
| 5371 | Request #5371 ? A total RPTC budget of US$ 15,000 is proposed, which will cover consultancy fee for the production of a Guidance note for incorporating the gender perspective in climate change statistics, to be used as a communicational piece for gender and climate statisticians, based on inputs from the IAEG-GS and the EG-ECCS. / Background: At the 51st session of the United Nations Statistical Commission, in 2020, the global statistical community â€œRequested that a gender perspective be adopted and integrated into all the agenda items of the Commission, as is, for example, the current practice in the Statistical Conference of the Americasâ€ (Decision 51/115, b). In response to this decision, the Inter-Agency and Expert Group on Gender Statistics (IAEG-GS) identified initial priority topics where a gender lens should be integrated, including climate change statistics. / In collaboration with the Expert Group on Environment and Climate Change Statistics (EG-ECCS), input materials have been prepared on the importance of integrating the gender perspective into climate change statistics, raising awareness among data producers about the need to address data gaps at the intersection of gender and climate change. | Completed | Statistics Division | 03 Nov 2025 | 17 Nov 2025 | 31 Mar 2026 | Maria Isabel Cobos ¦ cobos@un.org | A total RPTC budget of US$ 15,000 is proposed, which will cover consultancy fee for the production of a Guidance note for incorporating the gender perspective in climate change statistics, to be used as a communicational piece for gender and climate statisticians, based on inputs from the IAEG-GS and the EG-ECCS. / Background: At the 51st session of the United Nations Statistical Commission, in 2020, the global statistical community â€œRequested that a gender perspective be adopted and integrated into all the agenda items of the Commission, as is, for example, the current practice in the Statistical Conference of the Americasâ€ (Decision 51/115, b). In response to this decision, the Inter-Agency and Expert Group on Gender Statistics (IAEG-GS) identified initial priority topics where a gender lens should be integrated, including climate change statistics. / In collaboration with the Expert Group on Environment and Climate Change Statistics (EG-ECCS), input materials have been prepared on the importance of integrating the gender perspective into climate change statistics, raising awareness among data producers about the need to address data gaps at the intersection of gender and climate change. |  |  |
| 5321 | Request #5321 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Under consideration | Statistics Division | 19 Aug 2025 | 27 Oct 2025 | 31 Oct 2025 | Julian Chow ¦ chowj@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5299 | Request #5299 ? Support the Government of the United Republic of Tanzania, through the Tanzania Investment Centre (TIC), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. | Ongoing | Financing for Sustainable Development Office | 23 May 2025 | 23 May 2025 | 24 Nov 2025 | George Mukono ¦ george.mukono@tic.go.tz | Support the Government of the United Republic of Tanzania, through the Tanzania Investment Centre (TIC), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. |  |  |
| 5231 | Request #5231 ? The RCO in Tanzania has received requests from the Governments of Dodoma and Zanzibar for UN support in key areas including SDG indicator tracking, LDC graduation, access to financing (particularly for Zanzibarâ€™s SIDS-like needs), private sector development for women-owned businesses, and support to Zanzibarâ€™s Presidential Delivery Bureau. | Ongoing | Economic Analysis and Policy Division | 04 Jun 2025 | 04 Jun 2025 | 31 Dec 2025 | Charles Davies ¦ charleswndavies@outlook.com | The RCO in Tanzania has received requests from the Governments of Dodoma and Zanzibar for UN support in key areas including SDG indicator tracking, LDC graduation, access to financing (particularly for Zanzibarâ€™s SIDS-like needs), private sector development for women-owned businesses, and support to Zanzibarâ€™s Presidential Delivery Bureau. |  |  |
| 5222 | Request #5222 ? Support the Government of Zanzibar (Tanzania), through the Zanzibar Investment Promotion Authority (ZIPA), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. | Completed | Financing for Sustainable Development Office | 24 Apr 2025 | 28 Apr 2025 | 27 Oct 2025 | Saleh Saad Mohamed ¦ saleh.saad@zipa.go.tz | Support the Government of Zanzibar (Tanzania), through the Zanzibar Investment Promotion Authority (ZIPA), in mobilizing private financing for SDG-aligned projects and benefiting from participation in the SDG Investment Fair. |  |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 5207 | Request #5207 ? The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Completed | Statistics Division | 09 May 2025 | 30 Sept 2025 | 03 Oct 2025 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The 10th Global Forum on Gender Statistics is organized by UNSD and hosted by the National Statistics Office of Georgia. The Forum has been welcomed by the UN Statistical Commission in its decision 55/112. The Forum aims to: / (a) review progress towards gender equality and womenâ€™s empowerment, assess data availability, challenges, and countries' capacities to measure and monitor gender-relevant issues; / (b) discuss initiatives, tools, and methods for the collection, production, dissemination, and use of gender statistics; / (c) explore innovative approaches and initiatives for producing, analyzing, and utilizing data to monitor gender equality and womenâ€™s empowerment; and / (d) strategize on maximizing the use of existing data, including through the integration of a gender lens into current data processes. | Country standardized: 'Republic of Korea' -> 'Korea'. |  |
| 5126 | Request #5126 ? The United Nations Department of Economic and Social Affairs (UN DESA) is supporting countries in the early stages of social protection digital transformation by piloting newly developed capacity-building modules. Building on the successful pilot workshop in Zambia (November 2024) - as part of a PDF project that contributed to advancing a capacity building framework to support countries in their digital transformation towards integrated social protection - UN DESA is now responding to a request from the Government of Tanzania to organize a similar workshop in Dar es Salaam in 2025. / This two-day workshop will bring together 20 national experts working on social protection policy and information system integration across government. It will aim to strengthen national capacity to design, implement, and monitor digital social protection strategies and will include a new session dedicated to the global intergovernmental context on digital transformation and its role in addressing social development challengesâ€”delivered directly by DESA staff and Economic Policy Research Institute (EPRI) experts working with DESA on the development of the training tool. / The workshop will pilot three technical modules: / 1. Relevance and Foundations of Digitalization in Social Protection (including global trends and intergovernmental agendas on digital transformation) / 2. Needs Assessment Framework and Institutional Mapping / 3. Key Performance Indicators for Digitalizing Social Protection Processes / This technical cooperation initiative aligns with DESAâ€™s mandate to promote inclusive development, strengthen national institutions, and support the implementation of the 2030 Agenda and its commitment to leave no one behind. | Completed | Division for Inclusive Social Development | 12 Feb 2025 | 01 Jun 2025 | 31 Dec 2025 | Mary N. Maganga ¦ ps@kazi.go.tz | The United Nations Department of Economic and Social Affairs (UN DESA) is supporting countries in the early stages of social protection digital transformation by piloting newly developed capacity-building modules. Building on the successful pilot workshop in Zambia (November 2024) - as part of a PDF project that contributed to advancing a capacity building framework to support countries in their digital transformation towards integrated social protection - UN DESA is now responding to a request from the Government of Tanzania to organize a similar workshop in Dar es Salaam in 2025. / This two-day workshop will bring together 20 national experts working on social protection policy and information system integration across government. It will aim to strengthen national capacity to design, implement, and monitor digital social protection strategies and will include a new session dedicated to the global intergovernmental context on digital transformation and its role in addressing social development challengesâ€”delivered directly by DESA staff and Economic Policy Research Institute (EPRI) experts working with DESA on the development of the training tool. / The workshop will pilot three technical modules: / 1. Relevance and Foundations of Digitalization in Social Protection (including global trends and intergovernmental agendas on digital transformation) / 2. Needs Assessment Framework and Institutional Mapping / 3. Key Performance Indicators for Digitalizing Social Protection Processes / This technical cooperation initiative aligns with DESAâ€™s mandate to promote inclusive development, strengthen national institutions, and support the implementation of the 2030 Agenda and its commitment to leave no one behind. |  |  |
| 5168 | Request #5168 ? Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. | Completed | Statistics Division | 17 Jan 2025 | 1 | 1 | Deepchandsingh Jagai ¦ djagai@sadc.int | Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. |  |  |
| 4674 | Request #4674 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Completed | Statistics Division | 02 Aug 2023 | 02 Oct 2023 | 06 Oct 2023 | Ilaria di Matteo ¦ dimatteo@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for developing countries and for UNSD to attend the 28th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics Netherlands in The Hague, Netherlands, on 2- 6 October 2023. / The Wiesbaden Group on Business Registers is an international expert group of the United Nations Statistical Commission engaged in further development on business registers, survey frames and related topics. At this meeting, the Wiesbaden Group will exchange views and experiences in the development, maintenance and use of business registers. A capacity building training workshop on the SBR Maturity Model will be organized as part of the meeting to provide guidance for countries to conduct self-assessment on the development of their business registers and to identify areas of improvement. / The proposal concerns a total budget of US$35,582.28 covering the participation of nine participants from eight developing countries from Africa, Asia, and Latin America. This proposal also covers the travel of two DESA/UNSD staff members for organizing the workshop on the SBR Maturity Model as part of the meeting agenda. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 4739 | Request #4739 ? Technical assistance and capacity building on the development of public asset management policy for Revolutionary Government of Zanzibar. | Completed | Financing for Sustainable Development Office | 07 Aug 2022 | 01 Jan 2023 | 31 Dec 2023 | Aboud Hassan Mwinyi ¦ info@mofzanzibar.go.tz | Technical assistance and capacity building on the development of public asset management policy for Revolutionary Government of Zanzibar. |  |  |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 3962 | Request #3962 ? A five-day training workshop on the design of in-person Training of Trainers (TOT) workshop on evidence-based, risk informed and data driven Asset Management Action Plans (AMAPS) in Tanzania. As part of capacity building and ensure smooth transfer of knowledge, the TOT focused mainly to the trainers from Local Government Training Institute (LGTI). In addition to LGTI, some participants were drawn from the Ministry of Finance and Planning (Mainland Tanzania), the Ministry of Finance and Planning (Zanzibar), President Office-Regional Administration and Local Government (PO-RALG), and representatives and from local governments authorities. / The workshop was implemented in an innovative hybrid format in which participants were on-site with FSDO support from national consultants and international expert trainers. The training was undertaken from morning to the evening. The sessions were very interactive and the training participants had a chance of designing Asset Management Course and made presentations during the training. | Completed | Financing for Sustainable Development Office | 08 Jun 2021 | 01 Nov 2021 | 01 Mar 2022 | Ahmed Nassoro Nzao ¦ ahmednzao@yahoo.com | A five-day training workshop on the design of in-person Training of Trainers (TOT) workshop on evidence-based, risk informed and data driven Asset Management Action Plans (AMAPS) in Tanzania. As part of capacity building and ensure smooth transfer of knowledge, the TOT focused mainly to the trainers from Local Government Training Institute (LGTI). In addition to LGTI, some participants were drawn from the Ministry of Finance and Planning (Mainland Tanzania), the Ministry of Finance and Planning (Zanzibar), President Office-Regional Administration and Local Government (PO-RALG), and representatives and from local governments authorities. / The workshop was implemented in an innovative hybrid format in which participants were on-site with FSDO support from national consultants and international expert trainers. The training was undertaken from morning to the evening. The sessions were very interactive and the training participants had a chance of designing Asset Management Course and made presentations during the training. |  |  |
| 3922 | Request #3922 ? The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ | Ongoing | Statistics Division | 01 Mar 2021 | 01 Mar 2021 | 01 Mar 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ |  |  |
| 3875 | Request #3875 ? RGZ would request FSDO to facilitate updating of the developed Public Assets Management Policy (PAMP) and Public Assets Management Strategy (PAMS) to be in-line with the current Government plans and aspirations. This will involve the following activities: / (1) Reviewing the existing documents based on the current changes took place since their development in 2017; / (2) Undertaking capacity building workshop for assets management focal people at central and local governments for updating the developed Public Assets Management Policy (3 days); / (3) Undertaking capacity building workshop for assets management focal people at central and local governments for updating the developed Public Assets Management Strategy (4 days); and / (4) Undertaking a total of three (3) dissemination workshops for the developed Public Assets Management Policy and Public Assets Management Strategy for central government, local government, and public corporations. | Outdated | Financing for Sustainable Development Office | 03 Jun 2021 | 15 Jun 2021 | 30 Sept 2021 | Emmanuel Mashimba ¦ emma.mashimba11@gmail.com | RGZ would request FSDO to facilitate updating of the developed Public Assets Management Policy (PAMP) and Public Assets Management Strategy (PAMS) to be in-line with the current Government plans and aspirations. This will involve the following activities: / (1) Reviewing the existing documents based on the current changes took place since their development in 2017; / (2) Undertaking capacity building workshop for assets management focal people at central and local governments for updating the developed Public Assets Management Policy (3 days); / (3) Undertaking capacity building workshop for assets management focal people at central and local governments for updating the developed Public Assets Management Strategy (4 days); and / (4) Undertaking a total of three (3) dissemination workshops for the developed Public Assets Management Policy and Public Assets Management Strategy for central government, local government, and public corporations. |  |  |
| 2762 | Request #2762 ? Building capacities for infrastructure asset mangement | Outdated | Financing for Sustainable Development Office | 28 Jul 2020 |  |  |  | Building capacities for infrastructure asset mangement |  |  |
| 2752 | Request #2752 ? Capacity Building in designing a National Forest Financing Strategy | Completed | United Nations Forum on Forest | 02 Jun 2019 | 01 Sept 2020 | 31 Dec 2023 | n/a ¦ yan.lang@un.org | Capacity Building in designing a National Forest Financing Strategy |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001375.99.40 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | OISC | 30 Jun 2026 | 30 Jun 2026 | $114,966 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001377.99.10 | Strengthening national capacities in Rwanda, Uganda and United Republic of Tanzania for the 2027 LDC triennial review and sustainable graduation | EAPD | 30 Jun 2026 | 30 Sept 2026 | $85,000 | Rwanda, Uganda, United Republic of Tanzania |  | proposals.xlsx record 'SB-001377.99.10¦row:26': 'f_cashDESA' has non-numeric value 'Financial support for the project, covering travel cost of three staff members for each country, and workshop facilitation.'. / Proposal past due |
| SB-001379.99.30 | Strengthening Inclusive and Shock-Responsive Social Protection Systems in Africa | DISD | 31 Dec 2026 | 31 Dec 2026 | $40,889 | Djibouti, Ethiopia, Ghana, Kenya, Namibia, Rwanda, Senegal, Uganda, United Republic of Tanzania, Zambia |  | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| SB-001376.99.99.16 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | SD | 30 Jun 2026 | 30 Jun 2026 | $6,578 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001374.99.40 | Strengthening Artificial Intelligence (AI) Capabilities and Governance for Sustainable Digital Transformation in Africa and Asia-Pacific | DPIDG , DSDG | 30 Sept 2026 | 30 Sept 2026 | $87,767 | Algeria, Burkina Faso, Burundi, Cambodia, Democratic Socialist Republic of Sri Lanka, Gambia, Guinea-Bissau, Kenya, Lao People's Democratic Republic, Pakistan, Rwanda, Sierra Leone, Togo, Uganda, United Republic of Tanzania, Uzbekistan, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001375.99.31 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | Unspecified | 08 Apr 2026 | 10 Apr 2026 | $114,966 | 2,026 | 52 | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001375.99.31¦row:4': '#Conventions' has non-numeric value 'no'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Laws' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#National Plans' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Policies' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Reporting Obligations' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Strategies' has non-numeric value 'yes'. / No matching proposal |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002088917 - United Republic of Tanzania | 0002088917 | Past | United Republic of Tanzania |  | DIVISION FOR INCLUSIVE SOCIAL DEVELOPMENT | DIGITALIZATION SOCIAL PROTECTION WORKSHOP |  | 15 Jun 2025 | 22 Jun 2025 | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| 0002088989 - United Republic of Tanzania | 0002088989 | Past | United Republic of Tanzania |  | DIVISION FOR INCLUSIVE SOCIAL DEVELOPMENT | DIGITALIZATION OF SOCIAL PROTECTION WORKSHOP |  | 15 Jun 2025 | 22 Jun 2025 | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| 0002289886 - United Republic of Tanzania | 0002289886 | Past | United Republic of Tanzania |  | DIVISION FOR INCLUSIVE SOCIAL DEVELOPMENT | 64ROA DA PROJECT NATIONAL WORKSHOP ORGANIZATION |  | 30 May 2026 | 07 Jun 2026 | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment | 2021 | DSDG | Central African Republic, Lao People's Democratic Republic, Madagascar, Papua New Guinea, United Republic of Tanzania | - Harmonize the perceptions of different stakeholders about the project’s contribution to the SDGs and consider explicitly linking the project indicators to the relevant targets of specific SDGs. / - Formalize intra-institutional partnership between key participating parties (e.g., UNDESA, FAFU, and local partners) and incorporate detailed monitoring and reporting functions and responsibilities into the formal agreement. / - Consider developing an impact evaluation to address the effect of Juncao technology across different variables (e.g., the impact of the technology on poverty reduction and income generation, food security, and land restoration in the targeted communities). / - Strengthen the project's internal monitoring and evaluation scheme to allow better reporting on the results achieved as the project is scaled up and plays a more crucial role in increasing the visibility and promotion of Juncao technology and its contribution to achieving the SDGs. / - Elaborate gender-responsive S.M.A.R.T. performance indicators focused on both outputs and outcomes of the project. / - Elaborate S.M.A.R.T. indicators related to people in vulnerable situations to crystalize the project’s focus on the above groups, which might be useful for impact analysis as well. / - Develop a project monitoring and evaluation plan to assess the mixed results of both capacity-building interventions and technical assistance/advisory services. / - Gather data to assess the capacity-building activities across the Kirkpatrick Four-Level Training Evaluation Model. / - Continue proactive engagement of the UN Resident Coordinators and the relevant staff of other UN entities and international organizations into high-level regional and intergovernmental meetings to increase the visibility of Juncao technology and the project. / - Diversify the network of local partners and engage more non-state actors (including agriculture extension centers and educational institutions) as local partners of the project to acquire the knowledge and transfer it further. / - Continue focusing on multiple platforms for knowledge-sharing to cover face-to-face and virtual capacity building. It is advised to organize capacity-building workshops in regional centers (instead of remote areas) which offer better coverage and accessibility. / - Develop incentive schemes for the impoverished groups to enable/encourage them to travel to the Juncao demonstration sites and capacity-building workshops and improve their access to the internet. | - The design and implementation of the Juncao project were highly relevant to the needs and priorities of the targeted developing countries and direct beneficiaries, and fully aligned with the mission of UNDESA to support Member States in achieving the 2030 Agenda for Sustainable Development. / - The project lacked an exclusive focus on women, youth, and marginalized groups, which could be explained by the broader strategic mission to promote social, economic, and political inclusion through interventions at grassroots and policy levels. / - The Juncao project is distinctive as it was the first project implemented by the UN jointly with the Government of the People’s Republic of China and the intellectual property rights owner, Fujian Agriculture and Forestry University. / - Proactive involvement of the UN Resident Coordinators ensured increasing visibility and advanced promotion of the project among national stakeholders and state sector representatives. / - A mixed-method approach, combining theoretical and practical knowledge, and a mixture of top-down and bottom-up approaches, ensured alignment of the project’s implementation strategy with its objectives and expected accomplishments. / - The project indicators were not compatible with the S.M.A.R.T. framework and lacked specificity to track progress on important variables such as impact on people in vulnerable situations, gender equality, and job creation. / - The unique nature of the project partnership arrangement delayed the commencement of country-level advisory services, and the COVID-19 pandemic forced the project team to provide virtual/online solutions or postpone activities. / - The sustainability strategy demonstrated positive outcomes and overall ownership and commitment at the national level, but also showed vulnerability to external factors and dependency on the state sector. / - The project incentivized both national governments and the private sector to scale up and replicate results, but both lack the financial and human resources capacity to expand without external support or investment. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2017-01_Eval_DESA_17Jan22.docx | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx rows 216 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 249 (archived) and 2 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 55 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries | 2021 | DSDG; CDPMO | Brazil, Cambodia, Democratic Socialist Republic of Sri Lanka, Fiji, Gambia, Kenya, Lao People's Democratic Republic, Peru, Philippines, United Republic of Tanzania | - Build on the momentum and lessons from this Project in the design of a follow-on project. / - Ensure engagement at the senior policy level at project commencement and maintain or renew engagement as required to avoid loss of momentum. / - Include assistance for network mapping, activation, and strengthening in each country, with a project contacts database to support ongoing engagement. / - Invest in establishing and expanding the knowledge management aspects of the Project, including improved logical frameworks, performance indicators, and strengthened monitoring systems. / - Support critical pilot sub-projects with potential for both policy and inclusive MSME sector impact, ensuring sufficient resources and targeted technical support for implementation and scaling up. | - The Project entry point at a senior policy level activates national coordination and prioritization. / - A targeted, meso-level approach towards programming contributes towards a stronger MSME enabling environment. / - Active engagement and networking opportunities contribute to immediate and longer-term results, but contacts must be retained to maintain momentum. / - A flexible approach helps to optimize results, allowing activities to be adjusted to local context and requirements. / - National consultants and credible focal points in key ministries are important drivers of success. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2022_PDF-SDG-2016-04_Eval_DSDG_17Mar22.docx | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'The Gambia' -> 'Gambia'. | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 Agenda | 2021 | DSDG; EAPD; UNSD; DPIDG; FSDO; UNFFS; CDPMO; DISD; PD | Bangladesh, Ethiopia, Lao People's Democratic Republic, United Republic of Tanzania | - Prioritize countries which are in the process of preparing their Common Country Analysis (CCA) or other needs assessment processes. / - Increase the visibility of DESA’s capacity building work in its contributions to the CCA to ensure the UN Country Team better understands DESA’s products and services. / - Concentrate on substantive areas in countries where there is already clear demand. / - Convene a group of representatives from the divisions if considering delivery of a monitoring and evaluation product in another interdivisional project. / - Budget for a Coordinator role to help DESA’s divisions plan, implement, and execute operational activities jointly. / - Organize a facilitated workshop during the introductory phase of an interdivisional project to support building collaborative competencies within the divisions. / - Develop a Theory of Change or engage in a process that clarifies concrete outcomes intended to lead to institutional change. / - Develop multiple modalities of capacity building assistance, including working with national consultants to support country level implementation, to mitigate the effects of limited international travel. / - Continue to provide support to access multiple funding sources to support sustainable forest management in LDCs. | - The timing of project activities is instrumental; aligning support with the CCA process creates stronger entry points and partnerships. / - Having a national consultant on the ground greatly facilitates implementation and coordination with UN Country Teams and government. / - The Project Coordinator role is critical for effective communication and leveraging DESA’s expertise across divisions. / - Government capacity to absorb new assistance can be limited by internal hierarchies, competing priorities, and the need for leadership buy-in. / - DESA’s interdivisional projects benefit from an introductory phase where divisions can identify natural synergies and plan joint activities. / - A lack of a Theory of Change limited the ability to outline how intended institutional changes would occur and to track results effectively. / - DESA’s buy-in from the UN Country Team can be enhanced by increasing visibility and clarifying its added value during the CCA phase. / - Ambitious outcome statements in the logical framework should be matched with realistic timeframes and resources for sustainability. / - Gender and human rights mainstreaming require more than tracking participation rates; intentional planning and understanding are needed for effective integration. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_PDF-SDG-2018-02_Eval_DESA_15Dec21.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx rows 268 (archived) and 5 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Administrative data for disaggregated Sustainable Development Goals indicators in Africa, Asia and the Pacific and Latin America | 2024 | UNSD | Bhutan, Cameroon, Chile, Democratic Socialist Republic of Sri Lanka, Dominican Republic, Maldives, Namibia, United Republic of Tanzania | - Clarify project overall goal and better match resources to the strategic vision. / - Tighten the geographic scope to focus on fewer countries for more effective resource allocation. / - Use the project to kick start or accelerate other initiatives by strategically identifying synergies with partners. / - Adopt a time-bound, agile approach with more in-country resources and sprints for closer monitoring and engagement. / - Design robust results and learning frameworks that feed into strategic decision-making, including country-level output and outcome indicators. / - Rely on the e-learning course for capacity building and consider making its completion a prerequisite for country activities. / - Allow the purchase of equipment to support IT upgrades and incentivize country commitment. / - Introduce country call for proposal to select the most motivated countries for participation. / - Introduce peer reviews to expose countries to best practices and provide recommendations for statistical framework upgrades. / - Provide technical assistance from the onset to help countries identify priorities aligned with technical requirements for using administrative data. | - A demand-driven, country-owned approach fosters sustainability but requires countries to have sufficient capacity to identify and act on priorities. / - A wide geographic scope can dilute resources and limit the depth of support; focusing on fewer countries allows for more effective interventions. / - Strong political support and awareness-raising are critical for successful data sharing and integration of administrative data into official statistics. / - Open-source IT solutions and capacity building enhance sustainability and reduce dependency on external vendors. / - Robust knowledge management and learning frameworks are essential for capturing lessons and supporting replication and scale-up. / - Improvements in data accessibility and quality are achievable, but translating these into improved SDG reporting takes time and further effort. / - Sustainability of project impacts depends on continued country commitment and the ability to scale up beyond pilot areas. / - Synergies with other initiatives and partners can amplify project impact and should be systematically pursued. / - Challenges such as limited IT infrastructure, legal frameworks, and financial resources remain significant barriers to sustainability. / - Gender and human rights considerations, while not a core focus, can be advanced through improved data disaggregation and awareness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/2124C SB-017382 Admin Data/Evaluation/DESA_2124C_DA13 - Final evaluation report.docx | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Municipal Asset Management for Sustainable Development in Selected Least Developed Countries in Africa and Asia | 2022 | FSDO; CDPMO | Bangladesh, Nepal, Uganda, United Republic of Tanzania | - Expand the target audience to include more central level government officials to facilitate buy-in. / - Explicitly request a larger proportion of female workshop participants to advance gender equality, without compromising the calibre of qualified stakeholders. / - Continue experimenting with variations of the hybrid workshop model, combining online and in-person facilitation, and maintain the use of workshop questionnaires. / - Offer remuneration or support to cover connectivity fees for stakeholders facing internet access challenges. / - Provide relevant, context-specific examples in workshops, including examples clarifying the links between gender, asset management, and human rights. / - Spread workshops over the year, such as three or four sessions annually, if funding allows. / - Provide more support to address information gaps and climate proofing of assets, including producing short instructional videos on information gathering and climate-related asset management. / - Continue supporting the institutionalization of training in all four countries, including initiating and expanding ToT (Training of Trainers) development programs. / - Explore ToT training opportunities in Nepal with the Local Development Training Academy. / - Provide additional substantive support to the Government of Uganda to ensure effective policy implementation for municipal financing and asset management. / - Continue collaboration with the Town Development Fund in Nepal, as its mandate complements the project’s objectives. / - Make future results frameworks more realistic by including external factors such as pandemics, funding limitations, coordination challenges, and varying AMAP complexity as underlying assumptions. | - For stakeholders in Africa, internet access is unreliable and expensive; future evaluations should include monetary support to ensure equitable participation and that all voices are heard. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/1819AU SB-010719 Municipal Asset Management/Final evaluation/Final Evaluation Report 8 March 2022.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Inclusive Development for Indigenous Peoples in Africa | 2024 | DISD; CDPMO | Angola, Botswana, Burundi, Kenya, Malawi, Mozambique, Namibia, South Africa, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Design and implement, with the participation of target governments and Indigenous Peoples, a second phase of the project to continue processes initiated in target countries, including developing Free, Prior and Informed Consent (FPIC) mechanisms, Indigenous Peoples' Analysis (IPA) per country/region, and supporting institutional capacity. / - Engage other bilateral and multilateral donors such as USAID, European Union, World Bank, and African Development Bank to mobilize technical and financial support, ensuring meaningful participation of Indigenous Peoples. / - Increase engagement with Indigenous Peoples in target countries by setting mechanisms to increase diversity and reach Indigenous Peoples in remote areas, supporting their participation in project activities and political processes. / - Increase the incorporation of United Nations Resident Coordinators and Country Teams into the project to enable conversations and support Indigenous Peoples' rights, engaging them in the development of Development Assistance Frameworks and country program action plans. / - Expand dialogue and training on Indigenous women, youth, and other groups in society that remain invisible, implementing the project through intersectional lenses and ensuring sufficient financial and technical capacity. / - Improve data collection, monitoring and evaluation, and database management, developing indicators in cooperation with Indigenous Peoples and target governments, and ensuring relevant qualitative indicators are set from the beginning of the project. | - Development approaches that respect Indigenous Peoples’ rights and engage them as partners in design, implementation, management, administration, monitoring, and evaluation are vital to achieving the 2030 Sustainable Development Goals. / - Flexibility and adaptability are essential in project implementation to respond to emerging needs and local contexts, as demonstrated by the development of a conservation toolkit and COVID-19 materials. / - Ownership of the process by Indigenous Peoples and stakeholders at different levels is key to sustainability and success. / - Capacity development and participatory approaches are effective in strengthening national capacities and advancing policy drafts, but institutionalization and political support are necessary for long-term impact. / - Ensuring diversity and inclusion, particularly of Indigenous women and youth, requires targeted activities and proactive engagement strategies. / - Improved monitoring mechanisms, data collection, and systematic evaluation are needed to better assess project outcomes and inform future efforts. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/2023C SB-014517 Indigenous in Africa/Evaluation/DESA_2023C_Evaluation report_Mngt response.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| UN Capacity Development Initiative on Enhancing the Resilience, Accessibility, and Sustainability of Infrastructure Assets in Developing Countries in Support of the 2030 Agenda | 2025 | FSDO; CDPMO | Costa Rica, Gambia, Kenya, Lao People's Democratic Republic, Nepal, United Republic of Tanzania | - Engage major project stakeholders, including International Experts, to reflect on what avenues would be best to dive deeper into Data for IAM, Climate-Resilience, and IAM finance. / - Continue to engage females in selecting workshop participants in the future, especially if they are in senior management positions within the central government. Advocacy for female workshop participants and female focal points could be used. / - Strengthen the Training of Trainers (ToT) component and have a specific budget allocation for it. / - Consider other recruitment processes to address delays due to a large number of qualified applicants. / - When engaging central government officials, increase the amount of time allotted to the process. / - If continuing to use the UNOPS CAT-I Tool, reduce the number of questions or increase the amount of time allotted to the exercise, and streamline the tool to be consistent with the Diagnostic Tool. | - Female representation in workshops is enhanced when women are responsible for the selection of participants, especially in senior management positions. / - The process of engaging a broad base of stakeholders for infrastructure asset management is new in many countries and takes more time than anticipated. / - Customized Training of Trainers (ToT) and partnerships with National Training Institutes are critical for sustainability in capacity development projects. / - Switching project countries in response to political or commitment challenges can be managed efficiently without significant delays to project outcomes. / - Lengthy assessment tools (such as the CAT-I) may fatigue stakeholders and should be streamlined for future use. / - Savings from efficient project management can be reinvested to strengthen key project components, such as additional ToT workshops. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2021/PDF-2021-03 DESA-FSDO/Reports/Fin Rep_Evaluation/FINAL Evaluation Report 12 May.pdf | Country standardized: 'The Gambia' -> 'Gambia'. |  |
| Strengthening statistical capacity-building in support of progress towards the Internationally Agreed Development Goals in the Southern African Development Community (SADC) region | 2011 | UNSD | Angola, Botswana, Democratic Republic of the Congo, Eswatini, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, United Republic of Tanzania, Zambia, Zimbabwe |  | - Focus on a single objective to make project planning and evaluation more manageable and effective. / - Put more effort into developing indicators that encompass quantity, quality, and time, and that can be reliably calculated with minimal resources. / - Build production of monitoring and evaluation indicators into the project by providing appropriate budget, staffing, data sources, and procedures in project planning. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 86 - Support to MDGs in SADC/Eval Report Feeney/UNSD-SADC Final Evaluation Report.pdf | Country standardized: 'DR Congo' -> 'Democratic Republic of the Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development | 2018 | UNSD | Burundi, Indonesia, Kenya, Malaysia, Rwanda, South Sudan, Uganda, United Republic of Tanzania | - Future projects in the African region should encourage more equal gender participation in the workshops. / - Future projects working across different UNSD areas should set out guidelines for a consistent level of documentation that should be produced for each activity. / - International agencies and NSOs providing training programmes need to collaborate on the timing and content of their projects to ensure resources are used effectively and participating countries get the best value out of the activities. / - At the completion of the project, discussions should be undertaken with participating countries to assess what future support is needed and is available to assist with meeting the objectives of their national action plans. | - Workshops organized as part of the capacity building and concluding phases played a significant role in the successful outcome of the project objectives, especially by enabling the sharing of experiences among countries. / - Engaging consultants and providing guidance and feedback from UNSD was essential for countries to develop meaningful national action plans and environment statistics compendiums and pilot SEEA accounts. / - The involvement and support of regional organizations and other United Nations agencies contributed to the success and sustainability of the project outcomes. / - The project complemented broader goals of regional unions such as EAC, GDSA, and ASEAN, and future projects would benefit from working with groups of countries in similar unions. / - Working with countries in a sub-regional setting or with countries that work closely together in developing their statistical systems helped motivate progress and proved useful in advancing the implementation of SEEA and FDES. / - Participation of agencies outside the NSOs should be encouraged in similar projects, as environment data comes from a range of sources. / - FDES and SEEA frameworks, though both related to environment statistics, are generally the responsibility of different areas in the NSOs and require different implementation strategies; there are no dependencies in their implementation and countries can choose based on policy priorities. / - Examples of environmental-economic accounting drawn from the region or other developing countries were particularly helpful in understanding how to build the accounts; future projects should include more such examples. / - There is strong interest from all participating countries to continue or commence developing environmental-economic accounting programmes, and the project demonstrated that pilot SEEA accounts can be implemented successfully in data poor environments. / - The project was timely as participating countries noted that the 'environment' was becoming a key issue in policy dialogues, and the FDES and SEEA frameworks provide a response to global initiatives such as the SDGs and the 2030 sustainability agenda. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 258 - UNSD Final Evalution Report.pdf |  | evaluations.xlsx rows 211 (archived) and 209 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Conventions' has non-numeric value 'no'. |
| 2 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Laws' has non-numeric value 'yes'. |
| 3 | activity.xlsx record 'SB-001375.99.31¦row:4': '#National Plans' has non-numeric value 'yes'. |
| 4 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Policies' has non-numeric value 'yes'. |
| 5 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Reporting Obligations' has non-numeric value 'yes'. |
| 6 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Strategies' has non-numeric value 'yes'. |
| 7 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 8 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 9 | evaluations.xlsx rows 151 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; Divisions differs: archived row has 'DSDG'; retained row has 'DSDG; CDPMO'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 10 | evaluations.xlsx rows 211 (archived) and 209 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 11 | evaluations.xlsx rows 216 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 12 | evaluations.xlsx rows 243 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 13 | evaluations.xlsx rows 249 (archived) and 2 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 14 | evaluations.xlsx rows 268 (archived) and 5 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 15 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 16 | evaluations.xlsx rows 55 (archived) and 2 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 17 | evaluations.xlsx rows 65 (archived) and 3 (retained): Review conflicts: LessonsLearnedList differs between document copies. Country lists were not merged. |
| 18 | evaluations.xlsx rows 72 (archived) and 3 (retained): Review conflicts: Countries differs: archived row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines'; retained row has 'Brazil; Cambodia; Fiji; Kenya; Lao People's Democratic Republic; Sri Lanka; Tanzania; The Gambia; Philippines; Peru'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 19 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 20 | proposals.xlsx record 'SB-001377.99.10¦row:26': 'f_cashDESA' has non-numeric value 'Financial support for the project, covering travel cost of three staff members for each country, and workshop facilitation.'. |
| 21 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. |
| 22 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. |
| 23 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. |
| 24 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. |
| 25 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| 26 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 27 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 28 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 29 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 30 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 31 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 32 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 33 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 34 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 57 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 58 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 59 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 60 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 61 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 62 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 63 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 64 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 65 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 66 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 67 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 68 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 69 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 70 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 71 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 72 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 73 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 74 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 75 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 76 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 77 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 78 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 79 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 80 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 81 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |