Uruguay

Americas

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Uruguay is presented in this country card as part of Americas, with Uruguay also associated with an unspecified subregion and the no recorded country group grouping. The filtered data for Uruguay highlights 2 projects for Uruguay, including 1 active or planned projects for Uruguay and 1 completed or closed projects for Uruguay.

For Uruguay, the report includes 10 requests for Uruguay, 5 RPTC proposals for Uruguay, 3 RPTC activities for Uruguay, and 0 travel records for Uruguay. Financially, Uruguay shows USD 1,512,000 in project budget, $252,528 in proposal planned budget, and $316,554 in consumed RPTC activity budget for Uruguay.

The main organizational coverage for Uruguay points to Division for Inclusive Social Development, Financing for Sustainable Development Office, FSDO, OISC. Activity records for Uruguay list 3,407 participants, including 761 women participants, the current quality review for Uruguay includes 65 data quality notes. Current highlights for Uruguay include a request focus for Uruguay: Request #5567 ? The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics.

      

      

      
Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives.

      

      

      
The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions.

      

      

      
ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. 

      

      

      
The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026.

      

      

      
Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness.; an RPTC proposal focus for Uruguay: Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF ; an activity focus for Uruguay: Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 2 |
| Project budget | USD 1,512,000 |
| Requests | 10 |
| RPTC proposals | 5 |
| Proposal planned budget | $252,528 |
| RPTC activities | 3 |
| Consumed RPTC budget | $316,554 |
| Activity participants | 3,407 |
| Women participants | 761 |
| Travel records | 0 |
| Evaluations | 6 |
| Data quality notes | 65 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. | 2326A | country | Population Division | Active |  |  | USD 880,000 | Colombia, Costa Rica, Jamaica, Lao People's Democratic Republic, Malaysia, Maldives, Uruguay, Viet Nam | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. | projects.csv record 'Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ ¦ 2326A': End Date End Date is blank. / projects.csv record 'Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ ¦ 2326A': Start Date Start Date is blank. |
| Strengthening capacity of National Tax Administrations in developing countries to effectively negotiate and apply double tax treaties for financing of sustainable development | 1415A | country | Financing for Sustainable Development Office | Closed | 15 Jan 2020 | 18 Sept 2020 | USD 632,000 | Barbados, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Jamaica, Mexico, Nicaragua, Panama, Paraguay, Peru, Trinidad and Tobago, Uruguay, Venezuela (Bolivarian Republic of) |  |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5567 | Request #5567 ? The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 Dec 2026 | Kimberly Bordon ¦ kbordon@aladi.org | The UN Statistical Commission (at the 55th and 56th and sessions: decisions 55/116 and 56/113, as well as at the 57th session) underscored the importance of capacity development to strengthen the capabilities of the national statistical system for the compilation of business and trade statistics. / Furthermore, at its 57th session in March 2026, the United Nations Statistical Commission endorsed the revised Manual on Statistics of International Trade in Services (MSITS 2026) as the international recommendation for compiling and disseminating statistics on international trade in services (SITS). To ensure effective implementation of this revised manual, countries have expressed the need for targeted capacity-building initiatives. / The proposed Workshop will enhance capacity for national statistical offices and relevant agencies in implementing the updated conceptual and methodological framework of MSITS 2026. The focus will be on strengthening national statistical systems to produce high-quality, internationally comparable SITS. The Workshop will provide in-depth understanding of the expanded scope of SITS, recommendations and encouragements for several new data items for inclusion in the compilation and dissemination of MSITS 2026; clarifications and guidance on digital trade, globalization, modes of supply, gender, and inclusivity. The Workshop will include practical hands-on training; sharing of best practices and case studies; and discussion on challenges and solutions. / ALADI requested capacity-building and/or technical-assistance on MSITS 2026 for its Member States in an e-mail sent directly to DESA staff. / The UN Statistical Commission at its 57th session adopted the Manual on Statistics of International Trade in Services 2026, welcomed its implementation strategy, including compilation guidelines, and stressed the importance of capacity development to support Member States. In addition, during the global consultations for the revision of MSITS 2026 (17 October-28 November 2025), many countries expressed the need for support regarding capacity building for MSITS 2026. / Also, members of the Task team on International Trade Statistics (under the auspices of the UN Committee of Experts on Business and Trade Statistics; at its meeting of 21 October 2025) discussed several options/channels for capacity building, including regional Workshops, which was rated highly in terms of effectiveness. |  |
| 5373 | Request #5373 ? There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. | Under consideration | Statistics Division | 29 Oct 2025 | 01 Jan 2026 | 31 May 2026 | Kimberly Bordon ¦ kbordon@aladi.org | There is a need to develop an e-learning course on integrating business and trade statistics, implementing the Handbook on Integrating Business and Trade Statistics and recommendations in the International Merchandise Trade Statistics Manual 2026 and Manual on Statistics of International Trade in Services 2026. The e-learning will enhance capacity for linking business and trade statistics in developing countries. It will strengthen national statistical systems, including the improvement of quality, relevance, and comparability of the statistics. It will focus on the conceptual and methodological framework for linking trade statistics and business statistics, including methods that potentially can assist with the integration across many domains, such as the relationship between globalization and digitalization, informal trade, environmental sustainability, well-being, and inclusivity. It will also present methods and best practices for linking business and trade statistics to social statistics for producing disaggregations by gender and based on characteristics such as ethnicity, socio-economic factors, age, and conditions of disability. |  |
| 5246 | Request #5246 ? In accordance with Economic and Social Council resolution E/RES/2018/2 of 10 November 2017 and decision 2023/338 of 25 July 2023, the United Nations Group of Experts on Geographical Names convened its 2025 session from 28 April to the 2 May 2025 at the United Nations Headquarters in New York, in conference room three. There were 9 meetings of the 2025 session and each meeting will be three hours: 10:00 a.m - 1:00 p.m. and 3:00 - 6:00 p.m.. In all, 197 participants representing 56 Member States across UNGEGNâ€™s geographical and linguistic divisions and observers participated. Specifically, decision 2025/8 Geographical names data management (f): Urged Member States to mobilize resources to support the development of capacity across all Member States and welcomed the possibility of convening a workshop on Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals, and the Semantic Web from 11 to 15 August 2025 at the headquarters of the Economic Commission for Latin America and the Caribbean in Santiago. | Under consideration | Statistics Division | 02 May 2025 | 11 Aug 2025 | 14 Aug 2025 | Mark Iliffe ¦ mark.iliffe@un.org | In accordance with Economic and Social Council resolution E/RES/2018/2 of 10 November 2017 and decision 2023/338 of 25 July 2023, the United Nations Group of Experts on Geographical Names convened its 2025 session from 28 April to the 2 May 2025 at the United Nations Headquarters in New York, in conference room three. There were 9 meetings of the 2025 session and each meeting will be three hours: 10:00 a.m - 1:00 p.m. and 3:00 - 6:00 p.m.. In all, 197 participants representing 56 Member States across UNGEGNâ€™s geographical and linguistic divisions and observers participated. Specifically, decision 2025/8 Geographical names data management (f): Urged Member States to mobilize resources to support the development of capacity across all Member States and welcomed the possibility of convening a workshop on Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals, and the Semantic Web from 11 to 15 August 2025 at the headquarters of the Economic Commission for Latin America and the Caribbean in Santiago. |  |
| 5226 | Request #5226 ? The technical workshop on time, places, people and relationships to organize social and demographic outcomes and statistics is organized by UNSD and hosted by Statistics Canada. / The workshop aims to: / â€¢ Enhance national capacities, particularly in developing countries, to test and operationalize the building blocks TIME, PLACES, PEOPLE and RELATIONSHIPS as a lens to better organize social and demographic outcomes and statistics. / â€¢ Promote a shared understanding of the conceptual framework being advanced by the Friends of the Chair Group on Social and Demographic Statistics and how it can be applied to organize social and demographic statistics in a coherent and integrated manner; / â€¢ Refine the conceptual framework based on national experiences, technical inputs, and emerging user needs; / â€¢ Exchange national experiences and innovations in data production, integration, and dissemination that align with the proposed framework, including practical applications, institutional arrangements, and lessons learned; / â€¢ Identify technical and operational priorities for piloting and implementing the new approach at the national level, including tools, guidance, capacity-building needs, and opportunities for collaboration; / â€¢ Strengthen the alignment of the conceptual framework with global agendas, including the 2030 Agenda for Sustainable Development, the Pact for the Future, and initiatives to develop new measures of progress beyond GDP; / â€¢ Foster partnerships and peer learning among national statistical offices, regional and international organizations, and other stakeholders to support coherent implementation and promote long-term sustainability of the approach. / The Statistical Commission in its decision 55/112 (E/2024/24-E/CN.3/2024/36 ), endorsed the revised Guide to Producing Statistics on Time Use; took note of the interest expressed by countries in using the proposed methods, and requested the Statistics Division and partners to support countries in the implementation of the Guide, in collaboration with regional actors, to ensure its national relevance and effective implementation. Moreover, in its decision 56/108 (E/2025/24-E/CN.3/2025/37) the Commission, approved further research on a conceptual framework for social and demographic statistics, building on the elements TIME, PLACES, PEOPLE and RELATIONSHIPS to organize social outcomes and emphasize the need to consider innovative approaches as well as country contexts, available resources and implementation capacity. | Completed | Statistics Division | 21 May 2025 | 09 Sept 2025 | 11 Sept 2025 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The technical workshop on time, places, people and relationships to organize social and demographic outcomes and statistics is organized by UNSD and hosted by Statistics Canada. / The workshop aims to: / â€¢ Enhance national capacities, particularly in developing countries, to test and operationalize the building blocks TIME, PLACES, PEOPLE and RELATIONSHIPS as a lens to better organize social and demographic outcomes and statistics. / â€¢ Promote a shared understanding of the conceptual framework being advanced by the Friends of the Chair Group on Social and Demographic Statistics and how it can be applied to organize social and demographic statistics in a coherent and integrated manner; / â€¢ Refine the conceptual framework based on national experiences, technical inputs, and emerging user needs; / â€¢ Exchange national experiences and innovations in data production, integration, and dissemination that align with the proposed framework, including practical applications, institutional arrangements, and lessons learned; / â€¢ Identify technical and operational priorities for piloting and implementing the new approach at the national level, including tools, guidance, capacity-building needs, and opportunities for collaboration; / â€¢ Strengthen the alignment of the conceptual framework with global agendas, including the 2030 Agenda for Sustainable Development, the Pact for the Future, and initiatives to develop new measures of progress beyond GDP; / â€¢ Foster partnerships and peer learning among national statistical offices, regional and international organizations, and other stakeholders to support coherent implementation and promote long-term sustainability of the approach. / The Statistical Commission in its decision 55/112 (E/2024/24-E/CN.3/2024/36 ), endorsed the revised Guide to Producing Statistics on Time Use; took note of the interest expressed by countries in using the proposed methods, and requested the Statistics Division and partners to support countries in the implementation of the Guide, in collaboration with regional actors, to ensure its national relevance and effective implementation. Moreover, in its decision 56/108 (E/2025/24-E/CN.3/2025/37) the Commission, approved further research on a conceptual framework for social and demographic statistics, building on the elements TIME, PLACES, PEOPLE and RELATIONSHIPS to organize social outcomes and emphasize the need to consider innovative approaches as well as country contexts, available resources and implementation capacity. |  |
| 5136 | Request #5136 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. | Under consideration | Statistics Division | 03 Mar 2025 | 17 Mar 2025 | 27 May 2025 | Pedro Farinas ¦ farinas@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for two resource experts and for two UNSD staff to co-organize and co-lead a Regional Workshop on International Statistical Classifications that will be hosted by ESCAP in Santiago, Chile, on 20-22 May 2025. / This regional course aims to help participants acquire knowledge and skills to deepen their understanding of the principles and methodology of international statistical classifications. The course will review recent developments in classifications and provide guidance on the development and implementation of classifications. / The proposal concerns a total budget of US$41,903 covering the participation of two resource experts from Eurostat and the United States. This proposal also covers the travel of two DESA/UNSD staff members for co-organizing and co-leading the workshop. |  |
| 4945 | Request #4945 ? The objective of this support is to disseminate and strengthen local capacities for the use of data and information from the Survey in the country to guide social protection policies for families in situations of socioeconomic vulnerability in the country. | Completed | Division for Inclusive Social Development | 03 Apr 2024 | 01 May 2024 | 30 Sept 2024 | Mag. Cecilia Sena ¦ na@na.org | The objective of this support is to disseminate and strengthen local capacities for the use of data and information from the Survey in the country to guide social protection policies for families in situations of socioeconomic vulnerability in the country. |  |
| 4730 | Request #4730 ? This proposal is a response to country requests for training in support of estimation and use of National Transfer Accounts. Eight countries (Colombia, Costa Rica, Jamaica, Lao PDR, Malaysia, Maldives, Uruguay, and Viet Nam) will be participating in the 15th Tranche development account project on â€œInclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbeanâ€ â€“ jointly implemented by DESA, ECLAC, and ESCAP. A key prerequisite for successful participation in this DA project is the completion of a recent, full set of National Transfer Accounts by the end of 2023. / To this end and to strengthen the technical capacity in these 8 countries, this proposal will fund 8 participants (one from each of the DA project countries) to participate and receive training at the Fourteenth Global Meeting of the National Transfer Accounts project (NTA14): â€œBuilding Sustainable Generational Economiesâ€ which will take place 14-17 February 2023 at the UniversitÃ© Paris-Dauphine, France. DESA staff will co-organize and co-teach training workshops offered to participants from all countries (an estimated 60 to 80) participating at the global conference â€“ utilizing the UN manuals on National Transfer Accounts (DESA, 2013) and on National Time Transfer Accounts (DESA, 2023). | Completed | Population Division | 06 Jan 2023 | 14 Feb 2023 | 17 Feb 2023 | Tim Miller ¦ tim.miller@un.org | This proposal is a response to country requests for training in support of estimation and use of National Transfer Accounts. Eight countries (Colombia, Costa Rica, Jamaica, Lao PDR, Malaysia, Maldives, Uruguay, and Viet Nam) will be participating in the 15th Tranche development account project on â€œInclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbeanâ€ â€“ jointly implemented by DESA, ECLAC, and ESCAP. A key prerequisite for successful participation in this DA project is the completion of a recent, full set of National Transfer Accounts by the end of 2023. / To this end and to strengthen the technical capacity in these 8 countries, this proposal will fund 8 participants (one from each of the DA project countries) to participate and receive training at the Fourteenth Global Meeting of the National Transfer Accounts project (NTA14): â€œBuilding Sustainable Generational Economiesâ€ which will take place 14-17 February 2023 at the UniversitÃ© Paris-Dauphine, France. DESA staff will co-organize and co-teach training workshops offered to participants from all countries (an estimated 60 to 80) participating at the global conference â€“ utilizing the UN manuals on National Transfer Accounts (DESA, 2013) and on National Time Transfer Accounts (DESA, 2023). |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| 3922 | Request #3922 ? The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ | Ongoing | Statistics Division | 01 Mar 2021 | 01 Mar 2021 | 01 Mar 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ |  |
| 3435 | Request #3435 ? Joint DESA-ECLAC initiative in support of the Madrid International Plan of Action on Ageing (MIPAA). Held training workshop on forecasting the national economic and fiscal impacts of population ageing. | Completed | Population Division | 23 May 2019 | 09 Sept 2019 | 11 Sept 2019 | Mr. Paulo Saad ¦ paulo.saad@un.org | Joint DESA-ECLAC initiative in support of the Madrid International Plan of Action on Ageing (MIPAA). Held training workshop on forecasting the national economic and fiscal impacts of population ageing. |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001375.99.40 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | OISC | 30 Jun 2026 | 30 Jun 2026 | $114,966 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |
| SB-001376.99.99.19 | Workshop on the use of interoperability standards for the management of geographical names “Linking Geographical Names, the Disaggregation and Localization of Sustainable Development Goals and the Semantic Web” | SD | 30 Jun 2026 | 30 Jun 2026 | $43,886 | Argentina, Barbados, Brazil, Colombia, Costa Rica, Dominican Republic, Ecuador, Jamaica, Mexico, Panama, Uruguay |  | Proposal past due |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001376.99.99.32 | Regional Workshop on the Implementation of the Revised MSITS 2026 | SD | 31 Dec 2026 | 31 Dec 2026 | $62,098 | Argentina, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Cuba, Dominican Republic, Ecuador, El Salvador, Guatemala, Guyana, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay, Venezuela (Bolivarian Republic of) | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Venezuela' -> 'Venezuela (Bolivarian Republic of)'. | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. / proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| SB-001376.99.99.16 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | SD | 30 Jun 2026 | 30 Jun 2026 | $6,578 | Albania, Algeria, Bahrain, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Democratic Republic of the Congo, Egypt, Federation of Saint Kitts and Nevis, Gabon, Guinea, Guinea-Bissau, Jamaica, Jordan, Kiribati, Liberia, Malawi, Marshall Islands, Mozambique, Republic of Moldova, Rwanda, Saudi Arabia, Senegal, Somalia, Togo, Tonga, Tunisia, United Arab Emirates, United Republic of Tanzania, Uruguay | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001375.99.31 | Capacity building workshop for developing countries presenting voluntary national reviews at the 2026 HLPF | Unspecified | 08 Apr 2026 | 10 Apr 2026 | $114,966 | 2,026 | 52 | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001375.99.31¦row:4': '#Conventions' has non-numeric value 'no'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Laws' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#National Plans' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Policies' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Reporting Obligations' has non-numeric value 'yes'. / activity.xlsx record 'SB-001375.99.31¦row:4': '#Strategies' has non-numeric value 'yes'. / No matching proposal |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| SB-008163.35 | Global Compact for Safe, Orderly and Regular Migration – support for voluntary country reviews | PD | 03 Nov 2025 | 21 Jan 2027 | $194,900 | 82 | 44 | Country standardized: 'Côte d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data | 2018 | DPIDG | Bangladesh, Nepal, Panama, Uruguay | - Increase the number of participants in regional and international workshops and pursue new avenues of funding for additional participants from the target country, including contributions from local governments, private sector, and host countries. / - Translate the Guide on Lessons for OGD Action Planning for Sustainable Development into Spanish and regularly publicize its location on the UNDESA website. / - DPADM should recommend to the three Governments that have adopted the OGD National Action Plan to publicize this milestone to increase awareness among government and non-government stakeholders of its achievement and potential benefits. | - The selection of target countries should be based on in-depth feasibility study and assessment of demand, including analysis of needs, motivation, presence of a 'champion', political conditions, risks of political transitions, and early consultation with relevant regional organizations or networks. / - Future project design and planning should prioritize distributing benefits more widely within a region by leveraging the knowledge and capacity of key networks and more advanced countries. / - Greater planning and local consultation are needed to ensure participants have sufficient preparation and technical skills, relevant topics receive adequate time, and more country-specific case studies and local experts are included in workshops. / - More time should be allocated for group discussions and exercises, and documents and materials should be shared before the workshop. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/02 PROJECTS - CURRENT/UNSD/OGD FINAL_Eval Report_ Klein21March_submitted to CDO on 21 March 2018.docx |  | evaluations.xlsx rows 171 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 199 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. / evaluations.xlsx rows 252 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level | 2015 | UNSD | Algeria, Argentina, Bangladesh, Bolivia (Plurinational State of), Botswana, Brazil, Burkina Faso, Burundi, Cabo Verde, Cameroon, Chile, Costa Rica, Côte d’Ivoire, Ecuador, Egypt, Ethiopia, Guyana, Jordan, Kenya, Korea, Lebanon, Madagascar, Morocco, Nigeria, South Africa, State of Palestine, Sudan, Togo, Tunisia, Uganda, Uruguay | - Create conditions to improve the technological and knowledge transfer from developed to developing countries. / - Widely promote the adoption of internationally accepted standards related to the generation, process, dissemination and use of geospatial information, created by major standards organizations such as ISO/TC211, OGC, and IHO. / - Include the integration of statistical and geospatial information as a core issue in the UN-GGIM plan work for developing countries, especially in support of the 2020 Round of Censuses and Big Data. / - Continue the work with support of the regional committees of UN-GGIM and the countries themselves to encourage the building of spatial data infrastructures. / - Raise the awareness of the importance of geospatial information at the policy and decision making levels, and strengthen human capacities in developing countries through comprehensive trainings on geodesy, cartography, remote sensing, GIS, and geostatistical mapping. | - The Steering Committee and UNSD/DESA played an important role in aligning the deliveries of the project. / - UNSD/DESA-led projects are effective in connecting experts with organizations and countries interested in geospatial knowledge. / - At a global level, only an organization such as the UN through UNSD/DESA has the capacity to convene and lead projects of this magnitude. / - Developing countries need to increase their technological capacities, which requires more financial resources. / - Improving geospatial information management requires the creation of policies, rules, and methods for information generation, management, dissemination, and use. / - Increasing awareness and support for geospatial and statistical activities among high-level politicians and decision makers is necessary. / - Specialized human resources training is essential for functional geospatial information, beyond just technical, financial, and methodological resources. / - The information exchange mechanism used in this project was effective, allowing developing countries to learn from best practices. / - Institutional coordination between geospatial and statistical offices is still a work in progress and needs to be strengthened. / - Significant gaps in geospatial data and infrastructure exist in developing countries, and this project has helped indicate the right direction. / - There is a lack of economic resources to keep information updated in some developing countries. / - Technological capacities related to geospatial information need to be upgraded. / - There is still a lack of policies, rules, and methods for geospatial information management in some developing countries. / - Specialized human resources training in geospatial disciplines and statistics is essential. / - Strong efforts are needed to create and maintain spatial data infrastructures at all levels, considering the Global Geodetic Reference Frame. / - Awareness and support for geospatial and statistical activities from high-level decision makers need improvement. / - The 2030 Sustainable Development agenda and the 2020 Round of Censuses should be leveraged to reinforce the use of geospatial and statistical data, with executional and follow-up mechanisms for expected outcomes. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 212 - 8th tranche - Geospatial/Evaluation report/Evaluation Report- DA Project-212-8.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Cote d’Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Palestine' -> 'State of Palestine'. / Country standardized: 'Republic of Korea' -> 'Korea'. | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues | 2014 | FSDO | Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Dominican Republic, Ecuador, El Salvador, Guatemala, Honduras, Mexico, Nicaragua, Panama, Paraguay, Peru, Uruguay | - Ensure pilot countries have all necessary data available, including up-to-date and filtered taxpayer databases and appropriate sample weighting, before selection. / - Select countries that have not recently undergone major tax reforms to avoid distortion of TTCs due to adaptation processes. / - Include qualitative aspects such as psychological costs as part of non-economic costs in future TTCs studies to better understand results. / - Adapt survey implementation methods to the context (e.g., face-to-face vs. online) and include control questions to improve data quality. / - Encourage NTAs to seek synergies with other public institutions for information gathering and fieldwork support. | - Institutional support and commitment from NTAs are decisive factors for successful project implementation and sustainability. / - A thorough methodology that includes both administrative and compliance costs, considers the taxpayer cycle, and covers all relevant taxes is effective for TTC measurement. / - Allowing each country to choose its own survey method, considering size and cultural context, can improve implementation but may affect comparability. / - CIAT's coordination and reputation are critical for engaging countries and ensuring project sustainability. / - The methodology is generally easy to apply in interested countries, but successful implementation depends on institutional support and well-designed databases. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/ROA181-6B/Evaluation/Evaluation Report- FINAL.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Supporting the establishment of a Latin American Parliamentary Knowledge Network | 2014 | DPIDG | Argentina, Barbados, Bolivia (Plurinational State of), Brazil, Chile, Colombia, Costa Rica, Ecuador, El Salvador, Guatemala, Guyana, Mexico, Nicaragua, Panama, Paraguay, Saint Vincent and the Grenadines, Suriname, Trinidad and Tobago, Uruguay | - Establish regional agreement and resources for hosting of the Secretariat to ensure that it is properly funded and resourced and that the commitment for this is shared amongst those parliaments that can afford it. / - Expand opportunities for take part in network activities and extend these beyond those parliaments who have formally signed up to RIPALC. / - Ensure appropriate ongoing resources are committed to the digital portal as this is a critical component of the network and vital to ensuring the ongoing operation and relevance of it. / - Participants right across the region need to be encouraged to take ownership of the communities of interest and to see RIPALC as a place to learn, share and network. Ensuring the grass-roots value and use of the network will be the single most significant factor in the networks long term sustainability. / - RIPALC needs to be flexible and responsive to the needs of the users and allow them to create new communities of interest and for the model to develop to suit their requirements, it must be driven by demand, not controlled from the top down. / - It is important that RIPALC maintains the ability to run regional workshops and meetings so that parliamentary staff can network and collaborate. Digital networks are important and they help to sustain relationships and act as timely conduits for knowledge exchange, but they do not replace face to face meetings as a way of building social capital. / - Inter-parliamentary collaboration remains a priority and was seen by participants as a key pre-requisite for democratic strengthening in the region and RIPALC is an ideal vehicle to facilitate and support this. | - The RIPALC network was a timely and appropriate development for the region and has been well received by the participants in it. / - The clear weakness in the project was to rigidly implement a governance model based on the long-established ECPRD structure. This has proved restrictive and inflexible in the case of RIPALC and it has inhibited growth. A more organic and less rigid structure would have been more appropriate. / - Projects such as this need some level of formality and process if they are to be seen as reliable and trustworthy by parliaments, but the network must develop in line with the culture and expectations of the region it covers and duplicating a model from elsewhere can limit take-up. / - The network has become a force for active parliamentary development in the region, a timely catalyst to build on a growing desire for strong parliaments and recognition that it is important for parliaments to collaborate and share ideas, knowledge and experience. / - The network has successfully delivered face-to-face meetings and workshops, which are vital for building and sustaining relationships between parliaments, and has acted as a ‘role model’ for inter-parliamentary collaboration in a region where this is a relatively new and unknown concept. / - The web portal provides a fast and easy way for parliamentary staff to stay in touch and to discuss, advise and be advised about good practice and emergent issues in their field, which is particularly important for smaller legislatures. / - Though the uptake has been slower than expected, this is seen as a result of the structural limitations of RIPALC. In the medium to long term, the Secretariat needs to ensure that the portal is able to meet the needs and demands of its stakeholders and that it is promoted to all parliaments in the region, regardless of their formal membership of RIPALC. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/7th tranche/ROA 163 (DPADM)/RIPALC.Evaluation.FinalReport-1.0.docx | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'St Vincent and the Grenadines' -> 'Saint Vincent and the Grenadines'. | evaluations.xlsx rows 288 (archived) and 200 (retained): Review conflicts: Countries differs: archived row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; Ecuador; El Salvador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'; retained row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; El Salvador; Ecuador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'. Country lists were not merged. |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Conventions' has non-numeric value 'no'. |
| 2 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Laws' has non-numeric value 'yes'. |
| 3 | activity.xlsx record 'SB-001375.99.31¦row:4': '#National Plans' has non-numeric value 'yes'. |
| 4 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Policies' has non-numeric value 'yes'. |
| 5 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Reporting Obligations' has non-numeric value 'yes'. |
| 6 | activity.xlsx record 'SB-001375.99.31¦row:4': '#Strategies' has non-numeric value 'yes'. |
| 7 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 8 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 9 | evaluations.xlsx rows 171 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 10 | evaluations.xlsx rows 199 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 11 | evaluations.xlsx rows 218 (archived) and 153 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 12 | evaluations.xlsx rows 221 (archived) and 187 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 13 | evaluations.xlsx rows 252 (archived) and 38 (retained): Review conflicts: RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 14 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 15 | evaluations.xlsx rows 288 (archived) and 200 (retained): Review conflicts: Countries differs: archived row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; Ecuador; El Salvador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'; retained row has 'Argentina; Barbados; Bolivia; Brazil; Chile; Colombia; Costa Rica; El Salvador; Ecuador; Guatemala; Guyana; Mexico; Nicaragua; Panama; Paraguay; St Vincent and the Grenadines; Suriname; Trinidad and Tobago; Uruguay'. Country lists were not merged. |
| 16 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 17 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashGov' has non-numeric value 'N/A'. |
| 18 | proposals.xlsx record 'SB-001376.99.99.32¦row:49': 'f_cashOther' has non-numeric value 'N/A'. |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 51 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 52 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 53 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 54 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 55 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 56 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 57 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 58 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 59 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 62 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 65 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |