Uzbekistan

Asia | LLDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Uzbekistan is presented in this country card as part of Asia, with Uzbekistan also associated with an unspecified subregion and the LLDC grouping. The filtered data for Uzbekistan highlights 0 projects for Uzbekistan, including 0 active or planned projects for Uzbekistan and 0 completed or closed projects for Uzbekistan.

For Uzbekistan, the report includes 19 requests for Uzbekistan, 1 RPTC proposals for Uzbekistan, 0 RPTC activities for Uzbekistan, and 1 travel records for Uzbekistan. Financially, Uzbekistan shows Not provided in project budget, $87,767 in proposal planned budget, and $0 in consumed RPTC activity budget for Uzbekistan.

The main organizational coverage for Uzbekistan points to Division for Inclusive Social Development, Division for Public Institutions and Digital Government, DPIDG, DSDG. Activity records for Uzbekistan list 0 participants, including 0 women participants, the current quality review for Uzbekistan includes 49 data quality notes. Current highlights for Uzbekistan include a request focus for Uzbekistan: Request #5523 ? The proposed activity combines a technical meeting and international consultancy support to advance the development of a Central Framework for a System of Population and Social Statistics (CF-SPSS). It responds to the growing need for a more coherent, integrated and policy-relevant approach to social and demographic statistics, and builds on the work mandated by the United Nations Statistical Commission to strengthen this statistical pillar and advance a conceptual framework that better reflects the relationships between society, the economy and the environment. It also responds directly to requests from Member States for continued technical development, practical implementation guidance, exchange of country experiences, and sustained support for the future work of the proposed Committee of Experts on Population and Social Statistics (CEPSS). 

      
The activity aims to: (a) review and refine key conceptual and methodological elements of the CF-SPSS, including its scope, structure and practical value for national statistical systems; (b) facilitate the exchange of country experiences and technical knowledge on integrated population and social statistics; (c) identify practical priorities and next steps for the further development and implementation of the CF-SPSS in a sequenced, inclusive and country-relevant manner; and (d) prepare structured technical outputs, through the consultancy, to support future guidance and the work of the CEPSS.; an RPTC proposal focus for Uzbekistan: Strengthening Artificial Intelligence (AI) Capabilities and Governance for Sustainable Digital Transformation in Africa and Asia-Pacific.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 0 |
| Project budget | Not provided |
| Requests | 19 |
| RPTC proposals | 1 |
| Proposal planned budget | $87,767 |
| RPTC activities | 0 |
| Consumed RPTC budget | $0 |
| Activity participants | 0 |
| Women participants | 0 |
| Travel records | 1 |
| Evaluations | 3 |
| Data quality notes | 49 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5523 | Request #5523 ? The proposed activity combines a technical meeting and international consultancy support to advance the development of a Central Framework for a System of Population and Social Statistics (CF-SPSS). It responds to the growing need for a more coherent, integrated and policy-relevant approach to social and demographic statistics, and builds on the work mandated by the United Nations Statistical Commission to strengthen this statistical pillar and advance a conceptual framework that better reflects the relationships between society, the economy and the environment. It also responds directly to requests from Member States for continued technical development, practical implementation guidance, exchange of country experiences, and sustained support for the future work of the proposed Committee of Experts on Population and Social Statistics (CEPSS). / The activity aims to: (a) review and refine key conceptual and methodological elements of the CF-SPSS, including its scope, structure and practical value for national statistical systems; (b) facilitate the exchange of country experiences and technical knowledge on integrated population and social statistics; (c) identify practical priorities and next steps for the further development and implementation of the CF-SPSS in a sequenced, inclusive and country-relevant manner; and (d) prepare structured technical outputs, through the consultancy, to support future guidance and the work of the CEPSS. | Under consideration | Statistics Division | 08 Jun 2026 | 01 Jul 2026 | 31 Dec 2026 | Iliana Vaca Trigo ¦ iliana.vaca-trigo@un.org | The proposed activity combines a technical meeting and international consultancy support to advance the development of a Central Framework for a System of Population and Social Statistics (CF-SPSS). It responds to the growing need for a more coherent, integrated and policy-relevant approach to social and demographic statistics, and builds on the work mandated by the United Nations Statistical Commission to strengthen this statistical pillar and advance a conceptual framework that better reflects the relationships between society, the economy and the environment. It also responds directly to requests from Member States for continued technical development, practical implementation guidance, exchange of country experiences, and sustained support for the future work of the proposed Committee of Experts on Population and Social Statistics (CEPSS). / The activity aims to: (a) review and refine key conceptual and methodological elements of the CF-SPSS, including its scope, structure and practical value for national statistical systems; (b) facilitate the exchange of country experiences and technical knowledge on integrated population and social statistics; (c) identify practical priorities and next steps for the further development and implementation of the CF-SPSS in a sequenced, inclusive and country-relevant manner; and (d) prepare structured technical outputs, through the consultancy, to support future guidance and the work of the CEPSS. | Country standardized: 'Republic of Korea' -> 'Korea'. |
| 5321 | Request #5321 ? The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Under consideration | Statistics Division | 19 Aug 2025 | 27 Oct 2025 | 31 Oct 2025 | Julian Chow ¦ chowj@un.org | The United Nations Statistics Division (DESA/SD) is proposing to provide funding for 16 participants from developing countries and 1 DESA/UNSD staff member to attend the 29th Meeting of the Wiesbaden Group on Business Registers that will be hosted by Statistics South Africa in Johannesburg, South Africa, on 27 â€“ 31 October 2025. / The proposed activity is undertaken in response to the identified capacity gap in statistical business register development in Member States and the request by the UN Statistical Commission for the provision of capacity-building activities on business register to developing countries. / The funded participants are expected to gain practical skills and knowledge in the establishment and use of the statistical business register to produce business statistics, which allow them to identify actionable solutions to further progress their country work programme in this area. / The meeting will be conducted over five days from 27-31 October 2025, with the fifth day on 31 October 2025 designated solely for African countries to focus on experience-sharing and statistical capacity building matters on statistical business registers in Africa. / The total budget of this proposal is US$45,042.34 covering the participation of 16 participants from developing countries and one DESA/UNSD staff member. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Turkey' -> 'Türkiye'. |
| 5241 | Request #5241 ? The request is for a capacity building workshop to prepare census managers in Asian countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Under consideration | Statistics Division | 16 Jun 2025 | 20 Oct 2025 | 24 Oct 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Asian countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |
| 5145 | Request #5145 ? Climate change is one of the most pressing issues in the Asia-Pacific region. Countries requested the United Nations Statistical Institute for Asia and the Pacific (SIAP) to provide assistance on energy statistics, balances and accounts. UNSD co-organized a workshop with UNSIAP , with the support of the Office of the Director-General for Policy Planning on Statistical Policy, Ministry of Internal Affairs and Communications of the Government of Japan, focusing on the compilation of energy information in support of climate change policies The workshop took place on 13-16 May 2025 in Chiba, Japan. Nearly 30 people participated in the workshop, including 11 countries and the Asia Pacific Energy Research Centre. During the workshop, participants from national statistical offices and line ministries increased their capacity to compile and use energy statistics, balances and accounts according to international statistical methodology. | Completed | Statistics Division | 06 Feb 2025 | 13 May 2025 | 16 May 2025 | Jessica Ying Chan ¦ jessica.chan@un.org | Climate change is one of the most pressing issues in the Asia-Pacific region. Countries requested the United Nations Statistical Institute for Asia and the Pacific (SIAP) to provide assistance on energy statistics, balances and accounts. UNSD co-organized a workshop with UNSIAP , with the support of the Office of the Director-General for Policy Planning on Statistical Policy, Ministry of Internal Affairs and Communications of the Government of Japan, focusing on the compilation of energy information in support of climate change policies The workshop took place on 13-16 May 2025 in Chiba, Japan. Nearly 30 people participated in the workshop, including 11 countries and the Asia Pacific Energy Research Centre. During the workshop, participants from national statistical offices and line ministries increased their capacity to compile and use energy statistics, balances and accounts according to international statistical methodology. |  |
| 5166 | Request #5166 ? NCHR requested UNDESA to provide assistance within the framework of the National Action Plan and the Roadmap for the implementation of the UN Convention on the Rights of Persons with Disabilities. | Under consideration | Division for Inclusive Social Development | 13 Dec 2024 | 15 Feb 2025 | 15 Dec 2025 | A. Saidov ¦ info@nhrc.uz | NCHR requested UNDESA to provide assistance within the framework of the National Action Plan and the Roadmap for the implementation of the UN Convention on the Rights of Persons with Disabilities. |  |
| 5179 | Request #5179 ? The SDMX for SDGs Regional Workshop for Central Asian countries will introduce the participants to automated reporting and dissemination of SDG data with the use of the Statistical Data and Metadata eXchange (SDMX) standard. The training will cover data modelling, mapping, validation, reporting, and dissemination. / The workshop will introduce the participants to the global Data Structure Definition (DSD) for the SDGs, and provide the participants with hands-on skills in commonly used SDMX data modelling and mapping tools, raise the participantsâ€™ awareness of the latest developments in the area, and enable them to share their experience in standards-based data exchange and dissemination. / The workshop is planned to take place in Bishkek Kyrgyzstan, on 3 â€“ 6 February 2025 (4 days). At the host countryâ€™s request, a Technical Assistance meeting will be held on 7 February 2025. / A total of up to 20 participants are expected to attend the workshop as 8 will be funded by DESA. | Completed | Statistics Division | 10 Dec 2024 | 03 Feb 2025 | 07 Feb 2025 | Harumi Shibata Salazar ¦ shibata@un.org | The SDMX for SDGs Regional Workshop for Central Asian countries will introduce the participants to automated reporting and dissemination of SDG data with the use of the Statistical Data and Metadata eXchange (SDMX) standard. The training will cover data modelling, mapping, validation, reporting, and dissemination. / The workshop will introduce the participants to the global Data Structure Definition (DSD) for the SDGs, and provide the participants with hands-on skills in commonly used SDMX data modelling and mapping tools, raise the participantsâ€™ awareness of the latest developments in the area, and enable them to share their experience in standards-based data exchange and dissemination. / The workshop is planned to take place in Bishkek Kyrgyzstan, on 3 â€“ 6 February 2025 (4 days). At the host countryâ€™s request, a Technical Assistance meeting will be held on 7 February 2025. / A total of up to 20 participants are expected to attend the workshop as 8 will be funded by DESA. |  |
| 4992 | Request #4992 ? Training Workshop on an Accounting Approach to Climate Change and Biodiversity in Central Asia and the Caucasus, 9-12 September 2024, Bishkek, Kyrgyzstan / Climate change and biodiversity loss are some of the most pressing policy issues globally, given their wide-ranging impacts on well-being. Many of the countries in the Central Asia and the Caucasus region are particularly vulnerable to the adverse effects of climate change and biodiversity loss due to their geographic location. To effectively devise climate change mitigation and adaptation strategies and biodiversity loss prevention policies, countries in the region need reliable statistics and indicators on climate change impacts and biodiversity. These statistics and indicators also need to take into account the economic impacts of climate change and biodiversity, for example, the vulnerabilities of different economic sectors to climate impacts and or the state of ecosystems and the ecosystem services they provide. Integrated statistics on the environment-economy nexus will ensure that countries in the region can create policies which mitigate and adapt to climate change and biodiversity loss while strengthening their economies. / National statistical offices in the region are well placed to produce statistics on the environment-economy nexus, which can be compiled according to the international statistical standard, the System of Environmental-Economic Accounting (SEEA). At the same time, there is a need to strengthen their capabilities to produce and disseminate related statistics and indicators to better meet user needs. This workshop will cover SEEA energy and air emission accounts, and ecosystem accounts to support the compilation of indicators relevant to climate change and biodiversity. It will also cover dissemination practices and institutional mechanisms needed to strengthen the institutions producing these statistics. / The target audience are officials from national statistical offices, ministries of environment and experts from other relevant government agencies, from the nine countries that will be invited to the will be invited to the Workshop, namely Armenia, Azerbaijan, Georgia, Kazakhstan, Kyrgyzstan, Mongolia, Tajikistan, Turkmenistan and Uzbekistan. | Under consideration | Statistics Division | 31 May 2024 | 09 Sept 2024 | 12 Sept 2024 | Marko Javorsek ¦ marko.javorsek@un.org | Training Workshop on an Accounting Approach to Climate Change and Biodiversity in Central Asia and the Caucasus, 9-12 September 2024, Bishkek, Kyrgyzstan / Climate change and biodiversity loss are some of the most pressing policy issues globally, given their wide-ranging impacts on well-being. Many of the countries in the Central Asia and the Caucasus region are particularly vulnerable to the adverse effects of climate change and biodiversity loss due to their geographic location. To effectively devise climate change mitigation and adaptation strategies and biodiversity loss prevention policies, countries in the region need reliable statistics and indicators on climate change impacts and biodiversity. These statistics and indicators also need to take into account the economic impacts of climate change and biodiversity, for example, the vulnerabilities of different economic sectors to climate impacts and or the state of ecosystems and the ecosystem services they provide. Integrated statistics on the environment-economy nexus will ensure that countries in the region can create policies which mitigate and adapt to climate change and biodiversity loss while strengthening their economies. / National statistical offices in the region are well placed to produce statistics on the environment-economy nexus, which can be compiled according to the international statistical standard, the System of Environmental-Economic Accounting (SEEA). At the same time, there is a need to strengthen their capabilities to produce and disseminate related statistics and indicators to better meet user needs. This workshop will cover SEEA energy and air emission accounts, and ecosystem accounts to support the compilation of indicators relevant to climate change and biodiversity. It will also cover dissemination practices and institutional mechanisms needed to strengthen the institutions producing these statistics. / The target audience are officials from national statistical offices, ministries of environment and experts from other relevant government agencies, from the nine countries that will be invited to the will be invited to the Workshop, namely Armenia, Azerbaijan, Georgia, Kazakhstan, Kyrgyzstan, Mongolia, Tajikistan, Turkmenistan and Uzbekistan. |  |
| 4989 | Request #4989 ? The NSO of Mongolia requested the conduct of a workshop on data quality with national and international participation to allow exchange of experiences. UN-SIAP based on feedback of countries at a similar event in Malaysia in December 2024 is supporting this event. Countries at the Statistical Commission regularly request support for the implementation of a national quality assurance framework. | Under consideration | Statistics Division | 29 May 2024 | 23 Sept 2024 | 25 Sept 2024 | Mr. Batmunkh Batdavaa ¦ batdavaa@nso.mn | The NSO of Mongolia requested the conduct of a workshop on data quality with national and international participation to allow exchange of experiences. UN-SIAP based on feedback of countries at a similar event in Malaysia in December 2024 is supporting this event. Countries at the Statistical Commission regularly request support for the implementation of a national quality assurance framework. | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. / Country standardized: 'Turkey' -> 'Türkiye'. |
| 4921 | Request #4921 ? DPIDG was requested by the Government of the Rep of Uzbekistan, via its Ministry of Digital Technologies to host the 2025 UN Public Service Forum. | Completed | Division for Public Institutions and Digital Government | 03 Oct 2023 | 23 Jun 2025 | 25 Jun 2025 | Mr. Sherzod Shermatov ¦ info@digital.uz | DPIDG was requested by the Government of the Rep of Uzbekistan, via its Ministry of Digital Technologies to host the 2025 UN Public Service Forum. |  |
| 4912 | Request #4912 ? In 2024 the Government of the Republic of Uzbekistan in cooperation with the Association of Disabled Persons of Uzbekistan requested the UNDESA to provide further assistance within the framework of the National Action Plan and the Roadmap for the implementation of the UN Convention on the Rights of Persons with Disabilities and on conducting capacity building training on entrepreneurship for persons with disabilities. | Completed | Division for Inclusive Social Development | 15 Jan 2024 | 01 May 2024 | 15 Dec 2024 | A.Kh. Saidov ¦ info@nhrc.uz | In 2024 the Government of the Republic of Uzbekistan in cooperation with the Association of Disabled Persons of Uzbekistan requested the UNDESA to provide further assistance within the framework of the National Action Plan and the Roadmap for the implementation of the UN Convention on the Rights of Persons with Disabilities and on conducting capacity building training on entrepreneurship for persons with disabilities. |  |
| 4685 | Request #4685 ? The Department of Economic and Social Affairs, Division for Inclusive Social Development will conduct a three-day international workshop on Socio-economic Inclusion of Persons with Disabilities. / The workshop will be organized in collaboration with the Government of Uzbekistan. | Completed | Division for Inclusive Social Development | 10 May 2023 | 18 Oct 2023 | 20 Oct 2023 | Akmal Saidov ¦ info@nhrc.uz | The Department of Economic and Social Affairs, Division for Inclusive Social Development will conduct a three-day international workshop on Socio-economic Inclusion of Persons with Disabilities. / The workshop will be organized in collaboration with the Government of Uzbekistan. |  |
| 4695 | Request #4695 ? Second request from the National Center for Human Rights which is responsible to implement the UNCRPD to build national capacities for the implementation of the Convention in Uzbekistan. | Completed | Division for Inclusive Social Development | 05 Apr 2023 | 01 May 2023 | 15 Dec 2023 | Akmal Saidov ¦ info@nhrc.uz | Second request from the National Center for Human Rights which is responsible to implement the UNCRPD to build national capacities for the implementation of the Convention in Uzbekistan. |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |
| 4082 | Request #4082 ? Building capacity to design a project proposal for accessing forest finance | Completed | United Nations Forum on Forest | 23 Nov 2021 | 23 Nov 2021 | 27 Nov 2024 | N. Bakirov ¦ info@urmon.uz | Building capacity to design a project proposal for accessing forest finance |  |
| 4069 | Request #4069 ? minutes to be signed | Completed | Division for Inclusive Social Development | 11 Feb 2022 | 01 Mar 2022 | 31 Dec 2022 | Akmal Saidov ¦ na@na.org | minutes to be signed |  |
| 3947 | Request #3947 ? Request/ Gap/ Demand obtained from the 2020 Uzbekistan VNR submitted to the HLPF: (i) Capacity building for public and civil servants and strengthening of national institutional frameworks; and (ii) Collection, analysis, disaggregation and dissemination of data. | Not fulfilled by DESA | Statistics Division | 07 Jul 2020 | 07 Jul 2020 | 16 Jul 2020 | 2020 VNR ¦ hobeika@un.org | Request/ Gap/ Demand obtained from the 2020 Uzbekistan VNR submitted to the HLPF: (i) Capacity building for public and civil servants and strengthening of national institutional frameworks; and (ii) Collection, analysis, disaggregation and dissemination of data. |  |
| 3596 | Request #3596 ? Support for the preparation of the VNR; and upcoming development of the CCA, particularly for the macroeconomic pillar; support with the integration of the SDGs into national planning: / See below detailed request: / - SDGs integration into national planning: What concretely could we offer Uzbekistan, which has adopted national SDG goals, targets and indicators, but has not yet managed to integrate these into the national development plan (which is under development) nor into national long term sectoral plans? / - CCA: we are in the final stages of our CCA. It is not too late, however, to enhance the â€˜big pictureâ€™ analysis section and we would love to know what, if anything, DESA could do in terms of providing a page or two of analysis relevant to Uzbekistan using some of the tools mentioned. / - VNR: we are in the middle of supporting the Government with its first VNR to be presented next year. ESCAP has been providing support, and we are also beneficiaries of the DESA grant for multi-stakeholder consultations. Does DESA possibly have any resources to help countries with capacity for actually drafting? Uzbekistan has mobilised a couple of think tanks to engage but they also need to hire one or two consultants to pull the report together, and were looking to the UN for support on this. If DESA cannot support, any ideas of where we could turn? | Completed | Division for Sustainable Development Goals, Economic Analysis and Policy Division, Office for Intergovernmental Support and Coordination for Sustainable Development | 01 Nov 2019 | 01 Nov 2019 | 01 Nov 2019 | Helena Fraser ¦ fraser@un.org | Support for the preparation of the VNR; and upcoming development of the CCA, particularly for the macroeconomic pillar; support with the integration of the SDGs into national planning: / See below detailed request: / - SDGs integration into national planning: What concretely could we offer Uzbekistan, which has adopted national SDG goals, targets and indicators, but has not yet managed to integrate these into the national development plan (which is under development) nor into national long term sectoral plans? / - CCA: we are in the final stages of our CCA. It is not too late, however, to enhance the â€˜big pictureâ€™ analysis section and we would love to know what, if anything, DESA could do in terms of providing a page or two of analysis relevant to Uzbekistan using some of the tools mentioned. / - VNR: we are in the middle of supporting the Government with its first VNR to be presented next year. ESCAP has been providing support, and we are also beneficiaries of the DESA grant for multi-stakeholder consultations. Does DESA possibly have any resources to help countries with capacity for actually drafting? Uzbekistan has mobilised a couple of think tanks to engage but they also need to hire one or two consultants to pull the report together, and were looking to the UN for support on this. If DESA cannot support, any ideas of where we could turn? |  |
| 3492 | Request #3492 ? DPIDG was requested by the Ministry for Development of Information Technologies and Communications of the Republic of Uzbekistan and Kazakhstan for support in developing capacities for digital government transformation. | Completed | Division for Public Institutions and Digital Government | 18 Feb 2021 | 03 Aug 2021 | 05 Aug 2021 | H.E. Mr. Bakhtiyor Ibragimov ¦ uzbekistan.un@gmail.com | DPIDG was requested by the Ministry for Development of Information Technologies and Communications of the Republic of Uzbekistan and Kazakhstan for support in developing capacities for digital government transformation. |  |
| 2689 | Request #2689 ? Development of a sustainable urbanization strategy for the Government | Completed | Division for Sustainable Development Goals | 19 Jun 2020 | 01 Mar 2022 | 31 Mar 2023 | Azizkhan A Nazirov ¦ aziz.nazirov@gmail.com | Development of a sustainable urbanization strategy for the Government |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001374.99.40 | Strengthening Artificial Intelligence (AI) Capabilities and Governance for Sustainable Digital Transformation in Africa and Asia-Pacific | DPIDG , DSDG | 30 Sept 2026 | 30 Sept 2026 | $87,767 | Algeria, Burkina Faso, Burundi, Cambodia, Democratic Socialist Republic of Sri Lanka, Gambia, Guinea-Bissau, Kenya, Lao People's Democratic Republic, Pakistan, Rwanda, Sierra Leone, Togo, Uganda, United Republic of Tanzania, Uzbekistan, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women |
| --- | --- | --- | --- | --- | --- | --- | --- |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0002081869 - Uzbekistan | 0002081869 | Past | Uzbekistan |  | DIVISION FOR PUBLIC INSTITUTIONS AND DIGITAL GOVERNMENT | ATTEND UNPSF AND CONDUCT WORKSHOP |  | 20 Jun 2025 | 26 Jun 2025 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Realizing the Millennium Development Goals through socially inclusive macroeconomic policies | 2011 | DPAD | Egypt, Indonesia, Jordan, Kyrgyzstan, Morocco, Philippines, Senegal, South Africa, Tunisia, Uganda, Uzbekistan, Yemen | - Create a pool of potential national experts for future projects and consider contracting international experts to work closely with government officials. / - Strengthen the relationship between consultants, government officers, and UNDP country offices to ensure effective project implementation and appropriation of results. / - Increase the number of national and regional workshops, and emphasize the importance of national workshops for institutional arrangements and capacity building. / - Provide additional training and support to government staff to enable full use and institutionalization of the modeling framework. / - Develop a more user-friendly interface for the model to enhance usability for policy makers. / - Ensure better communication and collaboration between UNDP and partner institutions, especially at the country level. / - Schedule workshops and events well in advance to allow key participants to allocate time for participation. / - Enhance capacity building of local experts and national partners to increase the effectiveness and sustainability of the project. | - Careful selection of countries is crucial for project relevance and success. / - Selecting and forming national expert teams can be challenging due to limited local technical capacity, which may cause delays and affect project outcomes. / - High turnover among government staff can hinder institutionalization of project achievements. / - A close relationship between consultants, government agencies, and UNDP offices is essential for project success and appropriation of results. / - Both regional and national workshops are important for building institutional arrangements and capacity. / - Limited staff resources at the implementing division can slow down project progress and implementation. / - Early selection of a pool of country team members can help mitigate delays and negative effects from staff turnover. / - National trainings are crucial for generating necessary capacity at the country level and for transferring knowledge to stakeholders. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/5th tranche/ROA 87/ROA 87 - Terminal and Evaluation reports.pdf |  |  |
| Realizing the Millennium Development Goals through Socially-Inclusive Macroeconomic Policies | 2011 | DPAD | Egypt, Jordan, Kyrgyzstan, Morocco, Philippines, Senegal, South Africa, Tunisia, Uganda, Uzbekistan, Yemen | - Maintain close collaboration between UN agencies and the World Bank for project success and consider this approach for future projects. / - Establish a pool of potential experts to support implementation and provide flexibility for international experts to assist countries lacking national expertise. / - Identify institutions with close government relations to facilitate model appropriation by policy makers. / - Organize national workshops with participation from various government agencies to support appropriation of project results. / - Provide continuous and institutionalized technical assistance, not just one-off support, to ensure sustainability and capacity development. / - Increase the number of professionals in the DPAD/DESA team to address data availability issues and accelerate project implementation. | - Careful selection of participating countries is crucial for project success; relevance of the topic in selected countries should be ensured. / - Selection of national experts is critical; lack of local technical capabilities can delay or jeopardize country projects. / - High turnover among government staff can hinder institutionalization of project achievements; having a committed country counterpart is important. / - A strong relationship between consultants, government agencies, and UNDP offices is essential for project effectiveness and appropriation of results. / - Both regional and national workshops are important; national workshops strengthen institutional arrangements and support sustainability. / - Limited staff in DPAD/DESA can slow project progress; more professionals would help address challenges such as data availability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/5th tranche/ROA 87/External evaluation Report Final 032411.docx |  |  |
| Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies | 2015 | DPAD | Afghanistan, Bangladesh, Bhutan, Botswana, Cambodia, Chile, China, Democratic Socialist Republic of Sri Lanka, Eswatini, India, Indonesia, Kazakhstan, Korea, Lao People's Democratic Republic, Lesotho, Mozambique, Myanmar, Namibia, Nepal, Philippines, Singapore, South Africa, Tajikistan, Thailand, Uzbekistan, Viet Nam, Zambia | - Future capacity development projects of UNDESA should be sufficiently ambitious in their objectives but designed with adequate flexibility to deliver capacity development objectives in a demand-driven and nationally-owned manner. / - Future projects should ensure sufficient flexibility in the activities listed in project documents, making the list of activities indicative and not a binding constraint. / - Future training workshops should allocate additional time for discussion among participants and distribute research and background papers in advance. / - Future capacity development projects should include a post-project phase engagement framework to ensure sustainability of project interventions, especially since UNDESA is a non-resident entity. / - Future projects should earmark resources to facilitate the deployment of experts from other UN agencies to reduce dependence on external consultants. / - Future capacity development projects should make fostering South-South Cooperation a stated objective, with a clear focus on enabling developing countries to learn from each other. / - Future projects may devote technical and financial resources to develop an online forum to ensure the sustainability of interventions beyond completion. / - Future projects would benefit from having a clear and well-defined monitoring and evaluation strategy, including early recruitment of an external evaluator and allocation of resources for field visits and online evaluation tools. / - UNDESA should continue to provide policy-advisory and capacity development support to beneficiary countries and add a few additional countries to ensure sustainability of the impacts. | - An integrated approach, building on previous successful projects and deepening engagement in a few countries, leads to significant multiplier effects, cost-savings, and greater policy impact. / - Flexibility and improvisation in project implementation allow for responsiveness to evolving needs and ensure country ownership, rather than following a rigid, pre-determined set of activities. / - There is greater demand for country-specific, evidence-based policy advice than for generic handbooks or textbooks. / - Partnerships with other UN agencies, especially UNDP and regional commissions, are key to sustaining project impact and should be further strengthened. / - South-South cooperation, though not a stated objective, emerged as a valuable outcome and should be explicitly included in future project objectives. / - Establishing online communities or networks for trained officials and trainers can help sustain knowledge exchange and learning beyond project completion. / - A clear and well-defined monitoring and evaluation strategy, including early involvement of external evaluators and use of online tools, improves the quality and comprehensiveness of project evaluation. / - The project generated new requests for support from additional countries, indicating the importance of maintaining and expanding capacity development support to ensure sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/6th tranche/ROA 182 (DPAD)/Final Evaluation Report of MAC - Complete.pdf | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Vietnam' -> 'Viet Nam'. | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 2 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 3 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 4 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 5 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 6 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 7 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 8 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 9 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 10 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 11 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 12 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 13 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 14 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 15 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 16 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 17 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 18 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 19 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 20 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 21 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 22 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 23 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 24 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 25 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 26 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 35 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 36 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 37 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 38 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 39 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 40 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 41 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 42 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 43 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 44 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 45 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 46 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 47 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 48 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 49 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |