Vanuatu

Oceania | SIDS

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Vanuatu is presented in this country card as part of Oceania, with Vanuatu also associated with an unspecified subregion and the SIDS grouping. The filtered data for Vanuatu highlights 3 projects for Vanuatu, including 0 active or planned projects for Vanuatu and 3 completed or closed projects for Vanuatu.

For Vanuatu, the report includes 16 requests for Vanuatu, 3 RPTC proposals for Vanuatu, 2 RPTC activities for Vanuatu, and 0 travel records for Vanuatu. Financially, Vanuatu shows USD 1,924,649 in project budget, $149,904 in proposal planned budget, and $36,443 in consumed RPTC activity budget for Vanuatu.

The main organizational coverage for Vanuatu points to Division for Public Institutions and Digital Government, DPIDG, EAPD, Economic Analysis and Policy Division. Activity records for Vanuatu list 24 participants, including 11 women participants, the current quality review for Vanuatu includes 85 data quality notes. Current highlights for Vanuatu include a request focus for Vanuatu: Request #5585 ? The capacity building workshop is a direct response to General Assembly Resolution A/RES/78/317 (Paragraph 39): â€œWe call upon the Department of Economic and Social Affairs and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€

      

      

      
Resolution (A/Res/80/136) reiterates this call. In Paragraph 14, the General Assembly â€œEncourages small island developing States to utilize the monitoring and evaluation framework for reporting progress, on a voluntary basis, on the implementation of the Antigua and Barbuda Agenda for Small Island Developing States, and in this regard reiterates the call on the Department of Economic and Social Affairs of the Secretariat and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€

      

      

      
Additionally, during a two-day workshop held on 19-20 May 2026, members of the Association of Small Island States requested UNSD to organize a series of capacity building workshops to familiarize statistical experts of national statistical offices (NSOs) of SIDS with the ABAS M&E framework and to provide them with crucial technical support.; an RPTC proposal focus for Vanuatu: Pacific SIDS Regional Energy Statistics Training Workshop
; an activity focus for Vanuatu: Pacific SIDS Regional Energy Statistics Training Workshop.

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 3 |
| Project budget | USD 1,924,649 |
| Requests | 16 |
| RPTC proposals | 3 |
| Proposal planned budget | $149,904 |
| RPTC activities | 2 |
| Consumed RPTC budget | $36,443 |
| Activity participants | 24 |
| Women participants | 11 |
| Travel records | 0 |
| Evaluations | 5 |
| Data quality notes | 85 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Developing institutional capacities for digital data management and cooperation to advance progress toward the Sustainable Development Goals |  | country | Division for Public Institutions and Digital Government | Closed | 01 Oct 2021 | 31 Oct 2024 | USD 824,649 | Bangladesh, Bhutan, Cambodia, Democratic Socialist Republic of Sri Lanka, Egypt, Ethiopia, Fiji, Gambia, Ghana, Lao People's Democratic Republic, Morocco, Namibia, Rwanda, Samoa, Sierra Leone, United Republic of Tanzania, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Institutional arrangements for policy integration, coordination and stakeholder engagement in SDG implementation and reviews in Asia, and Asia and the Pacific | 1819G | country | Division for Public Institutions and Digital Government | Closed | 01 Apr 2018 | 31 Dec 2021 | USD 600,000 | Bhutan, Fiji, Lao People's Democratic Republic, Vanuatu | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. |
| Smooth transition beyond graduation for least developed countries in Africa, Asia and the Pacific in a post-COVID-19 environment | 2225B | country | Economic Analysis and Policy Division | Closed | 01 Feb 2022 | 30 Jun 2025 | USD 500,000 | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5585 | Request #5585 ? The capacity building workshop is a direct response to General Assembly Resolution A/RES/78/317 (Paragraph 39): â€œWe call upon the Department of Economic and Social Affairs and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€ / Resolution (A/Res/80/136) reiterates this call. In Paragraph 14, the General Assembly â€œEncourages small island developing States to utilize the monitoring and evaluation framework for reporting progress, on a voluntary basis, on the implementation of the Antigua and Barbuda Agenda for Small Island Developing States, and in this regard reiterates the call on the Department of Economic and Social Affairs of the Secretariat and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€ / Additionally, during a two-day workshop held on 19-20 May 2026, members of the Association of Small Island States requested UNSD to organize a series of capacity building workshops to familiarize statistical experts of national statistical offices (NSOs) of SIDS with the ABAS M&E framework and to provide them with crucial technical support. | Under consideration | Division for Sustainable Development Goals, Statistics Division | 17 Sept 2026 | 01 Dec 2025 | 31 Dec 2027 | Daniel Eshetie ¦ eshetie@un.org | The capacity building workshop is a direct response to General Assembly Resolution A/RES/78/317 (Paragraph 39): â€œWe call upon the Department of Economic and Social Affairs and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€ / Resolution (A/Res/80/136) reiterates this call. In Paragraph 14, the General Assembly â€œEncourages small island developing States to utilize the monitoring and evaluation framework for reporting progress, on a voluntary basis, on the implementation of the Antigua and Barbuda Agenda for Small Island Developing States, and in this regard reiterates the call on the Department of Economic and Social Affairs of the Secretariat and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and Small Island Developing States to conduct workshops to familiarize small island developing States with the application of the framework and build capacity to collect and submit their data.â€ / Additionally, during a two-day workshop held on 19-20 May 2026, members of the Association of Small Island States requested UNSD to organize a series of capacity building workshops to familiarize statistical experts of national statistical offices (NSOs) of SIDS with the ABAS M&E framework and to provide them with crucial technical support. |  |  |
| 5564 | Request #5564 ? The Government of Vanuatu expressed its appreciation for the support provided by UN DESA/EAPD on public-private partnerships (PPPs) through its DA14 project and RPTC projects, which contributed to the enactment of PPP legislation. Building on this achievement, the Government is now actively exploring potential PPP projects and identified a need for further support in areas such as investment promotion, financing, and project development. / In particular, the Government requested DESA's assistance in strengthening its national development monitoring framework. As a recently graduated country, Vanuatu emphasized the importance of enhancing monitoring and evaluation mechanisms for the implementation of its National Development Plan. This includes tracking progress in investment promotion, economic diversification, and structural transformation. / DESA acknowledged that this request falls within its area of expertise and indicated its willingness to explore potential funding opportunities and technical assistance modalities to support Vanuatu's capacity development needs in this area. | Under consideration | Economic Analysis and Policy Division | 02 Jun 2026 | 01 Aug 2026 | 31 Dec 2026 | Wensie Naki ¦ wwnaki@vanuatu.gov.vu | The Government of Vanuatu expressed its appreciation for the support provided by UN DESA/EAPD on public-private partnerships (PPPs) through its DA14 project and RPTC projects, which contributed to the enactment of PPP legislation. Building on this achievement, the Government is now actively exploring potential PPP projects and identified a need for further support in areas such as investment promotion, financing, and project development. / In particular, the Government requested DESA's assistance in strengthening its national development monitoring framework. As a recently graduated country, Vanuatu emphasized the importance of enhancing monitoring and evaluation mechanisms for the implementation of its National Development Plan. This includes tracking progress in investment promotion, economic diversification, and structural transformation. / DESA acknowledged that this request falls within its area of expertise and indicated its willingness to explore potential funding opportunities and technical assistance modalities to support Vanuatu's capacity development needs in this area. |  |  |
| 5387 | Request #5387 ? Transitioning to renewable energy is one of the most pressing policy issues in the Pacific region. Pacific SIDS face distinct challenges in transitioning to renewable energy, including limited resources and infrastructure, high dependence on imported fossil fuels and vulnerability to climate change. High-quality energy statistics and balances and GHG inventories play an important role in providing the data needed for effective policies for renewable energy transitions and climate change mitigation in Pacific SIDS. / Pacific SIDS requested the Pacific Community and the United Nations Statistical Institute for Asia and the Pacific (SIAP), with who we are organizing the workshop, to provide assistance on energy statistics and balances. The workshop aims to further build capacities in the region for the compilation of energy information in support of just energy transitions and climate change policies. | Under consideration | Statistics Division | 25 Nov 2025 | 25 Mar 2026 | 27 Mar 2026 | Jessica Ying Chan ¦ jessica.chan@un.org | Transitioning to renewable energy is one of the most pressing policy issues in the Pacific region. Pacific SIDS face distinct challenges in transitioning to renewable energy, including limited resources and infrastructure, high dependence on imported fossil fuels and vulnerability to climate change. High-quality energy statistics and balances and GHG inventories play an important role in providing the data needed for effective policies for renewable energy transitions and climate change mitigation in Pacific SIDS. / Pacific SIDS requested the Pacific Community and the United Nations Statistical Institute for Asia and the Pacific (SIAP), with who we are organizing the workshop, to provide assistance on energy statistics and balances. The workshop aims to further build capacities in the region for the compilation of energy information in support of just energy transitions and climate change policies. |  | requests.xlsx record '5387': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5387': Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5387': Country 'Tokelau' could not be matched to an ISO3 value. |
| 5319 | Request #5319 ? This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Completed | Statistics Division | 18 Aug 2025 | 15 Dec 2025 | 17 Dec 2025 | Sokunpanha You ¦ sokunpanha.you@un.org | This request is in response to request from members of the Alliance of Small Island States (AOSIS) for UNSD to organize a series of capacity building workshops to validate the M&E framework for the Antigua and Barbuda Action for Small Island Developing States (AOSIS) with statistical experts of national statistical offices (NSOs) of SIDS and to provide them with crucial technical support for the frameworkâ€™s implementation. / The workshop will be conducted face-to-face over and will consist of a series of presentations followed by group discussions. The main facilitators will be staff members from UNSD and SIDS Unit. / International and regional organisations who are custodians of selected SDG indicators will be invited to share lessons from SDG reporting and monitoring that can be adapted for the reporting and monitoring process for the ABAS. They will also be requested to share relevant resources and technical assistance opportunities to improve the production of the adopted ABAS indicators. / The workshop will benefit from the intergovernmental support work and analytical products by UNSD on areas including SDG reporting and monitoring, the implementation of the SDG global indicator framework, and evidence-based Voluntary National Reviews (VNRs). It is fully in line with the priorities set out in the approved work programme of the Inter-agency and Expert Group on SDG Indicators (IAEG-SDGs) to encourage data innovations and national efforts in bridging data gaps for SDG indicators as well as to improve data flows and global data reporting for the SDGs. / This workshop is being jointly planned and organized with the SIDS Unit of DSDG. The final decision on the venue and date will be made in September 2025. | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 5242 | Request #5242 ? The request is for a capacity building workshop to prepare census managers in Pacific countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the Pacific Community (SPC), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 16 Jun 2025 | 13 Oct 2025 | 17 Oct 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Pacific countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the Pacific Community (SPC), the United Nations Statistical Institute for Asia and the Pacific (SIAP), United Nations Population Fund (UNFPA), and the Economic and Social Commission for Asia and the Pacific (UNESCAP). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  | requests.xlsx record '5242': Countries Country text 'American Samoa' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'French Polynesia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Guam' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'New Caledonia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Pitcairn' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Countries Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country 'American Samoa' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'French Polynesia' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Guam' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'New Caledonia' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Northern Mariana Islands' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Pitcairn' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country text 'American Samoa' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'French Polynesia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Guam' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'New Caledonia' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Pitcairn' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Tokelau' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. / requests.xlsx record '5242': Country 'Tokelau' could not be matched to an ISO3 value. / requests.xlsx record '5242': Country 'Wallis and Futuna Islands' could not be matched to an ISO3 value. |
| 5046 | Request #5046 ? Support for INFF implementation through Financing for SIDS (FINS) | Not fulfilled by DESA | Division for Sustainable Development Goals, Financing for Sustainable Development Office | 20 Aug 2024 | 01 Nov 2022 | 31 Dec 2025 | Tony Sewen ¦ tasewen@vanuatu.gov.vu | Support for INFF implementation through Financing for SIDS (FINS) |  |  |
| 4916 | Request #4916 ? This proposal seeks to take advantage of SIDS4 as an opportune global policy space for the Government of Vanuatu with support from UNDESA, and in collaboration with the Asian Development Bank (ADB) and the International Finance Corporation (IFC), to co-organise a Side Event on South-South-Exchange on Attracting and Securing Private Financing and Expertise for Inclusive and Resilient Prosperity. | Completed | Economic Analysis and Policy Division | 15 Aug 2023 | 15 Aug 2023 | 31 Dec 2023 | Charlie Namaka ¦ cnamaka@vanuatu.gov.vu | This proposal seeks to take advantage of SIDS4 as an opportune global policy space for the Government of Vanuatu with support from UNDESA, and in collaboration with the Asian Development Bank (ADB) and the International Finance Corporation (IFC), to co-organise a Side Event on South-South-Exchange on Attracting and Securing Private Financing and Expertise for Inclusive and Resilient Prosperity. |  |  |
| 4731 | Request #4731 ? FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. | Completed | Financing for Sustainable Development Office | 31 Jan 2022 | 01 Jun 2022 | 12 Jan 2022 | Daniel Platz ¦ platz@un.org | FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. |  | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. / requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 2766 | Request #2766 ? DPIDG was requested by the Public Service Commission (Performance Improvement Unit) of the Government of Vanuatu to support the implementation of the Sendai Framework Monitoring and the development of a national DRR strategy as an outcome of the August 2018 Island States Forum in Sri Lanka. | Completed | Division for Public Institutions and Digital Government | 11 Aug 2018 | 18 Aug 2020 | 22 Sept 2020 | National Government ¦ n@gmail.com | DPIDG was requested by the Public Service Commission (Performance Improvement Unit) of the Government of Vanuatu to support the implementation of the Sendai Framework Monitoring and the development of a national DRR strategy as an outcome of the August 2018 Island States Forum in Sri Lanka. |  |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 4020 | Request #4020 ? The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. | Completed | Economic Analysis and Policy Division | 18 Nov 2021 | 01 Jan 2022 | 31 Jan 2022 | Namsuk Kim ¦ kimnamsuk@un.org | The activities are a response to the mandate by the ECOSOC resolution on CDP report in 2021 (E/RES/2021/11): / â€¢ paragraph 2, â€œ[ECOSOC] Notes the work carried out by the Committee on... (e) an enhanced monitoring and mechanism and graduation process...â€; / â€¢ paragraph 6, â€œ[ECOSOC] Notes that the Committee will pay special attention to the impacts of the pandemic on achieving Agenda 2030 when monitoring graduating and recently graduated countries in the coming years, and in this context calls upon Member States and relevant UN entities to support the Committeeâ€™s efforts to enhance the existing monitoring mechanism; / â€¢ paragraph 9, â€œ[ECOSOC] Calls upon the Committee to continue due consultations with the countries concerned, while conducting the triennial reviews of the list of least developed countries and monitoring the countries that are graduating and have graduated from the list, and requests the Committee to include in these consultations those least developed countries whose graduation may have been deferred. |  |  |
| 3903 | Request #3903 ? DPIDG was requested by the Government of Vanuatu to provide support in strengthening capacities for effective governance, and institutional arrangements for monitoring and evaluation to implement the 2030 Agenda. A training workshop is being organized for July 2022. The Workshop on "Enhancing National to Local Institutional Coordination and Monitoring Mechanisms for NSDP/SDG Implementation" will take place from 20-22 July 2022. / Event page: https://unpan.un.org/events/workshop-enhancing-national-local-institutional-coordination-and-monitoring-mechanisms | Completed | Division for Public Institutions and Digital Government | 23 Jun 2021 | 20 Jul 2022 | 22 Jul 2022 | Sylvain Kalsakau ¦ ksylvain@vanuatu.gov.vu | DPIDG was requested by the Government of Vanuatu to provide support in strengthening capacities for effective governance, and institutional arrangements for monitoring and evaluation to implement the 2030 Agenda. A training workshop is being organized for July 2022. The Workshop on "Enhancing National to Local Institutional Coordination and Monitoring Mechanisms for NSDP/SDG Implementation" will take place from 20-22 July 2022. / Event page: https://unpan.un.org/events/workshop-enhancing-national-local-institutional-coordination-and-monitoring-mechanisms |  |  |
| 3922 | Request #3922 ? The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ | Ongoing | Statistics Division | 01 Mar 2021 | 01 Mar 2021 | 01 Mar 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | The request is based on an overall demand from National Statistical Systems (NSS) overall in developing countries for support in producing more timely and disaggregated SDG indicators as well as information on COVID-19 using administrative data for statistical purposes. As a response to this, the Collaborative on Administrative Data was established in June 2020. It was presented to the UN Statistical Commission in March 2021, also based on earlier requests from the Commission in earlier years and through the Inter-Agency Expert Group on SDGs (IAEG-SDG). It received strong endorsement and support from the UN Statistical Commission in 2021. / Overall, there is a strong need to increase the knowledge on how to better make use of administrative data for statistics production in countries.. If such data sources are of sufficient quality, they reduce response burden on the population, reduce data collection costs and they may give a more complete and disaggregated picture of a situation than other sources. Many countries are, however, still struggling to use this source of data and through the Collaborative (and before that through a number of other channels), they have expressed a strong need for capacity development and training support. As part of the Collaborative, there has been much work, led by the countries that are members of the Collaborative, to collect currently available guidance, and where lacking, specifying needs for additional practical tools and guidance materials. As members, including international partners, have limited capacity to respond to these requests for practical guidance tools, it is, among others, proposed to hire consultant(s) who can support the work and help it progress more quickly. That way, countries will also be able to increase their efforts to provide more timely and disaggregated information on the SDGs and COVID-19 / This has mainly taken place through informal online meetings orally with no formal meeting minutes and cant therefore be attached as files to this request. / An overview of the Collaborative and the task teams can be found here: https://unstats.un.org/capacity-development/admin-data/ |  |  |
| 3915 | Request #3915 ? The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. | Completed | Economic Analysis and Policy Division | 10 May 2021 | 26 Jun 2021 | 15 Dec 2021 | Namsuk Kim ¦ kimnamsuk@un.org | The Committee for Development Policy (CDP) is mandated to monitor the development progress of countries graduated and graduating from the list of the LDCs. The CDP invites the countries being monitored to submit a report on preparation and/or implementation of the smooth transition strategy, but the participation of the countries in this monitoring exercise has been very limited in the past, partly due to their limited capacity. As requested by the CDP (E/2021/33) to be endorsed by the ECOSOC, EAPD will provide capacity development to countries being monitored, including 1) selecting relevant indicators and thresholds for each country that can alert and trigger the crisis response process within the LDC graduation monitoring framework; 2) identifying data gaps of those indicators and areas for improvement; and 3) assisting officials to prepare the monitoring report and to participate in the crisis response process. |  |  |
| 2759 | Request #2759 ? LDC graduation strategy | Ongoing | Economic Analysis and Policy Division | 03 Aug 2020 |  | 31 Dec 2021 | Mereseini Bower ¦ htoos@un.org | LDC graduation strategy |  |  |
| 2687 | Request #2687 ? DPIDG was requested to improve capacities through training/sharing tools/ coordinating mechanisms and institutional and partnership. | Completed | Division for Public Institutions and Digital Government | 07 Feb 2019 |  |  | na ¦ na@gmail.com | DPIDG was requested to improve capacities through training/sharing tools/ coordinating mechanisms and institutional and partnership. |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.17 | Pacific SIDS Regional Energy Statistics Training Workshop / | SD | 30 Jun 2026 | 30 Jun 2026 | $59,546 | Democratic Republic of Timor-Leste, Fiji, Kiribati, Marshall Islands, Micronesia (Federated States of), Nauru, Palau, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu | Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashDESA' has non-numeric value 'Total: $187,996 UNSD: $59,546 (RPTC) and $16,685 (XB); DSDG: $111,766'. / proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashOther' has non-numeric value '$30,000 (UN SIAP)'. / Proposal past due |
| SB-001376.99.99.37 | Antigua and Barbuda Action for Small Island Developing States (ABAS) 1st Capacity Building Workshop for the Pacific and 2nd Capacity Building workshop for the Caribbean | SD | 31 Dec 2026 | 31 Dec 2026 | $45,358 | Antigua and Barbuda, Dominica, Papua New Guinea, Samoa, Tonga, Vanuatu |  | proposals.xlsx record 'SB-001376.99.99.37¦row:25': 'f_cashGov' has non-numeric value '-'. / proposals.xlsx record 'SB-001376.99.99.37¦row:25': 'f_cashOther' has non-numeric value 'TBC'. |
| SB-001377.99.12 | Integrating Enhanced Monitoring Mechanism (EMM) with monitoring and evaluation framework for National Development Plan (NDP) of Cambodia and Vanuatu / ¦¦Integrating Enhanced Monitoring Mechanism (EMM) with monitoring and evaluation framework for National Development Plan (NDP) of Cambodia and Vanuatu | EAPD | 30 Sept 2026 | 31 Dec 2026 | $45,000 | Cambodia, Vanuatu |  | proposals.xlsx record 'SB-001377.99.12¦row:38': 'f_cashDESA' has non-numeric value 'Financial support for the project, covering consultancy fees, travel cost of one staff members for each country, and workshop facilitation'. |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.17 | Pacific SIDS Regional Energy Statistics Training Workshop | SD | 29 Apr 2026 | 01 May 2026 | $36,443 | 17 | 8 |  | activity.xlsx record 'SB-001376.99.99.17¦row:5': '#National Plans' has non-numeric value 'The workshop included a session on drafting national energy statistics roadmaps. As a follow up to the workshop, UNSD will produce a guide to developing a national energy statistics roadmap. It is hoped that the eight participating SIDS will formulate national energy statistics roadmaps with the help of the guide.'. |
| SB-001374.99.35 | Strengthening the capacity of Supreme Audit Institutions (SAIs) from Small Island Developing States (SIDS) to audit the implementation of the Sustainable Development Goals (SDGs) | DPIDG | 03 Aug 2026 | 05 Aug 2026 | $0 | 7 | 3 | Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. / activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Building Capacities for Promoting Women’s Presence and Leadership within Public Institutions at National Local Levels | 2024 | DPIDG | Bhutan, Cambodia, Lao People's Democratic Republic, Mauritius, Senegal, Sierra Leone, Solomon Islands, Vanuatu, Zambia | - Engage the target beneficiaries of the intervention in consultations during a project planning activity, to further inform and finalise the contextual project design. / - Conduct a risk assessment and identify viable mitigation measures for incorporation into the project document to stem the effects of possible risks to project implementation and results achievement. / - Explore a greater use of virtual interface options, to further support the contribution of the project towards value for money. / - Collaborate closely with a monitoring and evaluation specialist during project design, to inform the development of the project theory of change/ logical framework to guide effective results monitoring and reporting. / - Incorporate an element of follow-up into the project design and facilitate its implementation, to support the use of project learnings by participants for enhanced public administration practice. / - Ensure that the project results framework includes indicators for monitoring and reporting on the integration of the UNDESA cross-cutting themes into project implementation. | - Consultations with target project beneficiaries during the planning stages of the project are important for contextualising project implementation and mitigating risks to implementation and results achievement. / - A risk assessment is needed to support increased project efficiency and effectiveness by mitigating possible risks to project implementation and results achievement. / - Specialist guidance for the development of the project logical framework/theory of change increases the potential for the project to document rich evidence of its importance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects in Umoja/S1-179 Italy leadership of women in public institutions/Evaluation/Output-6-Final Evaluation Report_UNDESA_10DEC2024.pdf |  |
| Helping least developed countries (LDCs) pursue structural economic progress toward and beyond graduation | 2022 | EAPD; CDPMO | Bangladesh, Bhutan, Lao People's Democratic Republic, Myanmar, Vanuatu | - Ensure that DA Project guidelines provide greater clarity on how priority cross-cutting issues (such as gender, human rights, and climate change) can be integrated into project outcome and output indicators and applied in implementation plans and subsequent monitoring, evaluation, and reporting. / - Ensure that DA Project guidelines provide greater clarity with regards to coordination and collaboration between different UN agencies to create synergy and ensure effective division of labour from the outset. / - Ensure that all key stakeholders are made fully aware of what UNDESA, UNCTAD, and other UN entities will be doing in the future to build on the success of this project, and how they can access this type of support in the future. Further support is still required in line with the types of support already provided, including: relevant advisory services to policy makers, including responding to the findings of Impact Assessments and Vulnerability Profiles; Graduation support via iGRAD; enacting and monitoring implementation of smooth transition strategies; and staying abreast of changing international trade requirements through ePING. | - A coordinated, integrated approach ensures less burden on beneficiary countries and better leverages additional resources for enhancing the impact of planned actions. / - Preparation of smooth transition strategies (STS) required clear guidelines; developing and updating an STS Guidance Note, translated into multiple languages, was effective. / - Analytical work highlighted long-term structural challenges; embedding these findings into national development plans increased impact. / - The framework for vulnerability profiles needed to be revised and broadened to include issues such as gender and social inequalities. / - Piloting consolidated Graduation Assessments, synthesizing impact assessments and vulnerability profiles, helped policy makers quickly digest key findings and recommendations. / - South-South cooperation and peer-to-peer learning enhanced beneficiary countries' learning and ability to address graduation challenges. / - Remote training was successful, but follow-up is needed to ensure capacity building is effective. / - COVID-19 led to innovation in capacity-building modalities, such as interactive and translated training materials and adjusted delivery pace. / - Establishing a dedicated facility like iGRAD supports graduating and graduated LDCs and improves coordination among UN agencies. / - The digital divide, highlighted by the pandemic, limited engagement with local governments; future projects should address technology access to ensure inclusiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/1819F SB-009659 Helping LDCs progress towards graduation/Evaluation/DA11-Final Evaluation Report-11-11-2022.pdf |  |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |
| Smooth transition beyond graduation for least developed countries in Africa, Asian and the Pacific in a post-COVID-19 environment | 2026 | EAPD | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | - Where future programming allocates resources for it, build in structured post-delivery follow-up support for STS implementation. / - Require a written letter of commitment and interest from the government as a prerequisite for in-depth ePing training, to ensure that engagement is demand-driven and institutionally anchored from the outset. In addition, maintain the tripartite UNDESA–WTO–ITC coordination model as the delivery framework for future ePing support. / - Systematically integrate RCOs as operational partners in future multi-country projects. / - Strengthen UN system coordination and link STS processes to implementation and financing pathways. / - Incorporate flexible, demand-responsive analytical support within future projects. | - National ownership is the single most important determinant of results. Projects supporting LDC graduation are most effective and sustainable when anchored in strong national leadership, clear institutional mandates, and existing coordination mechanisms. / - Embedding transition strategies into existing systems enhances sustainability. Good practice was observed where STS priorities were integrated into national development plans, budgets, and monitoring systems. / - Depth of engagement matters more than breadth for technical tools. The ePing experience shows that intensive, hands-on training with follow-up produces durable behavioural change, while lighter engagement yields limited results. Training-of-Trainers models are particularly effective for sustainability. / - Flexibility and adaptive management are essential in volatile contexts. The project demonstrated that the ability to adapt activities, sequencing, and resource allocation in response to shocks is critical for maintaining relevance and efficiency in multi-country programmes. / - Modest resources can deliver meaningful results when well-targeted. Despite a relatively small budget, the project achieved substantial outputs and early outcomes by leveraging partnerships, aligning with national priorities, and focusing on catalytic interventions. / - Efficiency gains can be significantly enhanced when global technical assistance is anchored within existing UN country coordination structures. Integrating implementation through RCO platforms enables faster stakeholder mobilisation, improved alignment with national priorities, and sustained follow-up between missions. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/2225B_ SB-019218 LDC Graduation/Final Evaluation/DA14_project_evaluation Final EAPD 17June2026.pdf |  |
| Smooth transition beyond graduation for least developed countries in Africa, Asia and the Pacific in a post-COVID-19 environment | 2026 | EAPD | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | - Where future programming allocates resources for it, build in structured post-delivery follow-up support for STS implementation. / - Require a written letter of commitment and interest from the government as a prerequisite for in-depth ePing training, to ensure that engagement is demand-driven and institutionally anchored from the outset. In addition, maintain the tripartite UNDESA–WTO–ITC coordination model as the delivery framework for future ePing support. / - Systematically integrate RCOs as operational partners in future multi-country projects. / - Strengthen UN system coordination and link STS processes to implementation and financing pathways. / - Incorporate flexible, demand-responsive analytical support within future projects. | - National ownership is the single most important determinant of results. Projects supporting LDC graduation are most effective and sustainable when anchored in strong national leadership, clear institutional mandates, and existing coordination mechanisms. / - Embedding transition strategies into existing systems enhances sustainability. Good practice was observed where STS priorities were integrated into national development plans, budgets, and monitoring systems. / - Depth of engagement matters more than breadth for technical tools. The ePing experience shows that intensive, hands-on training with follow-up produces durable behavioural change, while lighter engagement yields limited results. Training-of-Trainers models are particularly effective for sustainability. / - Flexibility and adaptive management are essential in volatile contexts. The project demonstrated that the ability to adapt activities, sequencing, and resource allocation in response to shocks is critical for maintaining relevance and efficiency in multi-country programmes. / - Modest resources can deliver meaningful results when well-targeted. Despite a relatively small budget, the project achieved substantial outputs and early outcomes by leveraging partnerships, aligning with national priorities, and focusing on catalytic interventions. / - Efficiency gains can be significantly enhanced when global technical assistance is anchored within existing UN country coordination structures. Integrating implementation through RCO platforms enables faster stakeholder mobilisation, improved alignment with national priorities, and sustained follow-up between missions. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/2225B_ SB-019218 LDC Graduation/Evaluation report/DA14- Final Evaluation Report-21-04-2026.docx |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001374.99.35¦row:12': '#Strategies' has non-numeric value 'One of the key outcomes of the event was the identification of strategic priorities for strengthening SAIs in SIDS, including enhancing their role within accountability ecosystems, advancing sustainable development and resilience, promoting debt accountability and fiscal sustainability, building institutional capacity, fostering collaboration and peer learning, and leveraging digitalization and AI. Strategic priorities were linked to specific actions and initiatives to operationalize them.'. |
| 2 | activity.xlsx record 'SB-001374.99.35¦row:12': 'Consumed Budget' is blank. |
| 3 | activity.xlsx record 'SB-001376.99.99.17¦row:5': '#National Plans' has non-numeric value 'The workshop included a session on drafting national energy statistics roadmaps. As a follow up to the workshop, UNSD will produce a guide to developing a national energy statistics roadmap. It is hoped that the eight participating SIDS will formulate national energy statistics roadmaps with the help of the guide.'. |
| 4 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 5 | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashDESA' has non-numeric value 'Total: $187,996 UNSD: $59,546 (RPTC) and $16,685 (XB); DSDG: $111,766'. |
| 6 | proposals.xlsx record 'SB-001376.99.99.17¦row:17': 'f_cashOther' has non-numeric value '$30,000 (UN SIAP)'. |
| 7 | proposals.xlsx record 'SB-001376.99.99.37¦row:25': 'f_cashGov' has non-numeric value '-'. |
| 8 | proposals.xlsx record 'SB-001376.99.99.37¦row:25': 'f_cashOther' has non-numeric value 'TBC'. |
| 9 | proposals.xlsx record 'SB-001377.99.12¦row:38': 'f_cashDESA' has non-numeric value 'Financial support for the project, covering consultancy fees, travel cost of one staff members for each country, and workshop facilitation'. |
| 10 | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. |
| 11 | requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 12 | requests.xlsx record '5242': Countries Country text 'American Samoa' could not be matched; no country assignment was inferred. |
| 13 | requests.xlsx record '5242': Countries Country text 'French Polynesia' could not be matched; no country assignment was inferred. |
| 14 | requests.xlsx record '5242': Countries Country text 'Guam' could not be matched; no country assignment was inferred. |
| 15 | requests.xlsx record '5242': Countries Country text 'New Caledonia' could not be matched; no country assignment was inferred. |
| 16 | requests.xlsx record '5242': Countries Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. |
| 17 | requests.xlsx record '5242': Countries Country text 'Pitcairn' could not be matched; no country assignment was inferred. |
| 18 | requests.xlsx record '5242': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 19 | requests.xlsx record '5242': Countries Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. |
| 20 | requests.xlsx record '5242': Country 'American Samoa' could not be matched to an ISO3 value. |
| 21 | requests.xlsx record '5242': Country 'French Polynesia' could not be matched to an ISO3 value. |
| 22 | requests.xlsx record '5242': Country 'Guam' could not be matched to an ISO3 value. |
| 23 | requests.xlsx record '5242': Country 'New Caledonia' could not be matched to an ISO3 value. |
| 24 | requests.xlsx record '5242': Country 'Northern Mariana Islands' could not be matched to an ISO3 value. |
| 25 | requests.xlsx record '5242': Country 'Pitcairn' could not be matched to an ISO3 value. |
| 26 | requests.xlsx record '5242': Country 'Tokelau' could not be matched to an ISO3 value. |
| 27 | requests.xlsx record '5242': Country 'Wallis and Futuna Islands' could not be matched to an ISO3 value. |
| 28 | requests.xlsx record '5242': Country text 'American Samoa' could not be matched; no country assignment was inferred. |
| 29 | requests.xlsx record '5242': Country text 'French Polynesia' could not be matched; no country assignment was inferred. |
| 30 | requests.xlsx record '5242': Country text 'Guam' could not be matched; no country assignment was inferred. |
| 31 | requests.xlsx record '5242': Country text 'New Caledonia' could not be matched; no country assignment was inferred. |
| 32 | requests.xlsx record '5242': Country text 'Northern Mariana Islands' could not be matched; no country assignment was inferred. |
| 33 | requests.xlsx record '5242': Country text 'Pitcairn' could not be matched; no country assignment was inferred. |
| 34 | requests.xlsx record '5242': Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 35 | requests.xlsx record '5242': Country text 'Wallis and Futuna Islands' could not be matched; no country assignment was inferred. |
| 36 | requests.xlsx record '5387': Countries Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 37 | requests.xlsx record '5387': Country 'Tokelau' could not be matched to an ISO3 value. |
| 38 | requests.xlsx record '5387': Country text 'Tokelau' could not be matched; no country assignment was inferred. |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 57 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 58 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 59 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 60 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 61 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 62 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 63 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 64 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 65 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 66 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 67 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 68 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 69 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 70 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 71 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 72 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 73 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 74 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 75 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 76 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 77 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 78 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 79 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 80 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 81 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 82 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 83 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 84 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 85 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |