Zambia

Africa | LDC | LLDC

Exported 05 Oct 2026, 14:20 | Snapshot 03 Oct 2026, 21:47 GMT-4

Summary

Zambia is presented in this country card as part of Africa, with Zambia also associated with an unspecified subregion and the LDC, LLDC grouping. The filtered data for Zambia highlights 8 projects for Zambia, including 4 active or planned projects for Zambia and 4 completed or closed projects for Zambia.

For Zambia, the report includes 16 requests for Zambia, 5 RPTC proposals for Zambia, 1 RPTC activities for Zambia, and 1 travel records for Zambia. Financially, Zambia shows USD 18,303,539 in project budget, $362,043 in proposal planned budget, and $6,688 in consumed RPTC activity budget for Zambia.

The main organizational coverage for Zambia points to DISD, Division for Public Institutions and Digital Government, Division for Sustainable Development Goals, DPIDG. Activity records for Zambia list 1,299 participants, including 665 women participants, the current quality review for Zambia includes 73 data quality notes. Current highlights for Zambia include a request focus for Zambia: Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026)

      
This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA).

      
The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs).

      
Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop.

      
The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA.; an RPTC proposal focus for Zambia: Trade Data Tools Implementation and Maintenance 2026; an activity focus for Zambia: Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops..

Key Metrics

| Metric | Value |
| --- | --- |
| Projects | 8 |
| Project budget | USD 18,303,539 |
| Requests | 16 |
| RPTC proposals | 5 |
| Proposal planned budget | $362,043 |
| RPTC activities | 1 |
| Consumed RPTC budget | $6,688 |
| Activity participants | 1,299 |
| Women participants | 665 |
| Travel records | 1 |
| Evaluations | 16 |
| Data quality notes | 73 |

Projects

| Title | Project Code | Scope | Division | Status | Start | End | Budget | Countries | Data info |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries | 2427H | country | Financing for Sustainable Development Office | Active | 01 Feb 2024 | 01 Dec 2027 | USD 750,000 | Jamaica, Malawi, Zambia |  |
| Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure |  | country | Financing for Sustainable Development Office | Active | 01 Mar 2026 | 01 Mar 2029 | USD 2,510,310 | Fiji, Gambia, Kenya, Senegal, Uganda, Zambia |  |
| Monitoring the Sustainable Development Goals |  | country | Statistics Division | Closed | 01 Aug 2016 | 31 Jul 2022 | USD 9,334,229 | Bangladesh, Burundi, Cambodia, Democratic Republic of the Congo, Ethiopia, Ghana, Kyrgyzstan, Lao People's Democratic Republic, Liberia, Mozambique, Myanmar, Nepal, Rwanda, Tajikistan, Uganda, United Republic of Tanzania, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Strengthening capacities of developing countries in harnessing generative Artificial Intelligence to support micro-, small and medium-sized enterprises for transformative changes across the SDGs by enhancing digital connectivity, promoting jobs and elevating shared prosperity |  | country | Division for Sustainable Development Goals | Ongoing | 01 Jan 2025 | 31 Dec 2027 | USD 1,300,000 | Nigeria, Rwanda, Zambia |  |
| Smooth transition beyond graduation for least developed countries in Africa, Asia and the Pacific in a post-COVID-19 environment | 2225B | country | Economic Analysis and Policy Division | Closed | 01 Feb 2022 | 30 Jun 2025 | USD 500,000 | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | Country standardized: 'Lao PDR' -> 'Lao People's Democratic Republic'. |
| Strengthening capacities of developing countries in sub-Saharan Africa to effectively produce and use population estimates and projections in policy-making for sustainable development | ROA 262 | country | Population Division | Closed | 14 Jun 2020 | 17 Dec 2020 | USD 588,000 | Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Djibouti, Ethiopia, Gabon, Ghana, Kenya, Mali, Namibia, Niger, Nigeria, Senegal, Togo, Uganda, Zambia |  |
| Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance | 2427A | country | Division for Sustainable Development Goals | Active | 01 Feb 2024 | 31 Dec 2027 | USD 1,000,000 | Cambodia, Maldives, Namibia, Senegal, United Republic of Tanzania, Zambia | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |
| Towards integrated national financing framework | 2124A | country | Financing for Sustainable Development Office | Closed | 01 Mar 2021 | 28 Jun 2024 | USD 2,321,000 | Belarus, Burkina Faso, Colombia, Costa Rica, Egypt, Indonesia, Jordan, Kyrgyzstan, Pakistan, Zambia |  |

Requests

| Ref | Title | Status | Division | Request date | Start | End | Contact | Summary | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5474 | Request #5474 ? Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Under consideration | Statistics Division | 18 Feb 2026 | 31 Mar 2026 | 02 Apr 2026 | Kossi Edem Kludza ¦ edem.kludza@un.org | Preparing for the implementation of the 2025 SNA: Regional capacity-building workshop for African countries (31 March -2 April 2026) / This regional capacity-building workshop is jointly organized by the United Nations Statistics Division (UNSD), the International Monetary Fund (IMF), the African Union, and the United Nations Economic Commission for Africa (ECA), in collaboration with the other members of the Inter-Secretariat Working Group on National Accounts (ISWGNA). / The workshop aims to strengthen technical capacities of African countries to produce high-quality economic statistics in line with the updated macroeconomic standards, which reflect evolving global economic realities such as globalization, digitalization, and well-being and sustainability. Compiling national accounts in accordance with the updated standards will support data-driven policymaking and facilitate the implementation and monitoring of the Sustainable Development Goals (SDGs). / Approximately 100 participants, including senior officials and independent experts from African countries and international organizations, are expected to attend the workshop. / The requested funds of USD $16,527.46 will cover the travel expenses of two resource persons from UN DESA. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5408 | Request #5408 ? Request for support in macroeconomic analysis, development financing, and social policy | Under consideration | Division for Sustainable Development Goals | 16 Dec 2025 | 01 Jan 2026 | 31 Dec 2026 | Angela Chomba Kawandami ¦ Susan.Mwiche@MCDSS.GOV.ZM | Request for support in macroeconomic analysis, development financing, and social policy |  |  |
| 5235 | Request #5235 ? The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Under consideration | Statistics Division | 11 Jun 2025 | 11 Jun 2025 | 05 Dec 2025 | Matthias Reister ¦ reister@un.org | The Workshop will train participants from national statistical offices on quality assurance and its implementation throughout the national statistical system. It will provide an overview of the contents of the Manual and the UN National Quality Assurance Framework. It will train participants in quality assurance when using administrative and other data sources to produce official statistics using a newly developed tool. The workshop will review and discuss the implementation of quality assurance in participating countries. The Workshop will allow participating countries to share their country practices and challenges in implementing their national quality assurance framework. In addition, the Workshop will discuss the implementation of quality assurance in conjunction with the Generic Statistical Business Process Model (GSBPM). The sharing of experiences will also support the development of further implementation guidance. | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. |  |
| 5208 | Request #5208 ? The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. | Completed | Statistics Division | 12 May 2025 | 04 Aug 2025 | 08 Aug 2025 | Seiffe Tadesse ¦ tadesse5@un.org | The request is for a capacity building workshop to prepare census managers in Anglophone African countries to successfully plan their 2030 round censuses and to effectively implement the Revision 4 of the United Nations Principles and Recommendations for Population and Housing Censuses (P&R Rev.4), endorsed by the 56th session of the Statistical Commission in March 2025. The primary objectives of the workshop include fostering a shared understanding of the updated global standards contained in the P&R Rev.4, enhancing participants' technical proficiencies in applying the revised recommendations (including areas like geospatial data, administrative records, new core topics, contingency planning, quality assurance, and communication), facilitating the exchange of best practices and collaborative problem-solving for anticipated challenges in the upcoming census round, and exploring innovative methodologies and opportunities for future administrative data-based censuses to improve efficiency and quality. / The workshop is jointly organized by the United Nations Statistics Division (UNSD), the African Centre for Statistics at the United Nations Economic Commission for Africa (UNECA), United Nations Population Fund (UNFPA), Statistics South Africa, and the Office of National Statistics of the United Kingdom (ONS-UK). Participants will include representatives from national statistical offices, such as census managers/coordinators or senior census staff responsible for census planning and implementation, as well as managers/senior technical experts in census operations, such as mapping, data processing, ICT or other relevant areas. |  |  |
| 5129 | Request #5129 ? The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Completed | Population Division, Statistics Division | 28 Mar 2025 | 16 Jun 2025 | 20 Jun 2025 | Maria Isabel Cobos ¦ cobos@un.org | The 4th International Forum on Migration Statistics (IFMS 2025) is organised by the United Nations Statistics and Population Divisions, the Organisation for Economic Cooperation and Development (OECD) and the International Organization for Migration (IOM). It will be hosted by the Malmo University in Sweden. The Forum has been welcomed by the UN Statistical Commission, in its decisions 52/109 and 56/109, as a platform to discuss the challenges in gathering and using migration data, as well as related solutions and successful practices. The Forum aims to: / (a) intensify the exchange of information and to facilitate cooperation among relevant stakeholders; / (b) develop statistical capacity to produce basic data on stocks, flows and characteristics of international migrants; and / (c) discuss ways to improve the collection, analysis and use of migration data worldwide, to better inform policy making. | Country standardized: 'Turkey' -> 'Türkiye'. |  |
| 5152 | Request #5152 ? Support the Government of Zambia, through the Public-Private Partnership (PPP) Office under the Ministry of Finance and National Planning, in mobilizing private financing for SDG-aligned projects and benefiting from participation in a future SDG Investment Fair including further piloting and application of "STAIRS" diagnostic tool to pipelining and investment readiness of PPP unit's pipeline in SDG-aligned, infrastructure sectors. | Ongoing | Financing for Sustainable Development Office | 03 Feb 2025 | 03 Feb 2025 | 31 Oct 2025 | Andiseya Lengalenga ¦ collins.mudenda@mofnp.gov.zm | Support the Government of Zambia, through the Public-Private Partnership (PPP) Office under the Ministry of Finance and National Planning, in mobilizing private financing for SDG-aligned projects and benefiting from participation in a future SDG Investment Fair including further piloting and application of "STAIRS" diagnostic tool to pipelining and investment readiness of PPP unit's pipeline in SDG-aligned, infrastructure sectors. |  |  |
| 5168 | Request #5168 ? Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. | Completed | Statistics Division | 17 Jan 2025 | 1 | 1 | Deepchandsingh Jagai ¦ djagai@sadc.int | Background / The increasing complexity of international migration presents significant challenges for statistical measurement and policy formulation. Recognizing the importance of robust data for evidence-based policies, the United Nations Statistical Commission has, over recent years, undertaken several decisions to strengthen statistical standards and frameworks related to international migration and temporary mobility. / The Statistical Commission, in its Decision 49/101 (2018) welcomed the recognition of the importance of data for evidence-based policies in the Global Compact for Safe, Orderly and Regular migration (GCM) and established the Expert Group on Migration Statistics. Furthermore, the Statistical Commission, in its Decisions 52/109 (2021) and 54/104 (2023), endorsed the revised conceptual framework, statistical concepts and definitions, and the set of core and additional indicators on international migration and mobility statistics, as integral parts of the upcoming revision of the Recommendations on Statistics for International Migration. / The Statistical Commission also recognized the urgent need for statistical capacity-building and resources to support countries in their efforts to strengthen their migration data, in the context of the 2030 Agenda for Sustainable Development and the Global Compact for Safe, Orderly and Regular Migration (Decision 50/117, 2019). / The development of a harmonized migration database system to provide migration flows and profiles within the SADC region is a medium-term objective of the SADC Secretariat. / The regional workshop responds to the above mandates as well as the direct request from SADC secretariat and several requests received from countries and regions, notably during the International Forum on Migration Statistics 2023, and the 54th session of the Statistical Commission. The regional workshop will be implemented with technical support from the Collaborative on Administrative Data (CAD) and the United Nations Statistics Division, Social and Gender Statistics Section. / Objectives / â€¢ Increased awareness of target group of standards and methods related to migration statistics: Participants will gain enhanced knowledge of the revised framework, statistical concepts, and definitions endorsed by the United Nations Statistical Commission to improve the quality and comparability of migration data across countries. / â€¢ Enhanced data integration skills and improved implementation practices among target group: The workshop will provide guidance on the practical aspects of implementing new statistical methodologies and indicators on international migration, focusing on overcoming operational challenges, and integrating these into national systems. Emphasis will be on developing skills for understanding and managing administrative migration data, which is essential for producing relevant, high-quality, and disaggregated statistics that can inform policymaking and monitoring. / â€¢ Reinforcement of a community of practice: Participants will benefit from access to a network of experts and a pool of best practices that can assist in continuous improvement post-workshop, ensuring long-term capacity enhancement. |  |  |
| 4904 | Request #4904 ? The Acting Commissioner General of ZRA expressed interest for Zambia to be among the piloting developing countries in the DESA DA16 project on â€œIdentifying and Addressing Vulnerabilities to Aggressive Tax Avoidance in Developing Countriesâ€. The country aims at strengthening its capacity to deal with aggressive tax avoidance and is prepared to actively participate in the project. In response, FSDO acknowledged the efforts of the government of Zambia to increase domestic resource mobilization for financing the national budget and took note of the countryâ€™s request to be part of the piloting countries in the DA project referred above. FSDO expressed it would explore with the ZRA concrete in-country and virtual capacity development activities to address the need for strengthening the capacity of the revenue authority to deal with aggressive tax avoidance. The Office will liaise with ZRA appointed officials with the aim at engaging in further discussions and coordination. | Ongoing | Financing for Sustainable Development Office | 24 Jan 2024 | 01 Jan 2024 | 31 Dec 2027 | Mr. Joseph Nonde ¦ BANDADI@zra.org.zm | The Acting Commissioner General of ZRA expressed interest for Zambia to be among the piloting developing countries in the DESA DA16 project on â€œIdentifying and Addressing Vulnerabilities to Aggressive Tax Avoidance in Developing Countriesâ€. The country aims at strengthening its capacity to deal with aggressive tax avoidance and is prepared to actively participate in the project. In response, FSDO acknowledged the efforts of the government of Zambia to increase domestic resource mobilization for financing the national budget and took note of the countryâ€™s request to be part of the piloting countries in the DA project referred above. FSDO expressed it would explore with the ZRA concrete in-country and virtual capacity development activities to address the need for strengthening the capacity of the revenue authority to deal with aggressive tax avoidance. The Office will liaise with ZRA appointed officials with the aim at engaging in further discussions and coordination. |  |  |
| 4838 | Request #4838 ? Request for support to hold the ePing training for border agencies. | Ongoing | Economic Analysis and Policy Division | 08 Jan 2024 | 01 Feb 2024 | 31 Dec 2024 | Nalituba Mwale (Mrs.) ¦ Moses.Ngosa@mcti.gov.zm | Request for support to hold the ePing training for border agencies. |  |  |
| 4781 | Request #4781 ? UNSD is responding to the request put forward on the Compilation of main messages for the 2023 Voluntary National Reviews | Completed | Statistics Division | 10 Jul 2023 | 10 Jul 2023 | 09 Jul 2024 | Yongyi Min ¦ min3@un.org | UNSD is responding to the request put forward on the Compilation of main messages for the 2023 Voluntary National Reviews |  |  |
| 4678 | Request #4678 ? DPIDG has been requested by AAPAM for support us hosting a DESA breakaway workshop "Promoting Innovation and Digital Transformation for Attaining the SDGsâ€ on a selected thematic area, participation of cabinet secretaries/ Heads of Public Service. The Conference entitled Strengthening Innovation in Public Service to achieve the Sustainable Development Goalsâ€ , Livingstone, Zambia, December 5 â€“ 8, 2023. | Completed | Division for Public Institutions and Digital Government | 17 Apr 2023 | 05 Dec 2023 | 08 Dec 2023 | Dr. G.K. Scott ¦ g.k.scott@aapam.org | DPIDG has been requested by AAPAM for support us hosting a DESA breakaway workshop "Promoting Innovation and Digital Transformation for Attaining the SDGsâ€ on a selected thematic area, participation of cabinet secretaries/ Heads of Public Service. The Conference entitled Strengthening Innovation in Public Service to achieve the Sustainable Development Goalsâ€ , Livingstone, Zambia, December 5 â€“ 8, 2023. |  |  |
| 4731 | Request #4731 ? FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. | Completed | Financing for Sustainable Development Office | 31 Jan 2022 | 01 Jun 2022 | 12 Jan 2022 | Daniel Platz ¦ platz@un.org | FSDO has identified increased demand for peer learning to design risk-informed, data-driven development cooperation policies that support Covid-19 response/recovery. The workshops respond to demand from Member States participating in the 2021/2022 DCF Survey and related policy dialogue. |  | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. / requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 4741 | Request #4741 ? Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Completed | Financing for Sustainable Development Office | 30 Nov 2022 |  | 13 Dec 2023 | Feriel Zemzoum ¦ feriel.zemzoum@un.org | Technical Guidance on INFFs and Illicit Financial Flows (IFFs): Additional technical guidance material on INFFs and addressing IFFs and financial integrity, in response to a request of the General Assembly (GA L.60, paragraph 9: "[..] requests the Inter-Agency Task Force on Financing for Development to explore recommendations to assist Member States in incorporating financial integrity actions into their financing frameworks." | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. / requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. / requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 4234 | Request #4234 ? Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Completed | Statistics Division | 05 Jul 2022 | 08 Jan 2022 | 30 Dec 2022 | UN Statistical Commission ¦ vibeke.nielsen@un.org | Through the work of the Global Network of Institutions for Statistical Training (GIST) it has been re-confirmed that there is an urgent need to support developing countries in creating and better maintaining statistical training programs at national level. This is key for staff at the National Statistical Systems (NSS) to receive core trainings for doing their jobs efficiently, and will make the NSS less dependent on external partners. / GIST has identified that a key first step is to help countries develop a needs assessment tool to understand the training needs of their staff as well as key development area needs from a managerial perspective. In relation to this, there is also a need to provide guidance on how to prioritise among gaps identified as well as to provide template curriculums for courses that are expected to be core in all countries. / GIST members are actively supporting the work, but are in needs of support in coordinating the work, helping it move forward more quickly to respond to countries needs and ultimately help staff in the NSS improve their skills more systematically to increase efficiency of the NSS in providing quality and timely SDG and other statistics to the public. | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. |  |
| 4135 | Request #4135 ? 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Under consideration | Financing for Sustainable Development Office | 03 Jan 2022 | 03 Jan 2022 |  | Natalia Aristizabal Mora ¦ natalia.aristizabalmora@un.org | 1) E-learning course: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design an INFF online learning experience as well as develop interlinked modules of the INFF e-learning course, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 2) INFF videos: the proposal will allow the Financing for Sustainable Development Office (FSDO), to design and develop a series of explainer videos on INFFs and particularly the INFF building blocks, in collaboration with implementing partner organizations from the UN system, including UNDP and ESCAP. / 3) Deep dives: The proposal will allow the Financing for Sustainable Development Office (FSDO) to develop, in consultation with the Inter-agency Task Force on Financing for Development, additional guidance materials to support country authorities and UN Country Teams in the design and implementation of Integrated National Financing Frameworks in specific sectors and financing policy areas. / 4) SIDS workshop: The proposal will allow the Financing for Sustainable Development Office (FSDO), to contribute to the design and implementation of a workshop on Integrated National Financing Frameworks (INFF) specifically targeting the needs of Small Island Developing States (SIDS). | Country standardized: 'Cote d'Ivoire' -> 'Côte d’Ivoire'. / Country standardized: 'Timor-Leste' -> 'Democratic Republic of Timor-Leste'. |  |
| 3654 | Request #3654 ? The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" | Completed | Division for Public Institutions and Digital Government | 16 Feb 2021 | 11 Nov 2021 | 25 Nov 2021 | Jan Magoro ¦ JanMa@presidency.gov.za | The government of Kenya and other African countries requested support in promoting sound policymaking through the organization of an online webinar series on sound policy making. Webinar Series - Resilience & Recovery from Covid-19 through Sound Policymaking" |  |  |

RPTC Proposals

| Project ID | Title | Division | Planned start | Planned end | Budget | Countries | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001376.99.99.23 | Trade Data Tools Implementation and Maintenance 2026 | SD | 30 Sept 2026 | 31 Dec 2026 | $140,387 | Eswatini, Ghana, Guyana, Papua New Guinea, Saint Lucia, Zambia | Region standardized: 'global' -> 'Global'. | proposals.xlsx record 'SB-001376.99.99.23¦row:30': 'f_cashOther' has non-numeric value 'Eurostat provides a grant of 53,000 USD to improve and maintain TDT in 2026. The African Union Commission (AUC) will cover the participation cost of its selected member states.'. |
| SB-001380.90 | Peer-to-peer Learning Workshops for the Network of National Focal Points on Financing for Development | FSDO | 30 Sept 2026 | 31 Dec 2026 | $25,000 | Armenia, Bahrain, Belize, Benin, Botswana, Burkina Faso, Cabo Verde, Cambodia, Comoros, Croatia, Czechia, Democratic Socialist Republic of Sri Lanka, Djibouti, Egypt, Eswatini, Ethiopia, Finland, France, Germany, Greece, Guatemala, Hungary, Ireland, Italy, Japan, Kenya, Korea, Lao People's Democratic Republic, Luxembourg, Madagascar, Malawi, Malaysia, Mauritius, Norway, Oman, Papua New Guinea, Paraguay, Peru, Poland, Sao Tome and Principe, Saudi Arabia, Seychelles, Sierra Leone, Switzerland, Thailand, Togo, Tuvalu, Uganda, United Kingdom of Great Britain and Northern Ireland, Uruguay, Zambia, Zimbabwe | Country standardized: 'Republic of Korea' -> 'Korea'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Region standardized: 'global' -> 'Global'. |  |
| SB-001379.99.30 | Strengthening Inclusive and Shock-Responsive Social Protection Systems in Africa | DISD | 31 Dec 2026 | 31 Dec 2026 | $40,889 | Djibouti, Ethiopia, Ghana, Kenya, Namibia, Rwanda, Senegal, Uganda, United Republic of Tanzania, Zambia |  | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. / proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| SB-001375.99.48 | Preliminary review and strengthening of the proposed Vulnerability–Resilience Country Profile (VRCP) methodology | DSDG | 31 Dec 2026 | 31 Dec 2026 | $68,000 | Cabo Verde, Mauritius, Nauru, Seychelles, Sudan, Viet Nam, Zambia | Region standardized: 'global' -> 'Global'. |  |
| SB-001374.99.40 | Strengthening Artificial Intelligence (AI) Capabilities and Governance for Sustainable Digital Transformation in Africa and Asia-Pacific | DPIDG , DSDG | 30 Sept 2026 | 30 Sept 2026 | $87,767 | Algeria, Burkina Faso, Burundi, Cambodia, Democratic Socialist Republic of Sri Lanka, Gambia, Guinea-Bissau, Kenya, Lao People's Democratic Republic, Pakistan, Rwanda, Sierra Leone, Togo, Uganda, United Republic of Tanzania, Uzbekistan, Viet Nam, Zambia, Zimbabwe | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. | Proposal past due |

RPTC Activities

| Project ID | Title | Division | Start | End | Consumed budget | Participants | Women | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-001380.88 | Strengthening developing countries’ capacity to address transfer-pricing challenges related to centralized procurement activities and to enhance their VAT/GST systems through global virtual workshops. | FSDO | 29 Jan 2026 | 18 Feb 2026 | $6,688 | 1,299 | 665 | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'St. Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Tanzania (United Republic of)' -> 'United Republic of Tanzania'. / Region standardized: 'global' -> 'Global'. | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |

Travel

| Title | Travel Code | Past / Forecast | Country | City | Division | Travel Reason / Event | Event Type | Start | End |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S9AC0003_DSDG - Zambia | S9AC0003_DSDG | Forecast | Zambia | Lusaka | DSDG | Promoting Inclusive and Sustainable Adoption of Generative Artificial Intelligence among MSMEs in Zambia for Accelerating Sustainable Development | National Workshop | 27 Oct 2026 | 30 Oct 2026 |

Evaluations

| Title | Year | Divisions | Countries | Recommendations | Lessons learned | Document | Data info | Warnings |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Building Capacities for Promoting Women’s Presence and Leadership within Public Institutions at National Local Levels | 2024 | DPIDG | Bhutan, Cambodia, Lao People's Democratic Republic, Mauritius, Senegal, Sierra Leone, Solomon Islands, Vanuatu, Zambia | - Engage the target beneficiaries of the intervention in consultations during a project planning activity, to further inform and finalise the contextual project design. / - Conduct a risk assessment and identify viable mitigation measures for incorporation into the project document to stem the effects of possible risks to project implementation and results achievement. / - Explore a greater use of virtual interface options, to further support the contribution of the project towards value for money. / - Collaborate closely with a monitoring and evaluation specialist during project design, to inform the development of the project theory of change/ logical framework to guide effective results monitoring and reporting. / - Incorporate an element of follow-up into the project design and facilitate its implementation, to support the use of project learnings by participants for enhanced public administration practice. / - Ensure that the project results framework includes indicators for monitoring and reporting on the integration of the UNDESA cross-cutting themes into project implementation. | - Consultations with target project beneficiaries during the planning stages of the project are important for contextualising project implementation and mitigating risks to implementation and results achievement. / - A risk assessment is needed to support increased project efficiency and effectiveness by mitigating possible risks to project implementation and results achievement. / - Specialist guidance for the development of the project logical framework/theory of change increases the potential for the project to document rich evidence of its importance. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects in Umoja/S1-179 Italy leadership of women in public institutions/Evaluation/Output-6-Final Evaluation Report_UNDESA_10DEC2024.pdf |  |  |
| African Statistical Knowledge Network in support of progress towards the internationally agreed development goals | 2012 | UNSD | Algeria, Angola, Benin, Botswana, Burkina Faso, Burundi, Cabo Verde, Cameroon, Central African Republic, Chad, Comoros, Congo, Côte d’Ivoire, Democratic Republic of the Congo, Djibouti, Egypt, Eritrea, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guinea, Guinea-Bissau, Kenya, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Nigeria, Rwanda, Sao Tome and Principe, Senegal, Seychelles, Sierra Leone, Somalia, South Africa, Sudan, Togo, Tunisia, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Create awareness and promote the value of ASK-Net aggressively by disseminating information in major meetings, conferences, and professional associations. / - Re-invigorate inactive sub-networks within ASK-Net, possibly by introducing incentives or removing inactive sub-networks from the website. / - Follow up with study tour participants periodically to assess if they are applying what they learned. / - Encourage network members to actively update and contribute to the ASK-Net website to ensure its long-term impact. / - Monitor ASK-Net website performance using tools like Google Analytics and report traffic statistics quarterly to management. / - Promote sub-regional collaboration and coordination with Regional Economic Communities (RECs) in implementing statistical projects. / - Take workshop participant evaluations seriously, archive analyzed results, and conduct follow-up after some time, especially for study tours. / - Conduct surveys and questionnaires to measure awareness, use, and knowledge sharing as a result of ASK-Net, as originally planned in the project document. | - The Steering Committee, in collaboration with ACS and UNSD, was crucial in aligning project deliveries with other statistical development initiatives in Africa. / - The revised study tour modality enhanced South-South cooperation by making expert support more relevant to countries in need. / - Almost all African countries participated in project events, but future workshops should consider the distribution of country participation across events. / - Some NSOs sent staff not directly involved in workshop themes, which reduced optimal experience sharing and network strengthening. / - Contributions from resource persons at UNSD, ILO, and other organizations raised the quality of workshop outputs to international standards. / - Involvement of development partners contributed to project success and ensured sustainability of outcomes. / - Compiling member country inputs through the ASK-Net website for the statistical data management handbook proved to be a useful and cost-saving approach. / - ACS staff benefited from project execution and experience sharing with UNSD. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 102 - 6th tranche - Afr Stat Know Net towards Agreed Develop Goals/Progress Reports/ASKN Project Eval Rep-YZ-29 June.docx | Country standardized: 'Cape Verde' -> 'Cabo Verde'. / Country standardized: 'Republic of the Congo' -> 'Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Terminal Evaluation of Project (Final Report) DA13 INFF Project 2124A ‘Towards Integrated National Financing Framework’ | 2025 | FSDO; EAPD | Belarus, Burkina Faso, Costa Rica, Dominican Republic, Egypt, Jordan, Kyrgyzstan, Pakistan, Samoa, Zambia | - Project conceptualisation should be preceded by a scoping session and/or planning meeting between the executing entities and the cooperating entities, to establish synergies, enhance relevance, and minimise risk, including the possibility for and perception of duplicated efforts. / - Clarified roles and responsibilities at the level of project management and activity coordination should be established to allow for efficient oversight throughout the implementation timeframe. / - Guidance documents on the INFF methodology should provide detailed, step-by-step guidelines that can be easily contextualised by the implementing country. / - The FINS project should be scaled up to provide post-project technical assistance to target and non-target countries in response to their requests for context-specific support for INFF implementation. / - A strengthening of the process for finalising and approving the project results framework should be initiated, to ensure that appropriate results targets and performance measurement indicators are established to increase the usefulness of achieved results. | - The project development phase needs to be reliably informed by a detailed assessment of risk, parallel interventions, and the contextual situation in the countries of intervention focus. / - Efficient project oversight is dependent on a clarified overview of roles and responsibilities at the level of project management. / - The effective application of the INFF methodology at the country-level requires detailed step-by-step guidelines to inform contextualisation. / - The ownership of the INFF methodology by national political leadership contributes towards a demand-driven process that is critical for effective implementation. / - A flexible design combined with strategic partnerships contributes towards stronger impact and the maximisation of efficiency and synergies. / - Digital platforms and data infrastructure support effective implementation and enhance knowledge-exchange and sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/FSDO/2124A SB-016729.01 INFF/Evaluation report/REVISED Final Evaluation Report_INFF Evaluation_7OCT2025.docx |  |  |
| Inclusive Development for Indigenous Peoples in Africa | 2024 | DISD; CDPMO | Angola, Botswana, Burundi, Kenya, Malawi, Mozambique, Namibia, South Africa, Uganda, United Republic of Tanzania, Zambia, Zimbabwe | - Design and implement, with the participation of target governments and Indigenous Peoples, a second phase of the project to continue processes initiated in target countries, including developing Free, Prior and Informed Consent (FPIC) mechanisms, Indigenous Peoples' Analysis (IPA) per country/region, and supporting institutional capacity. / - Engage other bilateral and multilateral donors such as USAID, European Union, World Bank, and African Development Bank to mobilize technical and financial support, ensuring meaningful participation of Indigenous Peoples. / - Increase engagement with Indigenous Peoples in target countries by setting mechanisms to increase diversity and reach Indigenous Peoples in remote areas, supporting their participation in project activities and political processes. / - Increase the incorporation of United Nations Resident Coordinators and Country Teams into the project to enable conversations and support Indigenous Peoples' rights, engaging them in the development of Development Assistance Frameworks and country program action plans. / - Expand dialogue and training on Indigenous women, youth, and other groups in society that remain invisible, implementing the project through intersectional lenses and ensuring sufficient financial and technical capacity. / - Improve data collection, monitoring and evaluation, and database management, developing indicators in cooperation with Indigenous Peoples and target governments, and ensuring relevant qualitative indicators are set from the beginning of the project. | - Development approaches that respect Indigenous Peoples’ rights and engage them as partners in design, implementation, management, administration, monitoring, and evaluation are vital to achieving the 2030 Sustainable Development Goals. / - Flexibility and adaptability are essential in project implementation to respond to emerging needs and local contexts, as demonstrated by the development of a conservation toolkit and COVID-19 materials. / - Ownership of the process by Indigenous Peoples and stakeholders at different levels is key to sustainability and success. / - Capacity development and participatory approaches are effective in strengthening national capacities and advancing policy drafts, but institutionalization and political support are necessary for long-term impact. / - Ensuring diversity and inclusion, particularly of Indigenous women and youth, requires targeted activities and proactive engagement strategies. / - Improved monitoring mechanisms, data collection, and systematic evaluation are needed to better assess project outcomes and inform future efforts. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/2023C SB-014517 Indigenous in Africa/Evaluation/DESA_2023C_Evaluation report_Mngt response.pdf | Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Mobilizing Science, Technology and Innovation in developing countries for the SDGs | 2022 | DSDG | Belgium, Brazil, Cambodia, China, Ethiopia, Ghana, India, Japan, Kenya, Korea, Madagascar, Mozambique, Myanmar, Pakistan, Philippines, Rwanda, Serbia, Thailand, Uganda, United States of America, Zambia | - DESA should ensure that projects are based on clear objectives and SMART, relevant indicators which better help measure the impact of activities. / - DESA should ensure regular and efficient monitoring throughout the project, based on thorough monitoring plans. / - DESA should ensure the continuation of the Innovation Competition and participation in the STI Forum for the winners, and develop a longer term programme of Capacity Building and support for these winners. / - DESA should build on the Capacity Building events, Study Visits, STI Roadmaps work and the Ghana Pilot Programme, which were all highly relevant to STI in developing countries. / - DESA should focus on strengthening the OLP, which currently has a low level of relevance to STI in developing countries. DESA should revisit the Independent Technical Assessment and R4D’s recent report ‘UN 2030 Connect Report’ and integrate the prototypes into the OLP. / - If the OLP and associated capacity building activities are to continue, DESA should look carefully at the human and financial resources behind the work, ensuring that there is enough capacity to deliver meaningful results. DESA should consider the financial recommendations made in the Independent Technical Assessment. Resources available must match the ambition for the work, and the level of ambition should be clarified asap. / - Any future project should include longer term support for innovators on the ground, over a period of at least a year. This could focus on the winners of Innovation Competitions. / - Any future project should build on the successes and the lessons learned of the Ghana Pilot Project, which could be scaled to other countries in partnership with R4D. / - DESA should improve the ongoing monitoring around such projects, strengthening the indicators (ensure SMART and relevant indicators) and ensuring that questionnaires are provided to participants following relevant activities (Capacity Building sessions, Study Visits etc). / - DESA should spend more time persuading and convincing partners of the value of integrating their databases with that of the OLP, in order to address the perceived incoherence with OLP partners. / - DESA and partners should consider the viability of one overarching STI project / work stream which incorporates the various streams of work being undertaken - the STI Forum, STI Roadmaps for SDGs, 2030 Connect, Capacity Building etc. The possibility of a joint funding mechanism – an STI Trust Fund – should be explored in order to reduce inefficiencies. / - DESA should allocate meaningful human resources (at least 60% of a full time role) to ensure the success of the OLP and associated Capacity Building activities. / - DESA should ensure that resources allocated to the OLP match the ambition for the OLP. / - DESA should consider allocating more funds for longer term Capacity Building support to innovators across target countries. / - DESA should consider replicating / adapting the relationship with R4D, recognising the importance of having local partners to work with local innovators. This could either be done with R4D, other relevant CSOs or UNCTs (UN Country Teams). / - DESA should ensure there is enough time available for meaningful work to be completed, avoiding last minute rushes. / - DESA should systematically work through tools like Exit strategies, succession planning and cases for financial support before the end of a project, in order to ensure sustainability, whether a project is designed to continue or not. / - DESA, with the IATT, should revisit the Independent Technical Assessment, as well as the recent recommendations by R4D for the OLP, in order to be very clear about the ambition and strategic direction of the OLP before developing the case for support. / - Given the clear mandate provided by MS for the OLP, DESA should attempt to secure a mixture of UN regular budget and voluntary/extra-budgetary funds to finance the OLP. / - DESA should ensure that capacity building activities take place over a longer period, and provide more sustained support for innovators. This should be built into the case for support. / - The UN should integrate the principle of Leave No-One Behind into all its STI related work, ensuring that it does not inadvertently enhance the digital divide. This could be done in the context of this project by offering capacity building activities in different languages, offering interpretation, and ensuring translation of the OLP. / - DESA should consider scaling up the Ghana Pilot Project into other countries, specifically the Technical Support offered to local innovators. / - DESA should build on the momentum around the STI Roadmaps for SDGs and investigate whether a coherent package of work can be built around the Roadmaps, the OLP and the capacity building activities. / - DESA and OICT should consider structuring the OLP (specifically the Search Engine) around the SDGs in order to facilitate closer linkages between STI and HR & GE. / - DESA, and the UN more widely, should strengthen the focus on HR & GE in the project design and monitoring, including concrete details of how HR & GE issues will be addressed. UNEG’s guidance on this should be considered. / - DESA, and the UN more widely, should respect the SDG principle of LNOB by ensuring Capacity Building activities include interpretation, and official sites are available in at least the 6 official languages of the UN. / - DESA should consider contributing to tackling the existing gender inequality in STI by insisting on having at least 50% of women as speakers, moderators and participants in events. / - DESA should incorporate HR & GE specific indicators in its project design. Again, UNEG’s guidance on this should be considered. / - DESA should commit to gathering disaggregated data throughout its projects, starting with clear participant lists for every activity. / - The UN PDF should ensure that the recently developed form which collects HR & GE data is consistently used across all projects which it supports. / - DESA should build on the good practise of the Study Visits, Capacity Building Sessions and Ghana Project, linking STI to specific SDGs and gender issues in order to ensure a meaningful focus on HR & GE. / - DESA should use its position as implementer of this project and Co-Convenor of the IATT to work closely with the IATT to consider the ambition and funding for the OLP, ensuring coherence with the mandate given by MS in Agenda 2030, the AAAA and the Independent Assessment. / - DESA should continue the practise of piggybacking on other meetings and cost-sharing when organising activities. | - The project design could have been improved by developing stronger and more relevant indicators which better help measure the impact of the activities, and by ensuring regular and efficient monitoring throughout the project. / - Insufficient human and financial resources can significantly limit the effectiveness and efficiency of project implementation. / - A lack of clear exit planning, succession planning, and fundraising strategy can undermine the sustainability of project outcomes. / - Longer-term engagement and support for innovators, rather than one-off events or competitions, are valued and more likely to lead to sustained impact. / - Capacity building activities are more inclusive and effective when offered in multiple languages and with interpretation, supporting the Leave No-One Behind principle. / - Partnerships with local organizations, such as R4D in Ghana, enhance the relevance and effectiveness of capacity building for local innovators. / - Integrating gender and human rights considerations from the project design stage, with specific indicators and disaggregated data, leads to better outcomes and more inclusive participation. / - Administrative and technical barriers to integrating partner databases can undermine the effectiveness and coherence of online platforms. / - Piggybacking on existing meetings and cost-sharing with partners increases efficiency and reach. / - Clear political mandates and alignment with broader UN strategies facilitate project relevance and coherence, but must be matched by adequate resources and stakeholder engagement. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2016/PDF-2016-03 DSD internal STI/Reports/Final report & Eva/fisrt ver. 18 Mar 22/STI Evaluation LW final.pdf | Country standardized: 'USA' -> 'United States of America'. | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation | 2021 | DSDG | Algeria, Argentina, Austria, Bolivia (Plurinational State of), Bosnia and Herzegovina, Bulgaria, Colombia, Ecuador, Ethiopia, Georgia, Ghana, Guyana, Honduras, India, Italy, Kenya, Lebanon, Malawi, Morocco, Nauru, Niger, North Macedonia, Pakistan, Papua New Guinea, Poland, Portugal, Samoa, Seychelles, United Arab Emirates, United Kingdom of Great Britain and Northern Ireland, Zambia | - Future similar projects should apply a Results-Based Management approach, developing an M&E framework, plan, and data collection tools that articulate instrumental and transformational changes rather than processes. / - Additional resources should be mobilized to ensure follow-up and implementation of the commitments secured in the global roadmap and in the Energy Compacts, starting with pilot projects to determine their viability and scalability. / - Future similar projects should include studies on Cost-Benefit Analysis to determine the viability and scalability of policy changes, ranking options in the Energy Compacts according to their costs and benefits to society. / - More staff wholly dedicated to the project should be planned for at the conceptualization stage, including roles for communications and project management assistance, and a project steering committee to ensure recommendations for course corrections are followed. / - Future projects should develop a clear partnership strategy to guide implementers on where to invest in collaboration for the greatest value to the organization. / - The composition of the global Technical Advisory Group (TAG) should be replicated and cascaded to regional and national levels to ensure continuity and nuanced specificities beyond the project’s shelf life. / - Future projects should leverage United Nations Information Centers (UNICs) to develop and implement coordinated communications strategies for Member States, amplifying project achievements at the local level. | - The joint production and dissemination of knowledge products laid a strong foundation for sustainability, scaling up, replication, and future programming, increasing knowledge and capacities for accountability. / - Synergistic partnerships and multi-stakeholder participation facilitated ownership, sustainability, and coherence between national planning processes, enhancing coordination among line ministries for timely VNR production. / - Upstream activities allowed the project to adapt to challenges such as Covid-19, and partnering with the public sector leveraged government influence for mainstreaming SDG7 implementation. / - Engagement with the private sector was strategic, as private sector input and financial commitments in the Energy Compacts are essential for accelerating SDG7 implementation. / - The project was initially thinly staffed, but hiring a dedicated Project Officer after commencement improved implementation; future projects should plan for adequate dedicated staffing from the outset. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/2017/2017-02 DSD SDG7/Reports/Evaluation/Final_Dec 18th_UNDESA_Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| Strengthening statistical capacity-building in support of progress towards the Internationally Agreed Development Goals in the Southern African Development Community (SADC) region | 2011 | UNSD | Angola, Botswana, Democratic Republic of the Congo, Eswatini, Lesotho, Madagascar, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, United Republic of Tanzania, Zambia, Zimbabwe |  | - Focus on a single objective to make project planning and evaluation more manageable and effective. / - Put more effort into developing indicators that encompass quantity, quality, and time, and that can be reliably calculated with minimal resources. / - Build production of monitoring and evaluation indicators into the project by providing appropriate budget, staffing, data sources, and procedures in project planning. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/SD/ROA 86 - Support to MDGs in SADC/Eval Report Feeney/UNSD-SADC Final Evaluation Report.pdf | Country standardized: 'DR Congo' -> 'Democratic Republic of the Congo'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. |  |
| Global Centre for ICT in Parliament End-of-term Project Evaluation | 2013 | DPIDG | Algeria, Angola, Antigua and Barbuda, Bangladesh, Barbados, Belize, Benin, Botswana, Brazil, Cambodia, Cameroon, Canada, Chile, Colombia, Comoros, Congo, Costa Rica, Democratic Republic of the Congo, Democratic Socialist Republic of Sri Lanka, Dominica, Dominican Republic, Ecuador, Egypt, Eswatini, Federation of Saint Kitts and Nevis, Finland, Gabon, Georgia, Ghana, Grenada, Guyana, Haiti, Honduras, Italy, Jamaica, Kenya, Lesotho, Malawi, Malaysia, Mauritius, Mexico, Montenegro, Morocco, Mozambique, Namibia, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Saint Lucia, Saint Vincent and the Grenadines, Seychelles, Sierra Leone, South Africa, Spain, Suriname, Switzerland, Trinidad and Tobago, Turkmenistan, Uganda, United Kingdom of Great Britain and Northern Ireland, United Republic of Tanzania, United States of America, Uruguay, Viet Nam, Zambia, Zimbabwe | - Focus planning on short to medium term funding and create continuity of funding to enable proper planning and development of work streams. / - Consider increasing staff numbers to meet opportunity and demand, building a sustainable model for long-term support of parliaments. / - Continue collaboration between the United Nations (DESA) and the IPU, and expand where possible. / - Develop relationships with other parts of the UN interested in parliamentary strengthening, such as UNDPA and UNDP. / - Create a Partners Advisory Committee consisting of key funders to provide strategic input and increase funder engagement. / - Narrow policy work to areas directly related to and sustaining practical work in parliaments, such as open data policies, citizens’ participation, and access to information. / - Devote the majority of efforts to practical strategic and tactical areas: benchmarking and surveys, guides and reports, conferences and networks, and support and assistance to parliaments. / - Monitor and support the adoption of emerging digital trends, including open parliaments, social media, and mobile technologies. / - Increase staffing to deliver outputs and meet future stakeholder demand. / - Expand networks and training to cover a wider geographical base, including Asia and the Pacific region. / - Create virtual networks for peer-to-peer exchange, professional development, and support. / - Attract core funding from a wider range of funders and consider philanthropic, corporate, or alternative sponsorship with strong governance procedures. / - Balance project-based funding with core funding to avoid focus loss and ensure strategic vision. | - Practical support and peer-to-peer relationships are critical for building capacity in parliaments, especially in developing countries. / - Regional and topical networks are effective in supporting ICT development and democratic strengthening in parliaments. / - Benchmarking tools and guides are highly valued for supporting planning, business cases, and adoption of good practices. / - Collaboration with partners such as IPU, ASGP, and IFLA enhances the quality and reach of outputs. / - Sustainable funding and adequate staffing are essential to maintain and expand the Centre’s impact. / - Emerging trends in technology require ongoing training, support, and guidance for parliaments. / - The Centre’s unique parliamentary focus and ability to build goodwill among stakeholders are key to its effectiveness. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects (sent to archives)/INT05X73 - Global Centre for ICT Parliament/Final Evaluation/Global Centre Evaluation Final.pdf | Country standardized: 'Saint Kitts and Nevis' -> 'Federation of Saint Kitts and Nevis'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. / Country standardized: 'United Kingdom' -> 'United Kingdom of Great Britain and Northern Ireland'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development | 2018 | FSDO | Angola, Argentina, Bahamas, Barbados, Benin, Bolivia (Plurinational State of), Botswana, Burundi, Cambodia, Cameroon, Chad, Chile, Comoros, Costa Rica, Democratic Socialist Republic of Sri Lanka, Djibouti, Dominican Republic, Ecuador, El Salvador, Eswatini, Ethiopia, Gabon, Gambia, Ghana, Guatemala, Honduras, Indonesia, Jamaica, Kenya, Lao People's Democratic Republic, Lesotho, Liberia, Madagascar, Malawi, Mali, Mauritius, Mexico, Mongolia, Morocco, Mozambique, Namibia, Nepal, Nicaragua, Niger, Nigeria, Pakistan, Panama, Paraguay, Peru, Philippines, Rwanda, Samoa, Senegal, Seychelles, Sierra Leone, South Africa, Suriname, Thailand, Togo, Trinidad and Tobago, Uganda, United Republic of Tanzania, Uruguay, Viet Nam, Zambia, Zimbabwe | - UN-DESA FfDO must continue their capacity building activities on Double Tax Treaties at global, regional and national level. / - It is imperative to launch the online UN course on Double Tax Treaties and online platform allowing wide access to officials from the NTAs and MoFs in developing countries. / - More emphasis should be placed on enhancing networking opportunities at regional and global events, including tools for international tax collaboration and sharing practical lessons. / - FfDO might consider developing a portfolio of short case studies and country examples to deliver training seminars with practical sessions, using the online UN Course on Double Tax Treaties for basic knowledge. / - FfDO might make an extra effort to ensure inclusion of officials whose first language is not English by providing simultaneous interpretation and increasing the pool of facilitators able to deliver presentations in local languages. / - FfDO might consider implementing a more exhaustive screening process for participant selection, including a short CV and a specific trainee profile to guide candidate presentation. / - It is recommended to develop a plan to implement activities in Asia, including establishing partnerships with academic and professional networks to facilitate regional training events. / - Recommendation No.7 might be extended to Latin America and Africa, encouraging cooperation with academic and professional networks to sustain and institutionalize capacity development and knowledge in double tax treaties. | - Demand for training and building capacity in Double Tax Treaties is high and relevant; efficient tools include the UN Course, Manual, and Handbook, but more case studies and practical sessions are needed. / - Effective training on Double Tax Treaties requires participants to prepare in advance, acquiring basic international taxation theory, terminology, and knowledge of their own country's legal background. / - Regional tax organizations are key partners for project success and their stewardship can be expanded to institutionalize cooperation. / - Capacity building activities can have multiplier effects, such as creating regional pools of experts who disseminate knowledge and support peers; these effects should be strategically included in project planning. / - Indicators of achievement should be measurable and reflect quality benefits, including benchmarks and variables for counterfactual analysis, and should account for unintended effects to capture externalities. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Audits/2018 Audit information/ROA 257 - FFDO Final Evaluation Report.pdf | Country standardized: 'Bolivia' -> 'Bolivia (Plurinational State of)'. / Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Tanzania' -> 'United Republic of Tanzania'. | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. / evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies | 2015 | DPAD | Afghanistan, Bangladesh, Bhutan, Botswana, Cambodia, Chile, China, Democratic Socialist Republic of Sri Lanka, Eswatini, India, Indonesia, Kazakhstan, Korea, Lao People's Democratic Republic, Lesotho, Mozambique, Myanmar, Namibia, Nepal, Philippines, Singapore, South Africa, Tajikistan, Thailand, Uzbekistan, Viet Nam, Zambia | - Future capacity development projects of UNDESA should be sufficiently ambitious in their objectives but designed with adequate flexibility to deliver capacity development objectives in a demand-driven and nationally-owned manner. / - Future projects should ensure sufficient flexibility in the activities listed in project documents, making the list of activities indicative and not a binding constraint. / - Future training workshops should allocate additional time for discussion among participants and distribute research and background papers in advance. / - Future capacity development projects should include a post-project phase engagement framework to ensure sustainability of project interventions, especially since UNDESA is a non-resident entity. / - Future projects should earmark resources to facilitate the deployment of experts from other UN agencies to reduce dependence on external consultants. / - Future capacity development projects should make fostering South-South Cooperation a stated objective, with a clear focus on enabling developing countries to learn from each other. / - Future projects may devote technical and financial resources to develop an online forum to ensure the sustainability of interventions beyond completion. / - Future projects would benefit from having a clear and well-defined monitoring and evaluation strategy, including early recruitment of an external evaluator and allocation of resources for field visits and online evaluation tools. / - UNDESA should continue to provide policy-advisory and capacity development support to beneficiary countries and add a few additional countries to ensure sustainability of the impacts. | - An integrated approach, building on previous successful projects and deepening engagement in a few countries, leads to significant multiplier effects, cost-savings, and greater policy impact. / - Flexibility and improvisation in project implementation allow for responsiveness to evolving needs and ensure country ownership, rather than following a rigid, pre-determined set of activities. / - There is greater demand for country-specific, evidence-based policy advice than for generic handbooks or textbooks. / - Partnerships with other UN agencies, especially UNDP and regional commissions, are key to sustaining project impact and should be further strengthened. / - South-South cooperation, though not a stated objective, emerged as a valuable outcome and should be explicitly included in future project objectives. / - Establishing online communities or networks for trained officials and trainers can help sustain knowledge exchange and learning beyond project completion. / - A clear and well-defined monitoring and evaluation strategy, including early involvement of external evaluators and use of online tools, improves the quality and comprehensiveness of project evaluation. / - The project generated new requests for support from additional countries, indicating the importance of maintaining and expanding capacity development support to ensure sustainability. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/Evaluation reports/6th tranche/ROA 182 (DPAD)/Final Evaluation Report of MAC - Complete.pdf | Country standardized: 'Sri Lanka' -> 'Democratic Socialist Republic of Sri Lanka'. / Country standardized: 'Swaziland' -> 'Eswatini'. / Country standardized: 'Vietnam' -> 'Viet Nam'. | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Post-Facto Evaluation of Completed Projects under the 2030 Agenda for Sustainable Development Sub-Fund of the UN Peace and Development Fund (UNPDF) | 2021 | CDPMO; UNSD | Botswana, Ethiopia, Fiji, Ghana, Iran (Islamic Republic of), Kenya, Lao People's Democratic Republic, Lesotho, Malawi, Namibia, Pakistan, Samoa, Uganda, Vanuatu, Viet Nam, Zambia, Zimbabwe | - Continue ensuring that project proposals clearly state the suggested project management arrangements with clearly defined roles and responsibilities. / - For the assessment of new project proposals, include a new criterion titled 'virtual meetings' as an efficiency measure to enhance projects’ cost efficiency and reduce the environmental footprint of the projects with significant components concerning meetings and workshops. / - For the approval of final reports, contact lists of beneficiaries should be mandatory as attachments to the final reports for accountability purposes. This requirement should be clearly communicated in the funding guidelines. / - Use the factors identified for effective project performance, i.e. gender and equity and capacity building, when assessing the quality of new project proposals. For projects with a significant knowledge management or capacity building component it is recommended to demand from grantees the design and use of event and training feedback mechanisms to monitor project results. For projects with a focus on the community level, grantees should specify how to reach women, girls, and youth in general. The latter seems particularly relevant in the migration context, as well as access to education and health services. | - Bringing the SDGs to sub-national level is important, including preparing integrated financing frameworks, strengthening evaluative capacities, and accelerating progress at the sub-national level. Stakeholder engagement should be further strengthened in all steps of the implementation of 2030 Agenda at the sub-national level. / - Regular fortnightly field monitoring visits to all training institutes proved useful for checking teaching ability, availability of training aids, and ensuring attendance of trainees and teaching staff. / - Providing a nominal monthly allowance to trainees helped prevent dropout and non-attendance by addressing needs such as refreshments and transportation, without creating dependency. / - Training Afghan and Pakistani females in and near their refugee villages allowed the most vulnerable females, even in very conservative communities, to participate in vocational training. / - School club activities are essential for the quality of education, strengthening the relationship between teachers and students and providing thematic activities such as on the environment, HIV, or gender-based violence. / - Intensive consultation and capacity-building activities with government counterparts at the beginning of the project are important to ensure buy-in and ownership, increasing the likelihood of sustainability. / - Capacity building and sensitization interventions and the institutionalization of training are most effective when top managers or participants are involved, enabling swift decision-making and progress. / - Capacity building interventions are most effective when needs-based and contextualized. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2021_Post-Facto 8 Completed Projects_Eval.pdf | Country standardized: 'Iran' -> 'Iran (Islamic Republic of)'. / Country standardized: 'Vietnam' -> 'Viet Nam'. |  |
| Strengthening national capacity for the implementation of the Global HIV Prevention Coalition Roadmap | 2020 |  | Botswana, Kenya, Lesotho, Malawi, Namibia, Uganda, Zambia, Zimbabwe | - Consider a no-cost extension to enable utilisation of the unexpended funds to contribute to the impact and sustainability of results and, as part of this, consider funding a coordination post within country prevention coalitions. / - Reduce the reporting burden required for accountability of budget expenditures in order to reduce the level of effort required for compliance. / - Increase justified flexibility between budget lines to ensure optimal impact of expenditures according to emerging needs. / - Ensure effective project oversight and management with contingency planning and consolidated hand-over when staff change. / - Once the above is in place, and with redesigned costed work plans, apply for a no-cost extension to the end of 2021, based on specific priorities in the project countries. / - If feasible, consider contributing project funding for a full-time staff coordination post for prevention within country coalitions, either within the NAC or UNAIDS country office (this also aligns with a recommendation from the GPC review), e.g. UNV, and/or long-term consultancy positions; and seek to mobilise additional funding from other sources for dedicated prevention staff. / - Consider again sub-contracting/engaging ATHENA Initiative to augment further the capacity development among young women leaders in the focal countries to consolidate their impact. / - Consider whether to widen the focus to additional countries should any remain significantly behind regarding building leadership capacity among adolescent girls and young women. Weigh this against the benefit of consolidating gains in the existing countries and providing robust lessons for south to south learning to feed into existing GPC initiatives (such as the NAC community of practice and the South to South Learning Network). / - To improve efficiencies, should there be a no-cost extension, designate a staff member to oversee project implementation and put in place a robust hand-over mechanism in the event of staff changes. / - Identify funding needs to address gaps in capacity development, particularly among adolescent girls and young women, and develop a related capacity development and technical assistance plan. / - Continue to engage capacitated networks of adolescent and young women and implement mechanisms to provide them with small grants for specific events and activities. | - Even relatively small, short-term grants can be catalytic in impact and sustainability of results if timely, strategic and appropriately focused. / - Networks can be greatly strengthened by small, targeted grants for specific activities that build experience and credibility for effective management, and hence eligibility for other funding sources. / - The flexibility in use of project funds, while aligned to the original project objectives, was important in facilitating justified expenditures against changing work plans, and this should continue as good practice. / - Sufficient attention needs to be given to project oversight at both global and country levels, with sufficient hand over when staffing changes. / - Without first ensuring conformity with organisational rules and regulations and adequate oversight, available funds may not be efficiently utilised despite their high relevance to country needs. / - Care is needed to ensure that the mechanisms for utilisation of funds, e.g. for short-term consultancies, are not unduly burdensome, with respect to both initial budget lines and to opportunities for expenditure. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/6. Peace and Development TF/8. Funded projects/Evaluations_Fin. Rep/2020_PDF-SDG-2017-06_Eval_UNAIDS.pdf |  | evaluations.xlsx row 253: Divisions not provided. |
| Smooth transition beyond graduation for least developed countries in Africa, Asian and the Pacific in a post-COVID-19 environment | 2026 | EAPD | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | - Where future programming allocates resources for it, build in structured post-delivery follow-up support for STS implementation. / - Require a written letter of commitment and interest from the government as a prerequisite for in-depth ePing training, to ensure that engagement is demand-driven and institutionally anchored from the outset. In addition, maintain the tripartite UNDESA–WTO–ITC coordination model as the delivery framework for future ePing support. / - Systematically integrate RCOs as operational partners in future multi-country projects. / - Strengthen UN system coordination and link STS processes to implementation and financing pathways. / - Incorporate flexible, demand-responsive analytical support within future projects. | - National ownership is the single most important determinant of results. Projects supporting LDC graduation are most effective and sustainable when anchored in strong national leadership, clear institutional mandates, and existing coordination mechanisms. / - Embedding transition strategies into existing systems enhances sustainability. Good practice was observed where STS priorities were integrated into national development plans, budgets, and monitoring systems. / - Depth of engagement matters more than breadth for technical tools. The ePing experience shows that intensive, hands-on training with follow-up produces durable behavioural change, while lighter engagement yields limited results. Training-of-Trainers models are particularly effective for sustainability. / - Flexibility and adaptive management are essential in volatile contexts. The project demonstrated that the ability to adapt activities, sequencing, and resource allocation in response to shocks is critical for maintaining relevance and efficiency in multi-country programmes. / - Modest resources can deliver meaningful results when well-targeted. Despite a relatively small budget, the project achieved substantial outputs and early outcomes by leveraging partnerships, aligning with national priorities, and focusing on catalytic interventions. / - Efficiency gains can be significantly enhanced when global technical assistance is anchored within existing UN country coordination structures. Integrating implementation through RCO platforms enables faster stakeholder mobilisation, improved alignment with national priorities, and sustained follow-up between missions. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/2225B_ SB-019218 LDC Graduation/Final Evaluation/DA14_project_evaluation Final EAPD 17June2026.pdf |  |  |
| Smooth transition beyond graduation for least developed countries in Africa, Asia and the Pacific in a post-COVID-19 environment | 2026 | EAPD | Bangladesh, Lao People's Democratic Republic, Senegal, Solomon Islands, Vanuatu, Zambia | - Where future programming allocates resources for it, build in structured post-delivery follow-up support for STS implementation. / - Require a written letter of commitment and interest from the government as a prerequisite for in-depth ePing training, to ensure that engagement is demand-driven and institutionally anchored from the outset. In addition, maintain the tripartite UNDESA–WTO–ITC coordination model as the delivery framework for future ePing support. / - Systematically integrate RCOs as operational partners in future multi-country projects. / - Strengthen UN system coordination and link STS processes to implementation and financing pathways. / - Incorporate flexible, demand-responsive analytical support within future projects. | - National ownership is the single most important determinant of results. Projects supporting LDC graduation are most effective and sustainable when anchored in strong national leadership, clear institutional mandates, and existing coordination mechanisms. / - Embedding transition strategies into existing systems enhances sustainability. Good practice was observed where STS priorities were integrated into national development plans, budgets, and monitoring systems. / - Depth of engagement matters more than breadth for technical tools. The ePing experience shows that intensive, hands-on training with follow-up produces durable behavioural change, while lighter engagement yields limited results. Training-of-Trainers models are particularly effective for sustainability. / - Flexibility and adaptive management are essential in volatile contexts. The project demonstrated that the ability to adapt activities, sequencing, and resource allocation in response to shocks is critical for maintaining relevance and efficiency in multi-country programmes. / - Modest resources can deliver meaningful results when well-targeted. Despite a relatively small budget, the project achieved substantial outputs and early outcomes by leveraging partnerships, aligning with national priorities, and focusing on catalytic interventions. / - Efficiency gains can be significantly enhanced when global technical assistance is anchored within existing UN country coordination structures. Integrating implementation through RCO platforms enables faster stakeholder mobilisation, improved alignment with national priorities, and sustained follow-up between missions. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/EAPD/2225B_ SB-019218 LDC Graduation/Evaluation report/DA14- Final Evaluation Report-21-04-2026.docx |  |  |
| Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities | 2014 | DSPD | Ethiopia, Kenya, South Africa, Zambia | - Schedule a further phase of collaboration to implement activities that were planned but not completed, including follow up visits to project countries. / - Introduce former participants to the new Toolkit modules and updated package developed. / - Support the establishment or development of national multi-stakeholder committees to monitor, report and implement provisions of the CRPD. / - Work with participants of the ToT Workshops to support them to develop training plans and strategies. / - Support training of key target groups identified by local stakeholders including parliamentarians and the judiciary. / - Appoint and agree terms of reference for a national consultant in each country to support training activities. / - Follow up with local UN agencies to ensure their involvement in customising the toolkit for the local context. / - Further develop the Toolkit, including making it user friendly, adding video resources, developing detailed session plans, and creating trainers and participant manuals. / - Carry out a review process involving experts on each topic to ensure and improve the quality of the Toolkit content. / - Request relevant UN agencies and DPO experts to review specific Toolkit modules for quality and completeness. / - Include references to key websites within each module topic to allow trainers to expand their knowledge. / - Develop and implement a strategy for introducing the Toolkit to new countries, including establishing a local working group and understanding local coordination mechanisms. / - Extend the ToT by at least one day and consider a further stage where trainees train others under observation. / - Develop 'Master Trainers' in each country or region to carry out training of trainers and monitor training quality. / - Develop accessible multimedia training materials and make modules available through an e-learning tool. / - Simplify the language and structure of the Toolkit and provide materials in alternative and accessible formats. / - Engage with DPOs and provide resources for their involvement. / - Follow up with organizations and departments after training to assess changes made. | - A clear brief for the toolkit style at the outset could have saved time and resources and made it easier to use multiple consultants. / - Developing one initial module and reviewing it to agree on style, language, and complexity could have benefited the development process. / - UNDESA is now well positioned to develop a strategy for introducing the Toolkit to new countries and guiding local customisation. / - Strong local counterparts are essential to ensure activities can progress, as shown by challenges in Ethiopia due to lack of local commitment. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/5 - DEVELOPMENT ACCOUNT/DA - DESA/03 PROJECTS - CLOSED/DISD/ROA-180-CRP with Disabilities/Final & evaluation reports/EvalReport_UNDESA_FINAL_CC_140111.pdf |  | evaluations.xlsx rows 299 (archived) and 283 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Ethiopia; Kenya; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DSPD'; Evaluation Year differs: archived row has ''; retained row has '2014'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| Africa i-Parliaments Action Plan: Outcome Mapping of the support for the Africa Parliamentary Knowledge Network (APKN) | 2012 | DPIDG | Egypt, Kenya, Mauritius, Mozambique, Nigeria, South Africa, Uganda, Zambia | - The Executive Committee and the APKN Secretariat should be more active in promoting ownership of the APKN, leveraging existing mechanisms and forums. / - Solicit the involvement of the Pan African Parliament or regional parliaments to use the APKN portal as their virtual platform to increase active participation. / - Adopt the outcome mapping approach as an integral part of planning, monitoring, and evaluating APKN activities. / - Promote e-learning among parliamentary leadership to demonstrate its usefulness and cost-effectiveness. / - Motivate parliamentary leadership to contribute knowledge to the Network using APKN tools. / - Develop a networking culture among parliamentary leadership, especially promoting online networking. / - Promote the value of professionalism and continuous education among parliamentary staff and Members of Parliament. / - Develop awareness programs to highlight the importance of learning from and contributing to the Network. / - Provide incentives through a rewarding system or mechanisms that encourage participation in APKN activities. / - Develop awareness programs to familiarize and empower parliamentary staff and Members of Parliament to use e-learning and collaborative tools. / - Build the capacity of Members and staff to effectively use e-learning and collaborative tools. / - Encourage parliaments to establish APKN Centres in their libraries equipped with necessary multimedia tools. / - Empower parliaments with limited capacity to provide needed ICT infrastructure and Internet connectivity. / - APKN Secretariat/Executive Committee should identify and implement quick win activities immediately and consistently. / - Provide for a dedicated APKN Secretariat hosted at the Pan African Parliament to manage day-to-day activities. / - Collaborate with knowledge partners who can undertake activities, sometimes using their own resources. | - Ownership by national and regional parliaments is critical for the success and sustainability of the APKN. / - E-learning and online collaboration tools require greater appreciation and familiarity among parliamentary leaders and staff. / - Motivation and incentives are necessary to encourage participation and knowledge contribution from parliamentary staff and Members. / - Effective use of e-learning and collaborative tools depends on building capacity and awareness among users. / - Adequate ICT infrastructure and Internet connectivity are prerequisites for full participation in APKN activities. / - A low number of activities can hinder the visibility, relevance, and usefulness of the APKN to parliaments. / - Strategic withdrawal of external support should be matched with strengthened internal governance and ownership to maintain momentum. | https://unitednations.sharepoint.com/sites/DESA-CDPMO/Shared Documents/General/3. Finance Management/1 - TC PROJECTS/Closed Projects in Umoja/S1-67_RAF 08X01 - Africa i-Parl Plan/RAF 08X01 - Final Evaluation/APKN Outcome Mapping - Evaluation Report_December.pdf |  |  |

Data Quality Notes

| # | Note |
| --- | --- |
| 1 | activity.xlsx record 'SB-001380.88¦row:6': '#Policies' has non-numeric value 'more effective use of tax policy and administration as a lever for sustainable development and improved domestic resource mobilization'. |
| 2 | evaluations.xlsx record 'row:206': Country text 'French Guiana' could not be matched; no country assignment was inferred. |
| 3 | evaluations.xlsx row 253: Divisions not provided. |
| 4 | evaluations.xlsx rows 230 (archived) and 156 (retained): Review conflicts: Countries differs: archived row has 'Ghana; Brazil; China; Cambodia; Myanmar; Philippines; Ethiopia; India; Kenya; Serbia; USA; Thailand; Japan; Belgium; Korea'; retained row has 'Ghana; Ethiopia; India; Kenya; Serbia; Cambodia; Myanmar; Philippines; Brazil; China; USA; Thailand; Japan; Belgium; Korea; Uganda; Pakistan; Rwanda; Zambia; Madagascar; Mozambique; Cambodia'; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 5 | evaluations.xlsx rows 236 (archived) and 161 (retained): Review conflicts: Countries differs: archived row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; Panama; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Algeria; Bosnia and Herzegovina; Ghana; Guyana; Honduras; Malawi; Nigeria; France; Denmark; Spain; Brazil; Paraguay'; retained row has 'Kenya; Pakistan; Ethiopia; Bolivia; Colombia; United Arab Emirates; India; Italy; Lebanon; Poland; Portugal; United Kingdom; Zambia; Argentina; Austria; Bulgaria; Ecuador; North Macedonia; Morocco; Niger; Papua New Guinea; Samoa; Seychelles; Georgia; Bosnia and Herzegovina; Ghana; Guyana; Algeria; Honduras; Malawi; Nauru'; RecommendationsList differs between document copies. Country lists were not merged. |
| 6 | evaluations.xlsx rows 285 (archived) and 206 (retained): Review conflicts: Countries differs: archived row has 'Angola; Argentina; Bahamas; Bangladesh; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Comoros; Costa Rica; Djibouti; Dominican Republic; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; retained row has 'Angola; Argentina; Bahamas; Barbados; Benin; Bolivia; Botswana; Burundi; Cambodia; Cameroon; Chad; Chile; Comoros; Costa Rica; Dominican Republic; Djibouti; Ecuador; El Salvador; Ethiopia; French Guiana; Gabon; Gambia; Ghana; Guatemala; Honduras; Indonesia; Jamaica; Kenya; Lao People's Democratic Republic; Lesotho; Liberia; Madagascar; Malawi; Mali; Mauritius; Mexico; Mongolia; Morocco; Mozambique; Namibia; Nepal; Nicaragua; Niger; Nigeria; Pakistan; Panama; Paraguay; Peru; Philippines; Rwanda; Samoa; Senegal; Seychelles; Sierra Leone; South Africa; Sri Lanka; Suriname; Swaziland; Tanzania; Thailand; Togo; Trinidad and Tobago; Uganda; United Republic of Tanzania; Uruguay; Viet Nam; Zambia; Zimbabwe'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 7 | evaluations.xlsx rows 295 (archived) and 217 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Afghanistan; Bangladesh; Bhutan; Cambodia; Chile; China; India; Indonesia; Kazakhstan; Korea; Lao People's Democratic Republic; Lesotho; Myanmar; Nepal; Philippines; Singapore; South Africa; Sri Lanka; Swaziland; Tajikistan; Thailand; Uzbekistan; Vietnam; Zambia; Botswana; Mozambique; Namibia; Botswana; Mozambique; Namibia; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DPAD'; Evaluation Year differs: archived row has ''; retained row has '2015'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 8 | evaluations.xlsx rows 299 (archived) and 283 (retained): Review conflicts: Countries differs: archived row has ''; retained row has 'Ethiopia; Kenya; South Africa; Zambia'; Divisions differs: archived row has ''; retained row has 'DSPD'; Evaluation Year differs: archived row has ''; retained row has '2014'; RecommendationsList differs between document copies; LessonsLearnedList differs between document copies. Country lists were not merged. |
| 9 | GeoData_with_ISO3166_alpha3.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |
| 10 | proposals.xlsx record 'SB-001376.99.99.23¦row:30': 'f_cashOther' has non-numeric value 'Eurostat provides a grant of 53,000 USD to improve and maintain TDT in 2026. The African Union Commission (AUC) will cover the participation cost of its selected member states.'. |
| 11 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costConferenceServices' has non-numeric value '0 (UNECA will finance)'. |
| 12 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelConsultants' has non-numeric value '6,989 (3 experts: OPHI, EPRI, South Africa statistician)'. |
| 13 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'costTravelParticipants' has non-numeric value '19,152 (2 representatives for each of the 4 participant countries)'. |
| 14 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashDESA' has non-numeric value 'DISD to support the participation of 8 policymakers from Namibia, Tanzania, Senegal and Zambia. In addition, DISD will support the participation of 3 resources persons (one from Colombia, one from South Africa and one from the USA)'. |
| 15 | proposals.xlsx record 'SB-001379.99.30¦row:47': 'f_cashOther' has non-numeric value 'UNECA has allocated about US$27,000 to this workshop to support the travel of 17 participants from Ghana, Djibouti, Rwanda, Kenya, Ethiopia, Uganda.'. |
| 16 | requests.xlsx record '4731': Dates End date 2022-01-12 is before start date 2022-06-01. |
| 17 | requests.xlsx record '4731': End date 2022-01-12 is before start date 2022-06-01. |
| 18 | requests.xlsx record '4741': Countries Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 19 | requests.xlsx record '4741': Countries Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 20 | requests.xlsx record '4741': Countries Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 21 | requests.xlsx record '4741': Country 'Mayotte' could not be matched to an ISO3 value. |
| 22 | requests.xlsx record '4741': Country 'Reunion' could not be matched to an ISO3 value. |
| 23 | requests.xlsx record '4741': Country 'Saint Helena' could not be matched to an ISO3 value. |
| 24 | requests.xlsx record '4741': Country text 'Mayotte' could not be matched; no country assignment was inferred. |
| 25 | requests.xlsx record '4741': Country text 'Reunion' could not be matched; no country assignment was inferred. |
| 26 | requests.xlsx record '4741': Country text 'Saint Helena' could not be matched; no country assignment was inferred. |
| 27 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 100 removed; retained row 46 (Strengthening capacity of national policy analysts in the social and economic sectors of developing countries in the production and use of National Transfer Accounts). |
| 28 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 106 removed; retained row 88 (Implementation of national sustainable development strategies in selected countries in Africa and Latin America). |
| 29 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 14 removed; retained row 8 (Strengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development GoalsStrengthening national policy capacities for jointly building the Belt and Road towards the Sustainable Development Goals). |
| 30 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 151 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 31 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 158 removed; retained row 30 (Strengthening the capacity of governments and youth employment stakeholders in Africa in the implementation, monitoring and evaluation of policies and programmes promoting decent jobs for youth). |
| 32 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 171 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 33 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 185 removed; retained row 53 (Capacity-building for removing constraints in utilizing trade-related international support measures for Least Developed Countries). |
| 34 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 199 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 35 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 211 removed; retained row 209 (Supporting Member States in developing and strengthening environment statistics and integrated environmental-economic accounting for improved monitoring of sustainable development). |
| 36 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 216 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 37 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 218 removed; retained row 153 (Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level). |
| 38 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 221 removed; retained row 187 (Strengthening capacity of National Tax Administrations of Developing Countries in Latin America to reduce Tax Transaction Costs and thereby maximize tax revenues). |
| 39 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 230 removed; retained row 156 (Mobilizing Science, Technology and Innovation in developing countries for the SDGs). |
| 40 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 236 removed; retained row 161 (Accelerating the achievement of SDG7: Enhancing capacities and South-South cooperation in support of SDG7 review, follow up and implementation). |
| 41 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 243 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 42 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 249 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 43 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 252 removed; retained row 38 (Strengthening capacities of Developing Countries to provide access to Information for sustainable Development through Open Government Data). |
| 44 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 268 removed; retained row 5 (Strengthening the capacity of Least Developed Countries to develop evidence-based, coherent and well-financed strategies to implement the 2030 AgendaStrengthening the capacity of least developed countries to develop evidence-based, coherent and well financed strategies to implement the 2030 Agenda). |
| 45 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 282 removed; retained row 127 (Evaluation of the United Nations Centre for Regional Development (UNCRD)). |
| 46 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 285 removed; retained row 206 (Strengthening Capacity of National Tax Administrations in Developing Countries to Effectively Negotiate and Apply Double Tax Treaties for Financing of Sustainable Development). |
| 47 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 287 removed; retained row 201 (Integrating Climate Change into National Sustainable Development Strategies and Plans in Latin America and the Caribbean). |
| 48 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 288 removed; retained row 200 (Supporting the establishment of a Latin American Parliamentary Knowledge Network). |
| 49 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 295 removed; retained row 217 (Supporting Finance and Planning Authorities to Formulate and Implement Macroeconomic Policies). |
| 50 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 298 removed; retained row 220 (Strengthening National Capacity for the Integration of Sustainable Development Principles into Development Strategies in Countries Emerging from Conflict). |
| 51 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 299 removed; retained row 283 (Building Capacities of Governments to Mainstream Disability in Africa to Promote Implementation of the Convention on the Rights of Persons with Disabilities). |
| 52 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 306 removed; retained row 297 (). |
| 53 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 332 removed; retained row 302 (). |
| 54 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 42 removed; retained row 19 (Strengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goalsStrengthening the capacities of selected African countries to develop geospatial information resources and services in support of the implementation and monitoring of the sustainable development goals). |
| 55 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 55 removed; retained row 2 (Enhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employmentEnhancing capacity of developing countries to achieve sustainable agriculture through the transfer of Juncao technology for alleviating poverty and promoting productive employment). |
| 56 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 65 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 57 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 72 removed; retained row 3 (Enhancing National Capacities for Unleashing Full Potentials of Micro-, Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing CountriesEnhancing National Capacities for Unleashing Full Potentials of Micro- Small and Medium-sized Enterprises (MSMEs) in Achieving the SDGs in Developing Countries). |
| 58 | Resolved - Action: duplicate evaluation at evaluations.xlsx row 86 removed; retained row 75 (Addressing COVID-19 and Sustainable Investments along the Belt and Road by Strengthening Partner Countries’ Capacities and Establishing a Network of Sustainable Investment Promotion (SIP) Facilities with Serbia as an Early Pilot). |
| 59 | Resolved - Action: pipeline row (Advancing Gender Empowerment and Innovation for Latin America and Caribbean. ¦ [2629B]) skipped; retained the existing project with the same title. |
| 60 | Resolved - Action: pipeline row (Beyond GDP: Advancing global and national initiatives to develop, compile and integrate beyond-GDP metrics to foster inclusive, sustainable, and forward-thinking policy making ¦ [no id]) skipped; retained the existing project with the same title. |
| 61 | Resolved - Action: pipeline row (Developing Strategic Foresight Capacities for Anticipatory Governance to Promote Resilience and Sustainable Development in selected Pacific SIDS ¦ [no id]) skipped; retained the existing project with the same title. |
| 62 | Resolved - Action: pipeline row (Enhanced Statistical Capacity for Data Governance and Innovation Across National Data Ecosystems ¦ [2629A]) skipped; retained the existing project with the same title. |
| 63 | Resolved - Action: pipeline row (Evidence-based Climate Action through Artificial Intelligence and Data Innovation for Caribbean SIDS ¦ [2528A]) skipped; retained the existing project with the same title. |
| 64 | Resolved - Action: pipeline row (Identifying and addressing vulnerabilities to aggressive tax avoidance in developing countries ¦ [2427H]) skipped; retained the existing project with the same title. |
| 65 | Resolved - Action: pipeline row (Inclusive and sustainable economic growth in a society for all ages in the post-COVID-19 era in Asia and Latin America and the Caribbean. ¦ [2326A]) skipped; retained the existing project with the same title. |
| 66 | Resolved - Action: pipeline row (Innovation, Digital Government Transformation and Changing Mindsets in the Caribbean SIDS ¦ [2427J]) skipped; retained the existing project with the same title. |
| 67 | Resolved - Action: pipeline row (Innovative and digital technologies for forest monitoring and data-sharing by Indigenous Peoples, local communities, women and young people ¦ [2629C]) skipped; retained the existing project with the same title. |
| 68 | Resolved - Action: pipeline row (Localizing the SDGs through more resilient, inclusive, and sustainable infrastructure ¦ [no id]) skipped; retained the existing project with the same title. |
| 69 | Resolved - Action: pipeline row (Strengthening Capacity for evidence-based Social Protection Policies for responding to the triple global crisis in fuel, food and finance ¦ [2427A]) skipped; retained the existing project with the same title. |
| 70 | Resolved - Action: pipeline row (Strengthening capacity for evidence-informed policymaking: from inclusive data to inclusive policy for responding to national and global crises ¦ [2427I]) skipped; retained the existing project with the same title. |
| 71 | Resolved - Action: pipeline row (Strengthening local and national government capacities for SDG localization in Africa ¦ [no id]) skipped; retained the existing project with the same title. |
| 72 | Resolved - Action: pipeline row (Turning the tide on deforestation-Building partnerships to combat intensifying impacts of climate change, forest fires and zoonotic diseases ¦ [2326C]) skipped; retained the existing project with the same title. |
| 73 | unct.xlsx: last modified 2026-05-22, more than 30 days before ingestion (134 days). |